## High Level Timeline
| July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June
Task | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-20 | 2025-12-27 | 2026-01-01 | 2025-01-06 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2025-02-01 | 2025-02-08 | 2025-02-22 | 2026-02-28 | 2025-03-01 | 2026-03-08 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26
Design
Phase 1: Analysis & Redesign
Binder Check 1
TM-26 Initial CAD
System Leads Check 1
Phase 2: Prototyping
Binder Check 2
Finish Troubleshooting TM-25
Detailed TM-26 CAD
Track Testing
System Leads Check 2
Phase 3: Simulation & Optimization
Rules Check 1
Design Review 1
Manufacturing Sponsor Checkpoint
Litens Design Review 1 (EP System Only)
Design Concept Freeze
System Leads Check 3
Finalize CAD
Design Review 2
Alumni Design Review 2
Rules Check 2
ESF and SES Submission
Litens Design Review 2 (EP System Only)
Fasteners and Clearance
Final design freeze
Phase 4: Manufacturing and Validation
Send Out Frame and Frame Jigs
Accumulator Sendout
Detailed Manufacturing & Assembly Plan
Procurement Round 1
Sending Out Orders 1
Laser Cut/Water jet Sendout
Procurement Round 2
Sending Out Orders 2
Phase 5: Competition Preparations
Electric Powertrain
battery pack sizing decision
container material and joining methods decision
Busbar and fusible link documentation finalization
Riveting
Bending Bus bars
Segment completion
Accumulator Harness
Accumulator Container fully assembled
Accumulator testing
Wiring Harness - LV
Order the VCU and Discharge PCBs
Assemble HV cables
Print Enclosers
Assemble Enclosers
Mockup Container
Segment Improvement
Select New Dash Solution
Finalize Redesign of VCU
Select Vehicle Sensors
Finalize Sensor Integration Concepts
Wiring CAD
Updates to Vehicle Boards
Board Testing
Develop Standardization Documentation
Aerodynamics
CFD CAD TM25 Baseline - 1. Curved Front Endplate
CFD CAD Baseline - 2. Gurney Flaps
CFD CAD Baseline - 3. Undertray with Diffusers
CFD CAD Baseline - 4. Vortex Generators
CFD CAD - 5. Vertical FW Elements and Canards
Deciding if we want undertray
Finalizing Airfoil selection
Setting a downforce goal
Adjusting for suspension
Deciding number of elements (FW and RW)
RW endplates designed
FW endplates designed
FW CFD runs
RW CFD runs
Mold material selection
Mold manufacturing method selected
Nosecone finalized
Bodywork finalized
Finalizing FW Main element Height from Ground
Finalizing RW X & Y positioning
Additional devices designed
Designing radiator
FW Mold(s) designed
RW Mold(s) designed
Nosecone Mold(s) designed
Whole car CFD runs
Designing Radiator mounts
Designing Radiator Duct
Radiator Duct Testing
Designing Fan shroud
FW and RW internal rib structures
FW Mounts
FW Mounts FEA
RW Mounts
RW Mounts FEA
Nosecone CFD run
Nosecone Mounting
Aero Manufacturing
Sanding main element, rear wing
Sanding completed
Priming - 29/30 Sat/Sun
Gel coating -5/6
Front wing Infusion layups
Rear wing Infusion layups
Nose cone Infusion layups
Leading edges fixing
complete manufactuing
Nosecose
Bodywork
Livery
Cad for endplate
Mounts/Endplates waterjet
Frame Tabs - Inhouse
Rib structures printed
Vehicle Dynamics
Ergo Rig Built
Tire Analysis Complete (Tires Chosen)
Initial Frame Design
Initial Suspension Design
Uprights Designed
Detailed Frame Design
Drivetrain Packaged
Suspension Complete
Uprights Sent out
Steering Complete
Brakes Complete
Frame sub complete
Frame Tabs Designed
Final Frame Design
Frame Sendout
Manufacturing
Tack Frame
Weld Frame
Weld Tabs
Bellcrank/Uprights Machined
Rolling Chassis
Waterjet/bend Accumulator + Secondary Mahcining Items (Viking)
Tack Accumulator
Weld Accumulator
Secondary Welding Items Complete
Molds Sendout (Fw, Rw, Seat, Nosecone)
Undertray Mold Sendout
3D Print Aero Molds
Waterjet Carbon
Mold Prep
Cooling Tabs Machined
Carbon Layup
Procuring EP Materials
Machine FR4
Segment Assembly
Wiring
Cell Tap PCB Board
VCU
GLV
Stress test the accumulator (Charging Cycling)
Saftey Shutdown Circuit
Final Check Week Before Fire Up Day
Fire Up
Testing
Shakedown Day
Dyno Testing
Competition Documents
ESF Submission 1
ESF Submission 2
ESF Final Submission
ESO/ESA Document Final Submission
SES Submission 1
SES Submission 2
SES Final Submission
Design Spec Sheet
Design Review Briefing
Design 3 View Drawing
Business Presentation Online Event
Cost Report Submission
Pre Comp Accumulator Video
Fast Track Roster Deadline
Project Management
Confirm new ESA
Renew Sponsors
Prototyping procurement ready
Run Solidworks Certification
Run HV training and inperson Eval
Recommendation to talk to WiE and get our design team events on their budget
Recommendation to begin planning the WiE event
Student Group Summit
Engineering Expo
Renew Solidworks License
Plan a Team Drive Day if possible
Submit Student Group Status Form
Budget Proposal
Travel Request Form
Student Group Agreement
Send budget request to Mech Department
Send budget request to ECB Department
Recommendation to have 1st WiE event (panelist event)
Apply to Alan Shepard Equity Diversity and Inclusion Award on Awardspring
Student Group Budget Meeting
Register for Competition
Get all leads and apparentices required to submit their Visa and passport renewal
New Member orientations
Register for UFT Shootout
Reach out to teacher for AWIM
Book Unveiling Date and venue
Recommendation to send out unveiling save the dates
Confirm all Insurance for testing tacks is renewed
Get team 24 hour and holiday card access to school for winter break
Start Mentorship program
Inital Attendie List for Michigan
International Risk Forms
Identify any new members that may need to apply for a visa to go to michigan or double check all passports
Hotel rooms and cars booked by FEAS
Recommendation to have 2nd WiE event (eng expo)
Recommended selling period for apparel
Recommended selling period for unveiling
Register for Pittsburgh Shootout
Get entire team to apply to NOR awards
Final attendies list for michigan
Final International risk forms
Travel BioData
Apply to competition awards on fsaeonline
Recommended team building go karting day
Send out Competition and Season Summary Newsletter
Year In Review
Livery
Design submissions are open.
Design submissions closed, voting open
Voting closed, design chosen
Proper mockup in Illustrator finalized
For render CAD File Complete
For-render CAD File made 'lightweight' and exported
Livery Design added onto car in Solidworks
Final CAD render with Livery finalized and exported
Sponsor logos added onto TM-26 in Illustrator
Mockup & Individual image files sent to sponsor. Sponsor begins work.
Vinyl delivered, applied to TM-26
Recruitment
First semester: Applications Open
First semester: Applications closed & reviewed
First semester: Interviews held
First semester: Hirees selected, acceptance/rejection letters sent out
Second semester: Applications Open
Second semester: Applications closed & reviewed
Second semester: Interviews held
Second semester: Hirees selected, acceptance/rejection letters sent out

## Timeline
[6 empty] | DECEMBER | [11 empty] | January | [30 empty] | FEBRUARY
[6 empty] | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
[6 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Task |  | Date | Responsible | Status | Comment
Milestones |  |  |  |  | Use: https://www.fsaeonline.com/Deadlines.aspx?seriesCode=FSAE | DECEMBER Wed 20: July; DECEMBER Sun 24: August; DECEMBER Fri 29: September; January Tue 2: October; January Sun 7: November; January Thu 11: December; January Mon 15: January; January Sat 20: February; January Wed 24: March; January Sun 28: April; FEBRUARY Thu 1: May; FEBRUARY Tue 6: June
ESF Submission |  | 2024-12-09 | EP Team | Waiting |  | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-20 | 2025-12-27 | 2025-01-06 | 2026-01-09 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-22 | 2026-02-28 | 2025-03-01 | 2026-03-08 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26
ESO/ESA Form Submission |  | 2025-01-06 | EP Team | Waiting
SES Submission |  | 2025-01-13 | Team | Waiting
Business Request for Proposal |  | 2024-01-27 | Team | Waiting
Design 3-View Drawings |  | 2025-05-05 | Team | Waiting
Design Briefing |  | 2025-05-05 | Team | Waiting
Design Spec Sheet |  | 2025-05-05 | Team | Waiting
Cost Report |  | 2025-05-12 | Team | Waiting
Business Presenter Form |  | 2024-05-24 | Team | Waiting
Fast Track Roster |  | 2025-05-25 | Team | Waiting
Pre-Tech Accumulator Video |  | 2025-06-02 | Team | Waiting
EP - Electric Powertrain
Key Milestones
Task | Start Date | Due Date | Responsible | Status | Comment
GLV wiring
Rapid harness review / finalization | 2025-01-11 | 2025-01-18 | Nathan | Complete | design review this weekend | bar: January Wed 17 to January Thu 18
Procurement review and ordering | 2025-01-11 | 2025-01-18 | Nathan | In Progress | bar: January Wed 17 to January Thu 18
Solidworking routing design - front paths routed - rear paths routed | 2025-01-19 | 2025-02-01 | Nathan | In Progress | bar: January Thu 18
Wiring workspace construction - mounting blank working surface - printing out rapidharness connector details - correctly spacing and attaching connector details - design reference here - adding removable zipties for temporary wire placement | 2025-02-02 | 2025-02-22 | Nathan | In Progress | bar: January Thu 18 to January Fri 19
Rear harness construction | 2025-02-02 | 2025-02-22 | Nathan | Waiting | bar: January Fri 19 to January Mon 22
Front harness construction | 2025-02-02 | 2025-02-22 | Nathan | Waiting | bar: January Fri 19 to January Mon 22
harness testing/validation | 2025-02-23 | 2025-02-26 | Nathan | Waiting | bar: January Sun 21 to January Mon 22
harness cleanup / conduit |  |  | Nathan | Waiting
harness installation in car | 2025-02-26 | 2025-03-01 | Nathan | Waiting | bar: January Tue 23
Segment Construction
FR4 precut to size |  |  |  | Complete | bar: January Wed 17
FR4 CNC'd |  |  |  | Waiting | bar: January Wed 17 to January Fri 19
small segment prototype - finalizing the column lengths, PCB fixture quality, 3D printed sheet vs soft glue |  |  |  | Complete | bar: January Wed 17; January Sat 27
3D print segment caps and supporting columns - and install heat set inserts |  |  |  | Waiting | bar: January Thu 18
Segment bracket + cells assembly - install cells with some removable adhesive into cell holders - attach bracket pieces with fasteners/ glue |  |  |  | Waiting | bar: January Fri 19 to January Sat 20
Segment pole busbars installed |  |  |  | Waiting | bar: January Sat 20 to January Sun 21
Segment PCB order and arrival |  |  |  | Waiting | bar: January Fri 19
Segment PCB cosntruction |  |  |  | Waiting | bar: January Sat 20 to January Sun 21
Segement PCB validation |  |  |  | Waiting | bar: January Sun 21
Segment pcb installed |  |  |  | Waiting | bar: January Sun 21
nickel cell interconnects spot welded |  |  |  | Waiting | bar: January Sun 21
temperature sensors installed |  |  |  | Waiting | bar: January Sun 21
Solder wire connections to pcb |  |  |  | Waiting | bar: January Sun 21
insulate top of pcb |  |  |  | Waiting | bar: January Sun 21
Battery Pack
Finalize shelf component poistion/mounting in CAD |  |  |  | Waiting | bar: January Thu 18
Add routing paths inside accu in CAD |  |  |  | Waiting | bar: January Thu 18 to January Fri 19
Wiring workspace construction - mounting blank working surface - printing out rapidharness connector details - correctly spacing and attaching connector details - design reference here - adding removable zipties for temporary wire placement |  |  |  | Waiting | bar: January Thu 18 to January Fri 19
BMS enclosure design complete |  |  |  | Waiting | bar: January Thu 18
BMS enclosure 3D printed |  |  |  | Waiting | bar: January Fri 19
BMS assembly construction |  |  |  | Waiting | bar: January Sat 20
shelf component placement complete, DXF complete |  |  |  | Waiting | bar: January Fri 19
shelf manufacturing |  |  |  | Waiting | bar: January Sat 20
IR, fuse enclosure design complete |  |  |  | Waiting | bar: January Thu 18
IR enclosure 3D printed |  |  |  | Waiting | bar: January Fri 19
IR enclosure construction and wiring |  |  |  | Waiting | bar: January Sat 20
Cell tap harness construction |  |  |  | Waiting | bar: January Sat 20 to January Sun 21
Temperature sensor harness construction |  |  |  | Waiting | bar: January Sat 20 to January Sun 21
Main IO harness contruction |  |  |  | Waiting | bar: January Sat 20 to January Sun 21
Obtain voltage and temperature readings from segments through BMS |  |  |  | Waiting | bar: January Mon 22 to January Tue 23
Current sensor validation |  |  |  | Waiting | bar: January Mon 22 to January Tue 23
Individual segments to be cycled |  |  |  | Waiting | bar: January Mon 22 to January Tue 23
Validate operation of +ve IR through precharge |  |  |  | Waiting | bar: January Mon 22 to January Tue 23
Container
Waterjet Accumulator + Secondary Mahcining Items (Viking) |  |  |  | Waiting | bar: January Thu 18
Tack Accumulator |  |  |  | Waiting | bar: January Thu 18
Weld Accumulator |  |  |  | Waiting | bar: January Thu 18 to January Fri 19
Insulate accumulator |  |  |  | Waiting | bar: January Fri 19 to January Sat 20
Install Mesh |  |  |  | Waiting | bar: January Sun 21
Seal Accumulator |  |  |  | Waiting | bar: January Sun 21
Install Latches |  |  |  | Waiting
Tack + Weld Accumulator Mounts |  |  |  | Waiting | bar: January Thu 18 to January Fri 19
TS system & Enclosures
MC enclosure printed |  |  |  | Waiting | bar: January Thu 18
LV battery enclosure printed |  |  |  | Waiting | bar: January Thu 18
LV battery fitment test |  |  |  | Waiting | bar: January Thu 18
LV battery construction |  |  |  | Waiting | bar: January Thu 18 to January Fri 19
Rear Enclosure Printed |  |  |  | Waiting | bar: January Fri 19
Rear Enclosure construction |  |  |  | Waiting | bar: January Fri 19
Rear enclosure harness construction |  |  |  | Waiting | bar: January Fri 19 to January Sat 20
Waiting | bar: January Sat 20
Waiting
Waiting
Waiting
Waiting
Waiting
Waiting
Enclosures mounting to frame |  |  |  | Waiting | bar: January Mon 22
Waiting
PCBs
light board schematic completion |  |  |  | Waiting | bar: DECEMBER Thu 21; January Tue 16 to January Wed 17
Light board simulation |  |  |  | Waiting | bar: DECEMBER Fri 22
light board component selection |  |  |  | Waiting | bar: DECEMBER Fri 22
light board pcb design |  |  |  | Waiting
light board pcb component procurement |  |  |  | Waiting
light board assembly |  |  |  | Waiting
Light board testing / validation, debugging |  |  |  | Waiting
VCU pcb assembly |  |  |  | Waiting
VCU pcb testing |  |  |  | Waiting
Precharge resistor modifications |  |  |  | Waiting
Discharge board resistor modifications |  |  |  | Waiting
AR - Aerodynamics
Key Milestones
All molds designed | 2026-12-01 | 2026-01-20 |  | Complete
Procurement/Sendout Complete | 2026-01-05 | 2026-01-20 |  | Complete
Front wing completed | 2026-01-05 | 2026-03-27 |  | Waiting
Rear wing completed | 2026-01-05 | 2026-03-27 |  | Waiting
Nosecone completed | 2026-02-02 | 2026-04-10 |  | Waiting
Side panels completed | 2026-05-02 | 2026-05-02 |  | Waiting
Seat Completed | 2026-02-02 | 2026-04-10 |  | Waiting
Undertray Complete | 2026-01-05 | 2026-04-03 |  | Waiting
Cooling system assembled on car |  |  |  | Waiting
Front Wing
Molds Send out | 2026-01-05 | 2026-01-09 | Davis | Complete | Rough ETA is about 3-4 weeks out
Design and 3D print upper element molds | 2026-01-05 | 2026-01-23 | Davis | Delayed | Rough ETA is about 1 week out
Layup small elements | 2026-01-26 | 2026-02-13 | Aero Team | Waiting
Layup endplates | 2026-01-26 | 2026-02-13 | Aero Team | Waiting | Waiting on material
Weld tabs + print jigs | 2026-01-26 | 2026-02-13 | Yohana | Waiting | Waiting on material
Design and print front wing endplate inserts | 2026-01-26 | 2026-02-06 | Josiah | Waiting | Not urgent
Mold Prep | 2026-01-19 | 2026-02-13 | Aero Team | Waiting
Design and print loft section on front wing | TBD | TBD | Mahdi | Waiting
Design and print vortex generators | 2026-02-02 | 2026-02-13 | Shehreen | Waiting | Not urgent
Paint and de-burr the mounts | 2026-01-26 | 2026-01-30 | Dhruv | Waiting | Requires Viking Metal and Livery
Mold prep | 2026-02-16 | 2026-02-20 | Aero Team | Waiting
Layup main element | 2026-02-20 | 2026-03-20 | Aero Team | Waiting | Waiting on LRA3D
Sand/Post process | 2026-03-20 | 2026-03-27 | Aero Team | Waiting
Assemble Wing | 2026-03-20 | 2026-03-27 | Aero Team | Waiting
Rear Wing
Layup endplates | 2026-01-26 | 2026-02-13 | Aero Team | Waiting | Waiting on material
Mold prep | 2026-01-19 | 2026-02-13 | Aero Team | Waiting
Layup elements 1 and 2 | 2026-01-26 | 2026-02-13 | Aero Team | Waiting | Waiting on material
Weld tabs + print jigs | 2026-01-26 | 2026-02-13 | Yohana | Waiting | Waiting on material
Design and print vortex generators | 2026-02-02 | 2026-02-13 | Shathurjan | Waiting | Not urgent
Design and print rear wing endplate inserts | 2026-01-21 | 2026-02-06 | Jasmine | Waiting | End date TBC due to confirmation of capstone direction
Paint and de-burr the mounts | 2026-01-26 | 2026-01-30 | Dhruv | Waiting | Requires Viking Metal and Livery
Rear wing bottom tabs machined | TBD | TBD | Anisha | Waiting | Anisha to discuss with Luca
Mold prep | 2026-02-16 | 2026-02-20 | Aero Team | Waiting
Design and print tabs for endplate supports | 2026-01-19 | 2026-02-02 | Anisha | Waiting | Will work on with Mahdi
Layup main element | 2026-02-16 | 2026-03-20 | Aero Team | Waiting | Waiting on LRA3D
Sand/Post process | 2026-03-20 | 2026-03-27 | Aero Team | Waiting
Assemble Wing | 2026-03-20 | 2026-03-27 | Aero Team | Waiting
Undertray
Molds send out | 2026-01-05 | 2026-01-09 | Davis | Complete | Rough ETA is about 3-4 weeks out
Weld tabs + print jigs | 2026-01-26 | 2026-02-13 | Davis | Waiting | Waiting on material
Mold prep | 2026-02-16 | 2026-02-20 | Aero Team | Waiting
Layup undertray | 2026-02-16 | 2026-03-20 | Aero Team | Waiting | Waiting on LRA3D
Drill out holes for mounts | 2026-02-23 | 2026-03-27 | Aero Team | Waiting
Design and print inserts for tubes | 2026-02-23 | 2026-03-27 | Aero Team | Waiting
Sand/Post process | 2026-03-20 | 2026-03-27 | Aero Team | Waiting
Assemble Tubes | 2026-03-20 | 2026-03-20 | Aero Team | Waiting
Assemble Undertray | 2026-03-20 | 2026-04-03 | Aero Team | Waiting
Nosecone + Seat
Mold Prep | 2026-02-02 | 2026-02-13 | Aero Team | Delayed
Weld tabs + print jigs | 2026-01-26 | 2026-02-13 | Yohana | Waiting | Waiting on material
Seat and Nosecone Layup | 2026-02-16 | 2026-02-27 | Aero Team | Waiting
Sand/Post process | 2026-02-27 | 2026-03-04 | Aero Team | Waiting
Install magnets | 2026-04-06 | 2026-04-10 | Aero Team | Waiting | Waiting on material
Side Panels
Cut fabric | 2026-05-02 | 2026-05-03 | Aero Team | Waiting | Waiting on material
Adhere fabric | 2026-05-02 | 2026-05-03 | Aero Team | Waiting | Waiting on material
Iron fabric | 2026-05-02 | 2026-05-03 | Aero Team | Waiting | Waiting on material
Treat fabric/polytak | 2026-05-02 | 2026-05-03 | Aero Team | Waiting | Waiting on material
Bodywork
Layup face sheets for body panels | 2026-01-26 | 2026-02-13 | Aero Team | Waiting | Waiting on material
3d print rear cover mold | 2026-01-16 | 2026-01-23 | Maooz | Waiting | Waiting on material
Post process rear cover | 2026-01-26 | 2026-02-13 | Biblina | Waiting | Waiting on material
Assemble mounting mechanism for top cover | 2026-01-26 | 2026-02-13 | Biblina | Waiting | Waiting on material
Assemble face sheets on car | 2026-01-26 | 2026-02-13 | Biblina | Waiting | Waiting on material
Aero Structural
Print internal ribs | 2026-02-02 | 2026-02-13 | Aero Team | Waiting
Jigs for the internal ribs | 2026-02-02 | 2026-02-13 | Aero Team | Waiting
Machine metal ribs | 2026-01-26 | 2026-01-30 | Aero Team | Waiting | Waiting on material
Curved element ribs (3d print overlay for curve) pickup points printed | 2026-02-02 | 2026-02-20 | Aero Team | Waiting | Waiting on material
Assembly internal structure | 2026-03-20 | 2026-03-27 | Aero Team | Waiting | Waiting on material
Glue internal structure to wings | 2026-03-20 | 2026-03-27 | Aero Team | Waiting | Waiting on material
Cooling
Waiting
Waiting
Waiting
VD - Vehicle Dynamics
Key Milestones
Rolling Chassis Complete | Feb 1st 2026 | Feb 6th 2026 | VD Team | Waiting
Frame Fully Welded |  |  |  | Waiting | waiting on tabs to be cut and welded
Outboards/Steering/Supension Assembled | Jan 26th | Feb 15th | VD Team | Waiting | waiting for components to be built
Brake System full installed and bled | Feb 2nd | Feb 15th | Ethan | Waiting | waiting on pedals and outboards
Waiting
Waiting
Frame
Frame tubes welded | Dec 13th | Feb 1st | Luca | In Progress | Still waiting on steering tubes
Frame tabs welded | Jan 1st | Feb 8th | Luca | Waiting | Waiting on tabs to arrive
Frame painted | Feb 9th | Feb 12th | Dejan | Waiting | Needs tabs to all be welded
Torsion Testing | Feb 1st | Feb 8th | Dejan | Waiting | Developing test and need to create setup in thermo lab
Frame-Sub
Firewall bent | Feb 2nd | Feb 8th | Matteo | Waiting | Waiting on firewall to arrive
Firewall tabs designed/printed | Jan 1st | Jan 20th | Matteo | In Progress | awaiting printing
Tabs bent | Feb 2nd | Feb 8th | Matteo | Waiting | Waiting on tabs to arrive
Floor bent | Feb 2nd | Feb 8th | Drew | Waiting | Waiting on floor to arrive
Jacking bar tabs welded | Feb 2nd | Feb 5th | Luca | Waiting | waiting on tabs to arrive
Jacking point tube welded | Feb 5th | Feb 8th | Luca | Waiting | waiting on jacking point tabs
Anti-intrusion plate w/ IA welded to frame | Feb 8th | Feb 13th | Luca | Waiting | frame tabs need to be all welded first/off rotisserie
Driver Interface
Pedal faces and spacers designed and printed | Jan 1st | Jan 23rd | James | Complete | components printed in shop
Throttle pedal components welded | Jan 26th | Jan 30th | James | In Progress | currently jigged up
Brake pedal components welded | Jan 26th | Jan 30th | James | In Progress | currently jigged up
Head rest jig designed and printed | Jan 12th | Jan 30th | Filip P | In Progress | designed ready, to print
Head rest tabs welded/welded to frame | Jan 26th | Jan 30th | James | In Progress | looking into thinner headrest made in shop welded directly to chassis
Metal parts painted | Jan 30th | Feb 3rd | James | Waiting | waiting on welding first
Throttle pedal assembled | Feb 1st | Feb 6th | James | Waiting | waiting on welding first
Brake pedal assembled | Feb 1st | Feb 6th | James | Waiting | waiting on welding first
Pedals installed in chassis | Feb 6th | Feb 8th | James | Waiting
Steering
Metal tie rods assembled | Feb 2nd | Feb 9th | Luca | Waiting
Carbon tie rods assembled | Feb 9th | Feb 15th | Luca | Waiting | waiting on machined components to arrive
Steering rack tab jig designed and printed | Jan 19th | Feb 1st | Luca | In Progress | currently designing
Steering column jig designed and printed | Jan 19th | Feb 1st | Luca | In Progress | designed, awaiting printing
Steering rack tab bent | Feb 2nd | Feb 8th | Luca | Waiting | waiting on tab to arrive
Upper steering column quick release spline welded | Feb 2nd | Feb 8th | Luca | Waiting
Drivetrain
Tab jigs designed and printed | Jan 12th | Feb 1st | Ronnie | In Progress
Shaft machined | Jan 12th | Feb 1st | Ronnie | Waiting | waiting on Record
Drivetrain mounts cut | Jan 19th | Feb 1st | Ronnie | In Progress | Sent to Viking
Drivetrain sent to Record | Feb 1st | Feb 8th | Ronnie | Waiting | Waiting on Viking
Tabs welded onto frame | Feb 1st | Feb 8th | Ronnie | Waiting | Waiting for tabs to arrive
Bearing pressed into mounts | Feb 8th | Feb 12th | Ronnie | Waiting
Chain guard cut and bent | Feb 1st | Feb 8th | Ronnie | Waiting
Scatter shield bent | Feb 1st | Feb 8th | Ronnie | Waiting
Brakes
Master cylinder braided lines installed | Feb 6th | Feb 8th | Ethan | Waiting | awaiting pedals to be installed
Hard lines bent and flared | Feb 6th | Feb 13th | Ethan | Waiting | awaiting pedals to be installed
Suspension
Control arms welded | Jan 26th | Feb 1st | Omar | In Progress
Camber clevises welded | Jan 26th | Feb 1st | Omar | Waiting
Control arm bearings pressed-in | Feb 1st | Feb 8th | Omar | Waiting
Other linkages manufactured | Jan 26th | Feb 1st | Omar | In Progress | welding weld nuts and installing rod ends
Bellcrank bearings pressed-in | Feb 8th | Feb 15th | Omar | Waiting | waiting on bellcranks to arrive
Suspension tab jig test printed | Jan 26th | Feb 1st | Omar | Waiting
Outboards
bearings + hub pressed into outbaords |  |  |  | Waiting
Waiting
Waiting
Waiting
Waiting
Waiting
Waiting
Waiting
BU - Business
Unveiling
Sears form submitted |  |  | Anisha | Complete
Alternative venue(s) contacted if needed |  |  | Andrew | Waiting
Meet with Explore TMU to explore furnishing options |  |  | Andrew | Waiting
Planning for Catering, sponsorship gifts, water, misc. items finalized |  |  | Andrew | Waiting
Decorations complete |  |  | Andrew | Waiting
Unveiling held
Recruitment
First semester: Applications Open |  | 2025-08-28 | Andrew | Waiting
First semester: Applications closed & reviewed | 2025-09-15 | 2025-09-25 | Andrew | Waiting
First semester: Interviews held | October 14th | 2025-10-25 | Andrew | Waiting
First semester: Hirees selected, acceptance/rejection letters sent out | 2025-10-26 | 2025-11-02 | Andrew | Waiting
Second semester: Applications Open |  | 2025-01-12 | Andrew | Waiting
Second semester: Applications closed & reviewed | 2025-01-29 | 2025-02-14 | Andrew | Waiting
Second semester: Interviews held | 2025-02-25 | 2025-03-07 | Andrew | Waiting
Second semester: Hirees selected, acceptance/rejection letters sent out | 2025-03-08 | 2025-03-22 | Andrew | Waiting
Livery
Rough Design submissions are open, templates sent out |  | 2025-12-19 | Andrew | Waiting
Design submissions closed, voting open |  | 2025-01-19 | Andrew | Waiting
Voting closed, design chosen |  | 2026-02-06 | Andrew | Waiting
Proper mockup in Illustrator finalized |  | 2025-03-06 | Andrew | Waiting
For-render CAD File Complete |  | 2025-03-10 | Omar | Waiting
For-render CAD File made 'lightweight' and exported |  | 2025-03-13 | Omar | Waiting
Livery Design added onto car in Solidworks |  | 2026-03-20 | Omar | Waiting
Final CAD render finalized and exported |  | 2026-03-31 | Omar | Waiting
Sponsor logos added onto TM-26 in Illustrator |  | 2025-04-08 | Andrew | Waiting
Mockup & Individual image files sent to sponsor. Sponsor begins work. |  | 2025-04-15 | Andrew | Waiting
Vinyl recieved, wrapping begins |  | 2025-04-30 | Andrew, Omar, Justin | Waiting
Livery complete (latest possible date) |  | 2025-05-14 | Andrew, Omar, Justin | Waiting

## Aero Procurement
[21 empty] | Approval |  |  |  | Procurement
Type | Subsystem | Item | Description (Size/Type) | Why you need it | Critical? | Quantity | Spares | Total Qty. | Unit Price (CAD) | Shipping Cost (CAD) | Estimated Duty Charge (Use this calculator) ($ CAD) | Total Cost (CAD) (Incl. Tax) | Vendor Name | Part No. | Link | Do we have this, or a similar item that could be designed for, in the shop? (If similar or same in shop/storage already, provide explanation) | Item added by (if new member, include lead/ apprentice working with as well): | Companies contacted to sponsor item or get discount (if none, provide reasoning) | Details on company sponsoring + discount code etc. | Comments | System Lead Approval: | Management Approval: | Final Approval? | Purchased by(This column can be filled out by leads who made a purchase | Added to a Purchase Request by: | Purchase Request Spreadsheet Link: | Shipping and Receiving emailed with shop availability for dropoff OR pickup date/time? | Duties Paid Ahead of Time? (<$250 on peoples' cards, >$250 on PCard) | Duties invoice link: | Pickup or dropoff date? | Order Status
Example | aero structural | Steel | 16" x 14" plate 4130 steel | for mounting ribs | Critical | 1 |  | 1 | 100 | 0 | 0 | 100 | Metal Supermarket | N/A |  | Using 5 sq. inches of existing material, need to buy this amount extra. | Morgan, Nick | Metal Supermarkets (declined items and discount code), Company X (didn't respond after 2 weeks and a followup email). | None | Can pick it up from the Vaughan location | Ozge, Dejan, Emi | Maooz, Marta, Luca | Yes | P-CARD | Morgan | https://drive.google.com/drive/folders/1l6BRGBbI_woR5CXfgt1Ydn-UfLeRF23x?usp=share_link | Yes | N/A | N/A | Nov 26 1-5pm, shop dropoff, Morgan | Unpacked
Front Wing
Material | Front Wing | Carbon Fiber Pultruded Rod 1.2 m | 4mm OD | Front wing 4th Element | Critical | 1 | 0 | 1 | 4.1 |  |  | 4.1 | Composites Envisions | T-1579 | https://compositeenvisions.com/product/carbon-fiber-pultruded-rod-1-2m/ | [5 empty] | Maooz | Maooz | Yes | P-CARD | [6 empty] | Submitted P-Card
Total | [11 empty] | 4.1
Rear Wing
Material | Rear Wing | Carbon Fiber Pultruded Round Tube 1.2 Meter | 16 mm OD / 12mm ID | Rear Wing + Front 1st Element | Critical | 4 | 0 | 4 | 41.55 |  |  | 166.2 | Composite Envisions | T-1579 | https://www.compositeenvisions.com/Carbon-Fiber-Pultruded-Round-Tube-1.2m?quantity=1&outside-diameter=28 | [5 empty] | Maooz | Maooz | Yes | P-CARD | [6 empty] | Submitted P-Card
Material | Rear Wing | Carbon Fiber Pultruded Round Tube 1.2 Meter | 10 mm OD / 8mm ID | Rear Wing + Front 2nd Element | Critical | 4 | 0 | 4 | 11.13 |  |  | 44.52 | Composite Envisions | T-1579 | https://www.compositeenvisions.com/Carbon-Fiber-Pultruded-Round-Tube-1.2m?quantity=1&outside-diameter=28 | [5 empty] | Maooz | Maooz | Yes | P-CARD | [6 empty] | Submitted P-Card
Material | Rear Wing | Carbon Fiber Pultruded Rod 1.2m | 6 mm OD | Rear Wing + Front 3rd Element | Critical | 4 | 0 | 4 | 11.13 |  |  | 44.52 | Composite Envisions | T-1576 | https://compositeenvisions.com/product/carbon-fiber-pultruded-rod-1-2m/ | [5 empty] | Maooz | Maooz | Yes | Ozge | [6 empty] | Requires Cheq Req
Fastener | Rear Wing | Heat Set Inserts | Heat-Set Inserts for Plastic Brass, M6 x 1 mm, 12.7 mm Installed Length | Rib Fasteners | Critical | 2 |  | 2 | 14.7726 |  |  | 29.5453 | McMaster-Carr | 94459A220 | https://www.mcmaster.com/94459A220/ |  |  |  |  | Will be ordered later
Fastener | Rear Wing | Flat Head Screws | Phillips Thread-Locking Flat Head Screws 18-8 Stainless Steel, M6 x 1.00 mm Thread Size, 12 mm Long | Endplate Fasteners | Critical | 1 |  | 1 | 17.602 |  |  | 17.602 | McMaster-Carr | 90382A273 | https://www.mcmaster.com/90382A273/ |  |  |  |  | Will be ordered later
Material | Rear Wing | Loctite H3101 Speedbonder 1:1 (400ml) | Adhesive for gluing wings together |  | Critical | 1 |  | 1 | 91.06 |  |  | 91.06 | Canada Composites | LOH3101-400 | https://shop.compositescanada.com/#/product/LOH3101-400 | [5 empty] | Maooz | Maooz | Yes | PENDING | [6 empty] | Out of Stock
Material | Rear Wing | Black Epoxy Dye | Black Epoxy Resin Pigment Paste - 3.4 fl.oz / 100ml Concentrated Black Resin Dye Paste for DIY Resin Art | Paint epoxy black for sealing endplate edges | Critical | 1 |  | 1 | 12.59 |  |  | 12.59 | Amazon |  | https://www.amazon.ca/Black-Epoxy-Resin-Pigment-Paste/dp/B0CVTFLDFB/ref=sr_1_8?crid=349Q8RDK2JQW7&dib=eyJ2IjoiMSJ9.NeQInA27Xn7tabjeD09P3pV016moE9X704Li1njRye4WgTCtjHuxQiCUgb9ydvrNnYozdHC4X5SZwSmKD9VRZTBZ8x8nTp269b8cUADoRHtDcAPGaYTrQIk9MlwD6Ja6oqKEG1NDvwWnTF3Hmp8t5DZ_hPjIw_Lqle6TjBOu2jjvYN0QTCmNhG76ePpiiKpTUIBCeJw3igeHHUoyvtVmZT0eU_-jZYJ7cOv2IRVrD4mpf5sOQpgOS1CZgxt4unE_-7NwB90vav5a4Oi-hq27XU_BXQNohCGKXfUmn8kEYfk.Q_PcvAiZ17B_pWeg8iolAbKXzxx1kmtSIBNy0RjSHaI&dib_tag=se&keywords=polyurethane%2Bblack%2Bdye&qid=1732131737&sprefix=polyurethane%2Bblack%2Bdye%2Caps%2C110&sr=8-8&th=1 | [5 empty] | Maooz | Maooz | Yes | Ozge | [6 empty] | Requires Cheq Req
Material | Rear Wing | PET-CF Filament | Carbon Fiber Reinforced PET - 1kg | Airfoil Ribs | Critical | 4 |  | 4 | 98.09 |  |  | 392.36 | Bambu Labs |  | https://ca.store.bambulab.com/collections/filament-single-discount/products/pet-cf?variant=44029327671536 |  |  |  |  | Need to Purchase by memebr | Maooz | Maooz | Yes | P-CARD | [6 empty] | Unpacked
Total | [11 empty] | 798.3973
Aero Structural
Material | Aero Structural | 6061 Aluminium 0.25'' plate | 24" x 33" x 0.25" | Rear wing mount | Critical | 2 | 0 | 2 | 205.77 |  |  | 411.54 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/aluminum-plate-6061/ |  | Anisha Das |  |  |  | Maooz | Maooz | Yes | P-CARD | [6 empty] | Submitted P-Card
Material | Aero Structural | 6061 Aluminium 0.25'' plate | 35'' x 27'' x 0.12'' | Front wing mount | Critical | 1 | 0 | 1 | 164.56 |  |  | 164.56 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/aluminum-sheet-6061/ |  | Anisha Das |  |  |  | Maooz | Maooz | Yes | P-CARD | [6 empty] | Submitted P-Card
Material | Aero Structural | CC Carbon Fiber Tube Twill | 22mm x 20mm x 1.2m | Rear Wing Support/Mount | Critical | 1 | 1 | 2 | 44.26 | 0 | 0 | 88.52 | Composites Canada | CFT-22X20TW | https://shop.compositescanada.com/#/product/CFT-22X20TW | No | Anisha Das | N/A | N/A |  | Maooz | Maooz | Yes | P-CARD | [6 empty] | Submitted P-Card
Total | [11 empty] | 664.62
Infusion Supplies
Material | aero | 2x2 Twill Weave Carbon Fiber | Carbon Fiber/LMFG Stabilized Fabric 2x2 Twill 3k 50"/127cm 6.1oz/206gsm Toray T300 |  | Critical | 50 | 10 | 60 | 34.1838 |  | 266.6339 | 2317.6641 | Composite Envisions | F-1541-50 | https://www.compositeenvisions.com/Carbon-Fiber-LMFG-Stabilized-Fabric-2x2-Twill-3k-6.1oz-207gsm?quantity=26&width=624 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Material | aero | Infusion Epoxy | R-3501 Vacuum Infusion Epoxy 3:1 | Epoxy for Layup | Critical | 10 | 2 | 12 | 139.2247 |  | 217.1905 | 1887.8864 | Composite Envisions | 1171-.75_Gallon | https://www.compositeenvisions.com/R3501-31-Infusion-Epoxy?quantity=1&item-size=40 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Material | aero | Infusion Epoxy Hardener | H5000-01 3:1 Infusion Hardener | Hardener for Epoxy | Critical | 10 | 2 | 12 | 54.8873 |  | 85.6242 | 744.2718 | Composite Envisions | 1172-.25_gal | https://www.compositeenvisions.com/H5000-01-31-Infusion-Hardener | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Material | aero | Teflon release film | Non Porous Teflon Coated Release Film with Silicone Adhesive 39.37"/100cm width Thickness .007"/.18mm | For mold release | Critical | 10 | 1 | 11 | 32.1842 |  | 46.0234 | 400.0499 | Composite Envisions | 1803-39 | https://www.compositeenvisions.com/Non-Porous-Teflon-Coated-Peel-Ply-with-Silicone-Adhesive-Thickness-0.18mm?quantity=1&width=967 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Material | aero | Frekote 700-NC Industrial Mold Release | Frekot Mold Release (Pint) | Mold Release | Critical | 2 |  | 2 | 43.3929 |  | 11.2822 | 98.068 | Composite Envisions | 1406-Pint | https://www.compositeenvisions.com/Frekote-700-NC-Industrial-Mold-Release?quantity=1&item-size=28 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Part | aero | Vacuum Resin Trap Catch Pot - Stainless Steel 2 Quart | Catch Can for Infusion | Infusion Layups | Critical | 1 | 0 | 1 | 154.4054 |  | 20.0727 | 174.4781 | Composite Envisions | 986 | https://www.compositeenvisions.com/Vacuum-Resin-Trap-Catch-Pot-Stainless-Steel-2-Quart | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Material | aero | Fibertack MT-1 Spray Tack Adhesive | spray tack | Infusion Layups | Critical | 1 | 1 | 2 | 39.2577 |  | 10.207 | 88.7224 | Composite Envisions | 2270-16oz | https://www.compositeenvisions.com/Fibertack-MT-1-Spray-Tack-Adhesive?quantity=1&item-size=46&tint=1 | no | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Part | aero | Radius Compression Roller 1.5" Diameter |  | Infusion | Critical | 1 |  | 1 | 11.0999 |  | 1.443 | 12.5429 | Composite Envisions | 2019-.125 | https://www.compositeenvisions.com/Radius-Compression-Roller-1.5in-Diameter?quantity=1&radius=2 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Material | aero | Soric XF Infusible Honeycomb Core 50" Wide | Core Material | For seat and Undertray | Critical | 8 | 3 | 11 | 25.07 |  | 35.85 | 311.6196 | Composite Envisions | 1270-50-2mm | https://www.compositeenvisions.com/Soric-XF-Infusible-Honeycomb-Core?quantity=1&thickness=1&srsltid=AfmBOopsqvf84oYukx9W4KJ_cmyt3G4LzbbYzgvJH19HmhMhytYuJCyF | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | On Hold
Part | aero | Squeegee Yellow 4” |  | Epoxy Spreader | Critical | 10 |  | 10 | 1.18 |  | 1.534 | 13.334 | Composites Canada | 1827400 | https://shop.compositescanada.com/#/product/6903-4 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | In Shop
Part | aero | Squeegee Yellow 2” |  | Epoxy Spreader | Critical | 10 |  | 10 | 0.88 |  | 1.144 | 9.944 | Composites Canada | 1827341 | https://shop.compositescanada.com/#/product/6903-2 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | In Shop
Part | aero | Econo Wood Handle Brush 2” |  | Epoxy Spreader | Critical | 12 |  | 12 | 1.21 |  | 1.8876 | 16.4076 | Composites Canada | BR200-2-B24 | https://shop.compositescanada.com/#/product/BR200-2-B24 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | In Shop
Part | aero | Econo Wood Handle Brush 1” |  | Epoxy Spreader | Critical | 12 |  | 12 | 0.85 |  | 1.326 | 11.526 | Composites Canada | BR200-1 | https://shop.compositescanada.com/#/product/BR200-1 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | In Shop
Part | aero | CC Xtreme Plastic Graduated Cup-Pint |  | Epoxy Mixing | Critical | 20 |  | 20 | 0.78 |  | 2.028 | 17.628 | Composites Canada | 9036-PT | https://shop.compositescanada.com/#/product/9036-PT | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | In Shop
Part | aero | CC Xtreme Plastic Graduated Cup-Qrt |  | Epoxy Mixing | Critical | 20 |  | 20 | 0.88 |  | 2.288 | 19.888 | Composites Canada | 9037-Q | https://shop.compositescanada.com/#/product/9037-Q | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | In Shop
Part | aero | CC Xtreme Plastic Graduated Cup-2.5 Qrt |  | Epoxy Mixing | Critical | 15 |  | 15 | 1.8 |  | 3.51 | 30.51 | Composites Canada | 9037-25 | https://shop.compositescanada.com/#/product/9037-25 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | In Shop
Part | aero | CC Xtreme Plastic Graduated Cups-5 Qrt |  | Epoxy Mixing | Critical | 6 |  | 6 | 2.89 |  | 2.2542 | 19.5942 | Composites Canada | 2606858 | https://shop.compositescanada.com/#/product/9037-5 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | In Shop
Safety | aero | Full face respirator |  | Safet Equipment | Critical | 1 | 0 | 1 | 39.99 |  | 5.1987 | 45.1887 | Amazon |  | amazon.ca/gp/product/B0CQS5RSXZ/ref=ox_sc_act_title_2?smid=A2GTW3Q30TV3OT&psc=1 | No | Davis Macdonald |  |  | Absolutely necessary for safety | Maooz | Maooz | Yes | Davis | [6 empty] | Requires Cheq Req
Safety | aero | Replacement cartridge for 3M VO/P100 multi-purpose respirator, 1 pair | P100 respirator filters | Safet Equipment | Critical | 2 | 0 | 2 | 26.99 |  | 7.0174 | 60.9974 | Canadian Tire | #055-0286-0 | https://www.canadiantire.ca/fr/pdp/cartouche-de-rechange-pour-respirateur-multi-usage-3m-vo-p100-1-paire-0550286p.html#store=600 | No | Davis Macdonald |  |  | Absolutely necessary for safety | Maooz | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Material | aero | Tubing | CANADA TUBING Clear Vinyl Tubing, 1/4" inside diameter x 3/8" outside diameter x 100 ft coil. |  | Critical | 2 |  | 2 | 37.98 |  | 9.8748 | 85.8348 | Homedepot | Store SKU # 1001537759 | https://www.homedepot.ca/product/canada-tubing-clear-vinyl-tubing-1-4-inside-diameter-x-3-8-outside-diameter-x-100-ft-coil-/1001537759 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req | SOLDOUT
Material | aero | Filament | Pla Basic | For molds | Critical | 7 | 3 | 10 | 25.99 |  | 33.787 | 293.687 | Bambu Lab | Black (10101) | https://ca.store.bambulab.com/products/pla-basic-filament?id=43766892298480 | No | Davis Macdonald |  |  |  | Maooz | Maooz | Yes | P-CARD | [6 empty] | Unpacked
Total | [11 empty] | 6659.8428
Testing
Material | aero | Bryte Paraffin Lamp Oil | Bryte Paraffin Lamp Oil - Smokeless, Odorless, Clean & Clear, Paraffin Oil for Indoor and Outdoor Use, Funnel Included 1Gallon | Flow vis test | Non-critical | 1 | 0 | 1 | 47.99 |  |  | 47.99 | Amazon | B08R6JV1Q1 | https://www.amazon.ca/Bryte-Paraffin-Lamp-Oil-Smokeless/dp/B08R6JV1Q1/ref=asc_df_B08R6JV1Q1?mcid=d8676b660d6d3449bd88b9cc9de715f5&tag=googleshopc0c-20&linkCode=df0&hvadid=706727704281&hvpos=&hvnetw=g&hvrand=16348616914073916468&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=1002190&hvtargid=pla-1596667094810&hvocijid=16348616914073916468-B08R6JV1Q1-&hvexpln=0&gad_source=1&th=1 | No |  |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Material | aero | Oleic Acid | Oleic acid pure 112-80-1 C18H34O2 cis-octadec-9-enoic acid | Flow vis test | Non-critical | 1 | 0 | 1 | 21.45 | 14.47 |  | 35.92 | Etsy |  | https://www.etsy.com/ca/listing/1889277883/oleic-acid-pure-112-80-1-c18h34o2-cis?ls=s&ga_order=most_relevant&ga_search_type=all&ga_view_type=gallery&ga_search_query=oleic+acid&ref=sr_gallery-1-1&sr_prefetch=1&pf_from=market&pro=1&content_source=21bfdd1a-b943-48d2-bfa2-9882612e6418%253ALT927f1787e75e0ff0c364cf62dcd2ab18d7a8a88f&organic_search_click=1&logging_key=21bfdd1a-b943-48d2-bfa2-9882612e6418%3ALT927f1787e75e0ff0c364cf62dcd2ab18d7a8a88f | No |  |  |  |  | Maooz | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Material | aero | Invisible Blue Titanium Oxide | Fluorescein | Flow vis test | Non-critical | 1 | 0 | 1 | 43.98 |  |  | 43.98 | Amazon |  | https://www.amazon.ca/Fluorescein-DOSIDIAG-Intense-Tracer-Detection/dp/B0DPDT373R?source=ps-sl-shoppingads-lpcontext&ref_=fplfs&psc=1&smid=A1XKTVF3I6UNMV | No |  |  |  |  | Maooz | Maooz | Yes | Davis | [6 empty] | Requires Cheq Req
Total | [11 empty] | 127.89
Bodywork
Material | bodywork | Copper Mesh |  | Needed to ground upper side panels | Critical | 1 |  | 1 | 8.98 |  |  | 8.98 |  |  | https://www.amazon.ca/gp/product/B0B4TZRYKB/ref=ox_sc_act_title_1?smid=A385U2A6WE6O07&psc=1 |  | Biblina |  |  |  | Maooz | Maooz | Yes | Biblina | [6 empty] | Ordered
Part | bodywork | Bar Magnets |  | Needed to attach nose cone and rear cover onto frame | Critical | 1 |  | 1 | 25.99 |  |  | 25.99 |  |  | https://www.amazon.ca/DIYMAG-Powerful-Neodymium-Double-Sided-Office-60x10x3mm/dp/B07D5SH29K?source=ps-sl-shoppingads-lpcontext&ref_=fplfs&th=1 |  | Biblina |  |  |  | Maooz | Maooz | Yes | Biblina | [6 empty] | Ordered
Fastener | bodywork | Dzus Fasteners |  | Needed to mount nose cone and rear cover to frame | Critical | 8 |  | 1 | 30.64 |  |  | 30.64 |  |  | https://www.mcmaster.com/91382A530/ |  | Biblina |  |  |  | Maooz | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Material | bodywork | Ceconite |  | Needed for driver side panels. | Critical | 1 |  | 1 | 30.85 |  |  | 30.85 |  |  | Ceconite Fabric Ceconite 101 ¦ Aircraft Spruce Canada |  | Biblina |  |  |  | Maooz | Maooz | Yes | Biblina | [6 empty] | Ordered
Total | [11 empty] | 96.46
Undertray
Material | aero | Carbon Tubes | 15mm x 1 meter | undertray mounting | Critical | 2 | 0 | 2 | 30.15 |  |  | 68.139 | Composite envisions | T-1826-20mm | https://www.compositeenvisions.com/Roll-Wrapped-Carbon-Fiber-Tube-Twill-Weave-Gloss-Finish?quantity=1&length=35&outside-diameter=10&finish=1 | No | Davis |  |  |  | Maooz | Maooz | Yes | P-CARD | https://docs.google.com/spreadsheets/d/1loRnpEvRcwY8K_89g4f5wAHS1--0q0ijVATVHcMnAbw/edit?usp=share_link |  |  |  |  | In Shop | Submitted P-Card
Fastener | aero | Ball Joint Rod End | 1/4"-28 Thread | Under tray mount | Critical | 8 |  | 8 | 5.43 |  |  | 43.44 | McMaster Carr | 60645K12 | https://www.mcmaster.com/catalog/131/1275/4237N102 | No | Davis | N/A | N/A | Purchased version with nut instead https://www.mcmaster.com/catalog/131/1275/4237N102 | Maooz | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | aero | 1/4"-28 thread Heat Set insert | 1/4"-28 thread Heat Set insert 1/2" installed length | Support Rod Fasteners | Critical | 8 | 2 | 10 | 4.55 |  |  | 45.5 | McMaster-Carr | 94459A813 | https://www.mcmaster.com/94459A813/ | No | Maooz Ahmed | N/A | N/A |  | Maooz | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Total | [11 empty] | 157.079
GRAND TOTAL | [11 empty] | 8508.3891

## VD Procurement
[21 empty] | Approval |  |  |  | Procurement
Type | Subsystem | Item | Description (Size/Type) | Why you need it | Critical? | Quantity | Spares | Total Qty. | Unit Price (CAD) | Shipping Cost (CAD) | Estimated Duty Charge (Use this calculator) ($ CAD) | Total Cost (CAD) (Incl. Tax) | Vendor Name | Part No. | Link | Do we have this, or a similar item that could be designed for, in the shop? (If similar or same in shop/storage already, provide explanation) | Item added by (if new member, include lead/ apprentice working with as well): | Companies contacted to sponsor item or get discount (if none, provide reasoning) | Details on company sponsoring + discount code etc. | Comments | System Lead Approval: | Management Approval: | Final Approval? | Purchased by(This column can be filled out by leads who made a purchase | Added to a Purchase Request by: | Purchase Request Spreadsheet Link: | Shipping and Receiving emailed with shop availability for dropoff OR pickup date/time? | Duties Paid Ahead of Time? (<$250 on peoples' cards, >$250 on PCard) | Duties invoice link: | Pickup or dropoff date? | Order Status
Example | aero structural | Steel | 16" x 14" plate 4130 steel | for mounting ribs | Critical | 1 |  | 1 | 100 | 0 | 0 | 100 | Metal Supermarket | N/A |  | Using 5 sq. inches of existing material, need to buy this amount extra. | Rochelle, Rhythm | Metal Supermarkets (declined items and discount code), Company X (didn't respond after 2 weeks and a followup email). | None | Can pick it up from the Vaughan location | Ozge, Dejan, Emi | Maooz, Marta, Luca | Yes |  | Morgan | https://drive.google.com/drive/folders/1l6BRGBbI_woR5CXfgt1Ydn-UfLeRF23x?usp=share_link | Yes | N/A | N/A | Nov 26 1-5pm, shop dropoff, Morgan | Unpacked
Suspension
Part | suspension | Hydraulic Press | 10 Ton Capacity Hydraulic Shop Press, Long Lever Manual Operation, 3 Bed Height Positions, TMG-ASP10 | Pressing In Bearings | Non-critical | 1 |  | 1 | 538.68 | 240 |  | 778.68 | TMG Industrial | TMG-ASP10 | https://tmgindustrial.ca/products/tmg-industrial-10-ton-capacity-hydraulic-shop-press-long-lever-manual-operation-3-bed-height-positions-tmg-asp10 | No | Omar | TMG Industrial | Ask Dejan | Provided by Dejan from my understanding he sent an email, so see if they would sponsor us for it. | Dejan | N/A | No
Part | suspension | Loctite | Loctite 21448 Green 638 High Strength Retaining Compound, 50 mL Bottle | Bonding Bearings | Critical | 1 |  | 1 | 20 |  |  | 20 | Amazon | N/A | https://www.amazon.ca/Loctite-21448-Strength-Retaining-Compound/dp/B000O01EV0/ref=sr_1_1?crid=W98N5939DA6P&dib=eyJ2IjoiMSJ9.abA3xHgeKetbOAZE2MR1cIRJMuiMUUhkzEeFawId2X6aa9ZAMC7h8zFTuGGyOnAFYZhq-9avq0gpGfBRLibQs-LZSyv4fZjgl4RIhqaCnf_UKUrLxMe0LAzvM8xqh6UYXLJ75rfCUmfsUBAVfztfGie49s3OAmWJ-qbik0kX26_2ZlV4LjVl4B1peiItNHeCy2UzFT7Nj5uDew9jcfKXEZHRC-ST2dRbNEQg7w1XxY3P9bvFl9sWLbmNJffmaCKvN6WjpP_lPdpgu3t5rMAcM_LPMggEq6Eg_pSomzBprH0.zK9V3a6zSItGEdt3uIBRqf6ptyTO2U0RBm-5jv0oa0o&dib_tag=se&keywords=Loctite+green&qid=1729819463&sprefix=loctite+gree%2Caps%2C108&sr=8-1 |  | Omar |  |  |  | Dejan | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Material | suspension | 1" 4140 Heat Treated | 3" | Bearing Fixture | Critical | 1 |  | 1 | 10 |  |  | 10 | Metal Supermarket | N/A | https://www.metalsupermarkets.com/product/alloy-steel-round-bar-4140/ |  | Omar |  |  |  | Dejan | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Material | suspension | 0.625" 4140 Heat Treated | 2" | Bearing Fixture | Critical | 1 |  | 1 | 13 |  |  | 13 | Metal Supermarket | N/A | https://www.metalsupermarkets.com/product/alloy-steel-round-bar-4140/ |  | Omar |  |  |  | Dejan | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Material | suspension | 0.25" 4140 Heat Treated | 4" | Bearing Fixture | Critical | 1 |  | 1 | 7.4 |  |  | 7.4 | Metal Supermarket | N/A | https://www.metalsupermarkets.com/product/alloy-steel-round-bar-4140/ |  | Omar |  |  |  | Dejan | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Fastener | suspension | 863 Iron Copper Oil-Embedded Sleeve Bearing | Flanged, for 1/4" Shaft Diameter and 3/8" Housing ID, 3/8" Long | Top Hat | Critical | 80 | 30 | 110 | 1.06 |  |  | 116.6 | McMaster Carr | 2938T2 | https://www.mcmaster.com/2938T2/ |  | Omar |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | suspension | Corrosion-Resistant Swivel Joint | Lubrication-Free, 1/4" ID, 21/32" OD | Outboard Beaings | Critical | 8 | 4 | 12 | 25.43 |  |  | 305.16 | McMaster Carr | 63215K52 | https://www.mcmaster.com/63215K52/ |  | Omar |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | suspension | Tube-End Weld Nut | for 1/2" Tube OD and 0.058" Wall Thickness, 1/4"-28 Thread Size | Right Hand Thread Weld Nuts | Critical | 25 | 0 | 25 | 9.82 |  |  | 245.5 | McMaster Carr | 94640A881 | https://www.mcmaster.com/94640A881/ |  | Omar |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | suspension | Ball Joint Rod End with Nut | 1/4"-28 Thread Size | Right Hand Thread Rod Ends | Critical | 22 | 0 | 22 | 10.25 |  |  | 225.5 | McMaster Carr | 4237N13 | https://www.mcmaster.com/4237n102/ |  | Omar |  |  | luca thought of the fact that we can recycle them so i still need to take inventory | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | suspension | 863 Iron Copper Oil-Embedded Sleeve Bearing | Flanged, for 1/4" Shaft Diameter and 3/8" Housing ID, 1/4" Long | PR Top Hat | Critical | 8 | 10 | 18 | 0.85 |  |  | 15.3 | McMaster Carr | 2938T1 | https://www.mcmaster.com/2938T1/ |  | Omar |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | suspension | Tube-End Weld Nut | Left-Hand Threaded, for 1/2" OD and 0.058" Wall Thickness, 1/4"-28 Thread | Left Hand Thread Weld Nuts | Critical | 9 | 0 | 9 | 9.82 |  |  | 88.38 | McMaster Carr | 94640A882 | https://www.mcmaster.com/94640A882/ |  | Omar |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | suspension | Ball Joint Rod End with Nut | Left Hand Thread 1/4"-28 Thread Size | Left Hand Thread Rod Ends | Critical | 6 | 0 | 6 | 10.25 |  |  | 61.5 | McMaster Carr | 4237N14 | https://www.mcmaster.com/4237n102/ |  | Omar |  |  | luca thought of the fact that we can recycle them so i still need to take inventory | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | suspension | Stainless Steel Ball Bearing | Shielded with Extended Inner Ring, Number R188-2Z | BL Pivot | Critical | 8 | 2 | 10 | 9.48 |  |  | 94.8 | McMaster Carr | 57155K387 | https://www.mcmaster.com/57155K387/ |  | Omar |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Master Jig
Part |  | T-Slotted Framing | 6ft - Single 4-Slot Rail, Silver, 1.5" High x 1.5" Wide, Hollow | Alum Ext. | Critical | 2 | 0 | 2 | 64.73 |  |  | 129.46 | McMaster Carr | 47065T148 | https://www.mcmaster.com/47065T102-47065T148/ |  | Omar |  |  |  | Dejan | Maooz | Yes | Dejan | [6 empty] | Ordered
Part |  | T-Slotted Framing | 8ft - Single 4-Slot Rail, Silver, 1.5" High x 1.5" Wide, Hollow | Alum Ext. | Critical | 2 | 0 | 2 | 84.2 |  |  | 168.4 | McMaster Carr | 47065T157 | https://www.mcmaster.com/47065T102-47065T157/ |  | Omar |  |  |  | Dejan | Maooz | Yes | Dejan | [6 empty] | Ordered
Part |  | T-Slotted Framing | Silver Flush Tee Bracket for 1.5" High Rail, 4.5" Long | 90 Connection | Critical | 4 | 0 | 4 | 28.83 |  |  | 115.32 | McMaster Carr | 3136N161 | https://www.mcmaster.com/3136N161/ |  | Omar |  |  |  | Dejan | Maooz | Yes | Dejan | [6 empty] | Ordered
Part |  | T-Slotted Framing | 1ft - Single 4-Slot Rail, Silver, 1.5" High x 1.5" Wide, Hollow | Alum Ext. | Critical | 4 | 0 | 4 | 13.66 |  |  | 54.64 | McMaster Carr | 47065T601 | https://www.mcmaster.com/47065T102-47065T601/ |  | Omar |  |  |  | Dejan | Maooz | Yes | Dejan | [6 empty] | Ordered
Part |  | Silver Corner Bracket | 1.5" Long for 1.5" High Rail T-Slotted Framing | Corner Mounts | Critical | 4 | 0 | 4 | 12.25 |  |  | 49 | McMaster Carr | 47065T845 | https://www.mcmaster.com/47065T845/ |  | Omar |  |  |  | Dejan | Maooz | Yes | Dejan | [6 empty] | Ordered
Part |  | T-Slotted Framing | Sleeve Bearing, 1.5" High Rail, 2 Flange, 2-13/16" Long, Silver | Slotted Frame | Critical | 4 | 0 | 4 | 120.33 |  |  | 481.32 | McMaster Carr | 47065T962 | https://www.mcmaster.com/47065T962/ |  | Omar |  |  |  | Dejan | Maooz | Yes | Dejan | [6 empty] | Ordered
Part |  | Self-Aligning T-Slotted Framing Nuts | End-Feed, for 1.5", 30 mm and 40 mm Rail, 5/16"-18 Thread | Frame Mounting Nuts | Critical | 2 | 0 | 2 | 7.09 |  |  | 14.18 | McMaster Carr | 5278N11 | https://www.mcmaster.com/5278N11/ |  | Omar |  |  |  | Dejan | Maooz | Yes | Dejan | [6 empty] | Ordered
Part |  | Zinc-Plated Grade 5 Steel Flanged Hex Head Screws | Medium-Strength, 5/16"-18 Thread Size, 7/8" Long, Fully Threaded | Bolts | Critical | 1 | 0 | 1 | 5.97 |  |  | 5.97 | McMaster Carr | 92979A157 | https://www.mcmaster.com/92979A157/ |  | Omar
Part |  | Zinc-Plated Medium-Strength Steel Hex Nut | SAE Grade 5, 5/16"-18 Thread Size | Nuts | Critical | 1 | 0 | 1 | 13.33 |  |  | 13.33 | McMaster Carr | 95462A030 | https://www.mcmaster.com/95462A030/ |  | Omar |  |  |  | Dejan | Maooz | Yes | Dejan
Total | [11 empty] | 1031.62
Manufacturing
Material |  | PETG filament | Bambu HF PETG filament | needed for frame and tab jigs for other systems | Critical | 5 |  | 5 | 25.99 | 0 | 0 | 129.95 | Bambu Labs | Gray (33101) | https://ca.store.bambulab.com/products/petg-hf |  | Dejan | Bambu | none |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | Unpacked
Total | [11 empty] | 129.95
Frame Primary
Material | frame | 4130 Tubes | Tubes cut from VR3 (all tubes) | for frame, suspension and acu tabs | Critical | 1 | 0 | 1 | 6250 | 0 | 0 | 8068.2 | VR3 | N/A |  |  | Dejan | VR3 | Sponsored (50% discount) | based on last years VR3 order, since we are adding acu mounts added ~250 on top to account for it | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Total | [11 empty] | 8068.2
Frame-Sub
Material | frame-sub-items | 6061 Aluminum | 39.8" x 20.9" x 0.05" plate sheet metal, 16 gauge | Front Floor Closeout | Critical | 1 |  | 1 | 108.87 |  | 0 | 108.87 | Metal Supermarket | N/A | https://www.metalsupermarkets.com/product/aluminum-sheet-6061/ | No | Drew |  |  | Measurements have an extra inch for cutting | Dejan | Luca | Yes | Luca | [6 empty] | In Shop (Lead Notified)
Material | frame-sub-items | 6061 Aluminum | 21.2" x 22.5" x 0.05" plate sheet metal, 16 gauge | Rear Floor Closeout | Critical | 1 |  | 1 | 75.68 |  | 0 | 75.68 | Metal Supermarket | N/A | https://www.metalsupermarkets.com/product/aluminum-sheet-6061/ | No | Drew |  |  | Measurements have an extra inch for cutting | Dejan | Luca | Yes | Luca | [6 empty] | In Shop (Lead Notified)
Material | frame-sub-items | 6061 Aluminum | 22.22" x 16 " x 0.032 " Aluminum | Top Firewall | Critical | 1 |  | 1 | 60.85 |  | 0 | 60.85 | Metal Supermarket | N/A | https://www.metalsupermarkets.com/product/aluminum-sheet-6061/ | No | Matteo |  |  | Measurements have an extra inch for cutting | Dejan | Luca | Yes | Luca | [6 empty] | In Shop (Lead Notified)
Material | frame-sub-items | 6061 Aluminum | 22.22 " x 17.6" x 0.032 Aluminum | Lower Firewall | Critical | 1 |  | 1 | 65.65 |  | 0 | 65.65 | Metal Supermarket | N/A | https://www.metalsupermarkets.com/product/aluminum-sheet-6061/ | No | Matteo |  |  | Measurements have an extra inch for cutting | Dejan | Luca | Yes | Luca | [6 empty] | In Shop (Lead Notified)
Fastener | frame-sub-items | Aluminum Rivets | Aluminum Blind Rivets with Aluminum Mandrel, Domed Head, 3/16" Diameter, for 0.126"- 0.25" Material Thickness | Mounting floors | Critical | 34 (not final) | 66 | 100 | 9.47 |  | 0 | 9.47 | Mcmaster Carr | 97447A050 | https://www.mcmaster.com/97447A050/ | No | Drew |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | frame-sub-items | Loctite | 50 ml | Sealing Top and bot firewall | Critical | 1 |  | 1 | 24.15 |  | 0 | 24.15 | Mcmaster Carr | 6430A19 | https://www.mcmaster.com/products/loctite/ | No | Matteo |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | frame-sub-items | Impact Attenuator | Aluminum Honeycomb Extrusion Impact Attenuator |  | Critical | Lot of 2 | 2 | 2 | 76 |  | 0 | 152 | Plascore |  |  |  | Matteo |  |  | Still have one from last year | Dejan | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Material | frame-sub-items | FramSub tob firewall Tabs | 7 " x 8 " x 0.032 " | Fram tabs | Critical | 1 | 0 |  | 30.47 |  | 0 | 27 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/alloy-steel-sheet-4130/ | No | Matteo |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Material | frame-sub-items | FramSub tob firewall Tabs | 3.36 " x 3.36 " x 0.05 " | Fram tabs | Critical | 1 | 0 | 0 |  |  |  | 50 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/alloy-steel-sheet-4130/ | No | Matteo |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Material | frame-sub-items | Self tapping | 1/4 self tapping screws | Attach the firewall to the head restraint tube | Critical | 2 | 98 | 100 | 8.97 | 0 | 0 | 8.97 | Home Depot |  | https://www.homedepot.ca/product/paulin--8-15-x-1-1-4-in-pan-head-square-drive-self-tapping-sheet-metal-screws-zinc-plated-100pcs/1000139772 |  | Matteo |  |  |  | Dejan | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Total | [11 empty] | 582.64
Steering
Fastener | steering | Ball Joint Rod End with Nut | 1/4"-28 Thread Size (Left Hand) | Future Reference Only - Shared with suspension | Non-critical | 0 | 0 | 0 | [8 empty] | Luca
Fastener | steering | Ball Joint Rod End with Nut | 1/4"-28 Thread Size (Right Hand) | Future Reference Only - Shared with suspension | Non-critical | 0 | 0 | 0 | [8 empty] | Luca
Fastener | steering | Tube-End Weld Nut | for 1/2" Tube OD and 0.058" Wall Thickness, 1/4"-28 Thread Size | Future Reference Only - Shared with suspension | Non-critical | 0 | 0 | 0 | [8 empty] | Luca
Fastener | steering | Tube-End Weld Nut | Left-Hand Threaded, for 1/2" OD and 0.058" Wall Thickness, 1/4"-28 Thread | Future Reference Only - Shared with suspension | Non-critical | 0 | 0 | 0 | [8 empty] | Luca
Fastener | steering | Shoulder Screw | Same-Size Thread 18-8 Stainless Steel Shoulder Screw | Steering linkage fasteners | Critical | 6 | 2 | 8 | 7.3 |  | 0 | 65.992 | Mcmaster Carr | 91273A587 | https://www.mcmaster.com/catalog/131/3541/91273A587 | No | Luca |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | steering | Nylock | 1/4-28 Nylock | Steering linkage fasteners | Critical | 4 | 21 | 1 Pack of 25 | 0.1628 |  | 0 | 4.5991 | Mcmaster Carr | 90630A145 | https://www.mcmaster.com/90630A145/ | No | Luca |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | steering | SHCS | 1/4"- 20 Socket Head Cap Screw | Steering Rack Fasteners | Critical | 2 | 48 | 1 Pack of 50 | 0.3618 |  | 0 | 20.4417 | Mcmaster Carr | 91251A548 | https://www.mcmaster.com/91251A548/ | No | Luca |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
[11 empty] | 0 | [8 empty] | Keep this item on hold until I'm able to check the metal in the shop Nov. 1st |  |  |  | P-CARD | [6 empty] | In Shop (Lead Notified)
[11 empty] | 0 | [8 empty] | Keep this item on hold until I'm able to check the metal in the shop Nov. 1st |  |  |  | P-CARD | [6 empty] | In Shop (Lead Notified)
Material | steering | Carbon Tube | Carbon Fiber Tube (Twill Weave, 0.064" Wall Thickness, 0.503" OD) | Tie rod material | Critical | 1 | 0 | 1 | 54.92 |  | 0 | 62.0596 | Mcmaster carr | 5287T81 | https://www.mcmaster.com/5287T81-5287T672/ | No | Luca |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Total |  |  | TOTAL | [8 empty] | 153.0924
Outboards
Part | outboards | machined uprights | Machined uprights from chinese contact | for the uprights | Critical | 1 | 0 | 1 | 1178 |  |  | 1178 | [7 empty] | based on price Steven gave me for the Tm-25 uprights accounting for shipping charges and some flucauation to costs | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | outboards | Timken 08231-20024 bearing cup | front bearing cup for hub | to allow wheels to spin | Critical | 4 | 2 | 6 | 36.26 | tbd | 0 | 245.84 | Motion Canada | 657442 | https://www.motioncanada.ca/products/sku/00657442 | no | Dejan | no | no | can't get shipping price | Dejan | Maooz | Yes | P-CARD | [6 empty] | Ordered
Part | outboards | timken 08125-20082 bearing roller | front bearing rollers for hub | allow wheels to spin | Critical | 4 | 2 | 6 | 87.33 | tbd | 0 | 592.1 | Motion Canada | 657434 | https://www.motioncanada.ca/products/sku/00657434 | no | Dejan | no | no | can't get shipping price | Dejan | Maooz | Yes | P-CARD | [6 empty] | Ordered
Part | outboards | Timken L610510-20024 bearing cup | rear bearing cup for hub | allow wheels to spin | Critical | 4 | 2 | 6 | 109.79 | tbd | 0 | 744.38 | Motion Canada | 662016 | https://www.motioncanada.ca/products/sku/00662016 | no | Dejan | no | no | can't get shipping price | Dejan | Maooz | Yes | P-CARD | [6 empty] | Ordered
Part | outboards | Timken L610549-20024 bearing roller | rear bearing roller for hub | allow wheels to spin | Critical | 4 | 2 | 6 | 272.87 | tbd | 0 | 1850.06 | Motion Canada | 662021 | https://www.motioncanada.ca/products/sku/00662021 | no | Dejan | no | no | can't get shipping price | Dejan | Maooz | Yes | P-CARD | [6 empty] | Ordered
Total | [11 empty] | 4610.38
Brakes
Part | brakes | Front Caliper | Front Caliper AP Racing CP4227-2S0 | Front Right caliper was dammaged during testing (July 31 2025) | Critical | 1 | 0 | 1 | $1183.47 (€738,84) | will be defined by the Sales Manager during order processing | 234.09 | 1417.56 | ATOMIC-SHOP Performance Parts & Motorsport Equipment | CP4227-2S0 | https://atomic-shop.eu/products/ap-racing-cp4227-2s0-brake-caliper-acalaarhx04-0-cp4226 | No | Ethan | None | European | need for testing, could not find any north american vendors | Dejan | N/A | No
Part | brakes | Outboard Softline | Summit Racing™ Stainless Steel Braided Brake Line Assemblies Length: 16 in. (Hose End 1: Female -3AN, Hose End 2: Female -3AN) | Front right line broken during testing (July 31) | Critical | 1 | 0 | 1 | 20.63 | 18.85 | 14.92 | 54.4 | Summit Racing | SUM-220304 | https://www.summitracing.com/int/parts/sum-220304?retaillocation=int | No | Rhys | None | American | need for testing | Dejan | Maooz | Yes | Ethan | [6 empty] | Ordered
Part | brakes | Soft line (Braided) | Brake Line, Braided Stainless, 20 in. Length, Straight -3 AN Female, Straight -3 AN Female | Need longer braided lines for pedal adjustment considerations | Critical | 2 | 0 | 2 | 19.57 | 18.39 | 18.63 | 76.16 | Summit Racing | SUM-220306 | https://www.summitracing.com/parts/sum-220306 | No | Ethan | None |  |  | Dejan | Maooz | Yes | Ethan | [6 empty] | Ordered
Part | brakes | Brake pads | For CP4226, CP4227 rotors, CP4226D27-RX |  | Critical | 6 | 0 | 12 | ≈ $64 | need to contact |  |  | Atomic shop or MOCP | CP4226D27-RX | Atomic shop - https://atomic-shop.eu/products/ap-racing-cp4226d27-rx-pad-pair-2-7-00t MOCP - https://mailordercarparts.co.uk/ap-racing-pad-pair-2-7-00t-cp4226d27-rx | Yes, Old brake pads | Ethan | None |  | No North american vendors anymore. Old team vendor does not sell anymore | Dejan |  |  | PENDING
Part | brakes | Rubber Grommets | SBR Rubber Grommet for 5/16" Hole Diameter, 1/2" Flange Diameter | Sealing Firewall from brake lines | Critical | 5 | 95 | 100 | 18.31 |  |  |  | McMastercarr |  | https://www.mcmaster.com/products/grommets/grommets-1~~/id~3-16/for-material-thickness~1-16/hole-diameter~5-16/flange-diameter~1-2/ | No |  |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Total | [11 empty] | 1548.12
Pedal Box
Part | Pedal Box | BOTS | Switch toggle 3A 125V Minature | BOTS | Critical | 1 | 1 | 2 | 1.02 | 0 |  | 2.3052 | Digi Key | SW-T3-1A-A-A3-S1 | https://www.digikey.ca/en/products/detail/adam-tech/SW-T3-1A-A-A3-S1/15284460 | No | Filip/James |  | None | Can't get cheaper | Dejan | Maooz | Yes | Nathan | [6 empty] | Ordered
Fastener | Pedal Box | Spring | Torsion Spring, 120 Degree Left-Hand Wound, 0.56" OD | (Brake) Return Spring | Critical | 1 | 0 | 1 | 6.69 |  |  | 6.69 | Mcmaster | 9271K641 | https://www.mcmaster.com/products/torsion-springs/ | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | Pedal Box | MC Spacer | Aluminum Unthreaded Spacer, 13 mm OD, 10 mm Long, for M6 Screw Size | (Brake) Bias Bar Spacer | Critical | 2 | 1 | 3 | 1.16 |  |  | 3.48 | Mcmaster | 94669A175 | https://www.mcmaster.com/catalog/131/3731/94669A175 | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | Pedal Box | Bearing | Ultra-Low-Friction Oil-Embedded Sleeve Bearing, Flanged, for 1/4" Shaft Diameter and 3/8" Housing ID, 3/16" Long | (Brake) Bearing | Critical | 3 | 0 | 2 | 1.14 |  |  | 2.28 | Mcmaster | 1677K316 | https://www.mcmaster.com/products/1677k316/ | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
[12 empty] | 0 |  |  |  | No | Filip/James |  |  |  |  | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
[12 empty] | 0 |  |  |  | No | Filip/James |  |  |  |  | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
[12 empty] | 0 |  |  |  | No | Filip/James |  |  |  |  | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
[12 empty] | 0 |  |  |  | No | Filip/James |  |  |  |  | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
[12 empty] | 0 |  |  |  | No | Filip/James |  |  |  |  | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
[12 empty] | 0 |  |  |  | No | Filip/James |  |  |  |  | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
[8 empty] | 1 |  |  |  | 0 |  |  |  | No | Filip/James |  |  |  |  | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Fastener | Pedal Box | Fastener | Alloy Steel Shoulder Screw1/4" Shoulder Diameter, 3" Shoulder Length, 10-24 Thread | (Brake) Bias Bar Fastener | Critical | 1 | 1 | 1 | 3.18 |  |  | 3.18 | Mcmaster | 91259A106 | https://www.mcmaster.com/91259A106/ | No | James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | Pedal Box | Fastener | Ultra-Low-Friction Oil-Embedded Sleeve Bearing, Flanged, for 1/4" Shaft Diameter and 3/8" Housing ID, 1/4" Long | (Throttle) Bearing | Critical | 2 | 0 | 2 | 1.21 |  |  | 2.42 | Mcmaster | 1677K1 | https://www.mcmaster.com/products/1677k1/ | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | Pedal Box | Spring | Torsion Spring, 90 Degree Right-Hand Wound, 0.848" OD, 0.106" Wire Diameter | (Throttle) Return Spring RH | Critical | 1 | 0 | 1 | 4.48 |  |  | 4.48 | Mcmaster | 9271K113 | https://www.mcmaster.com/products/9271k113/ | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | Pedal Box | Spring | Torsion Spring, 90 Degree Left-Hand Wound, 0.848" OD, 0.106" Wire Diameter | (Throttle) Return Spring LH | Critical | 1 | 0 | 1 | 4.48 |  |  | 4.48 | Mcmaster | 9271K114 | https://www.mcmaster.com/products/9271k114/ | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | Pedal Box | Pin | 18-8 Stainless Steel Dowel Pin 5/32" Diameter, 1-1/4" Long | (Throttle) Reststop + Spring | Critical | 5 | 3 | 1 | 7.53 |  |  | 7.53 | Mcmaster | 90145A494 | https://www.mcmaster.com/90145A494/ | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | Pedal Box | Spring | Female Threaded Round Standoff, Aluminum, 1/2" OD, 1" Long, 10-32 Thread Size | (Throtle) Return Spring Shaft | Critical |  |  | 1 | 1.37 |  |  | 1.37 | Mcmaster | 93330A651 | https://www.mcmaster.com/catalog/131/3740/93330A651 | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | Pedal Box | Rotation Pin | Dowel Pin 4140 Alloy Steel, 1/4" Diameter, 1-7/8" Long | (Throttle) Rotation Pin | Critical |  |  | 1 | 3.31 |  |  | 3.31 | Mcmaster | 98381A430 | https://www.mcmaster.com/98381A430/ | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Part | Pedal Box | Rotation Pin | 416 Stainless Steel Dowel Pin 1/4" Diameter, 1-3/8" Long | (Brake) Rotation Pin | Critical |  |  | 1 | 9.75 |  |  | 9.75 | Mcmaster | 98380A545 | https://www.mcmaster.com/98380A545/ | No | Filip/James |  |  |  | Dejan | Maooz | Yes | P-CARD | [6 empty] | In Shop (Lead Notified)
Material | Headrest | Headrest Padding | SFI Approved High Density Foam, 16.3 x 18" Sheet, 1" thick |  | Critical |  |  |  | 41.99 | 50 |  | 91.99 | Pegasus Auto Racing Supply | SKU: 44007 | https://www.pegasusautoracing.com/productselection.asp?Product=2400-02 | No | James |  |  |  | Dejan | Maooz | Yes | PENDING | [6 empty] | Requires Cheq Req
Total | [11 empty] | 143.2652
Drive Train
Material | drivetrain | Aluminum | 16" x 10" x 0.75" plate 6061 Aluminum | Sprocket side DT mount | Critical | 1 |  | 1 | 145.16 |  |  | 145.16 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/aluminum-plate-6061/ |  | Ronnie |  |  | We have plate metal for this already
Material | drivetrain | Aluminum | 16" x 10" x 0.5" plate 6061 Aluminum | sensor side DT mount | Critical | 1 |  | 1 | 97.41 |  |  | 97.41 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/aluminum-plate-6061/ |  | Ronnie |  |  |  | Dejan | Maooz | Yes | Ronnie | [6 empty] | Ordered
Material | drivetrain | Aluminum | 6"x 6" x 0.375" plate 6061 Aluminum | Sensor side DT mount eccentric plate | Critical | 1 |  | 1 | 56.51 |  |  | 63.86 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/aluminum-plate-6061/ |  | Ronnie |  |  |  | Dejan | Maooz | Yes | Ronnie | [6 empty] | Ordered
Material | drivetrain | Aluminum | 6" x 6" x 0.625" plate 6061 Aluminum | Sprocket side DT mount eccentric plate | Critical | 1 |  | 1 | 38.73 |  |  | 38.73 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/aluminum-plate-6061/ |  | Ronnie |  |  |  | Dejan | Maooz | Yes | Ronnie | [6 empty] | Ordered
Material | drivetrain | Steel | 4" x 3.8" mild steel 1045 | Sprocket shaft | Critical | 1 |  | 1 | 80.22 |  |  | 90.65 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/mild-steel-round-bar-cold-rolled-1045/ |  | Ronnie |  |  |  | Dejan | Maooz | Yes | Ronnie | [6 empty] | Ordered
Part | drivetrain | Ball Bearing | 61810-2rs1 | Sensor side Diff Bearing | Critical | 1 |  | 1 | Sponsored |  |  | 0 | SKF | 61810-2rs1 | https://www.skf.com/ca/en/products/rolling-bearings/ball-bearings/deep-groove-ball-bearings/productid-61810-2RS1 |  | Ronnie |  |  |  | Dejan | Maooz | Yes | Sponser
Part | drivetrain | Ball Bearing | 61911-2rs1 | Sprocket Side Diff Bearing | Critical | 1 |  | 1 | Sponsored |  |  | 0 | SKF | 61911-2rs1 | https://www.skf.com/ca/en/products/rolling-bearings/ball-bearings/deep-groove-ball-bearings/productid-61911-2RS1 |  | Ronnie |  |  |  | Dejan | Maooz | Yes | Sponser
Part | drivetrain | Ball Bearing | 61908-2rs1 | Sprocket shaft Bearing | Critical | 1 |  | 1 | Sponsored |  |  | 0 | SKF | 61908-2rs1 | https://www.skf.com/ca/en/products/rolling-bearings/ball-bearings/deep-groove-ball-bearings/productid-61908-2RS1 |  | Ronnie |  |  |  | Dejan | Maooz | Yes | Sponser
Total | [11 empty] | 435.81
Grand Total | [11 empty] | #REF!

## EP Procurement
ans | [20 empty] | Approval |  |  |  | Procurement
Type | Subsystem | Item | Description (Size/Type/Brand Name) | Why you need it | Critical? | Quantity | Spares | Total Qty. | Unit Price (CAD) | Shipping Cost (CAD) | Estimated Duty Charge (Use this calculator) ($ CAD) | Total Cost (CAD) (Incl. Tax) | Vendor Name | Part No. | Link | Do we have this, or a similar item that could be designed for, in the shop? (If similar or same in shop/storage already, provide explanation) | Item added by (if new member, include lead/ apprentice working with as well): | Companies contacted to sponsor item or get discount (if none, provide reasoning) | Details on company sponsoring + discount code etc. | Comments | System Lead Approval: | Management Approval: | Final Approval? | Purchased by(This column can be filled out by leads who made a purchase | Added to a Purchase Request by: | Purchase Request Spreadsheet Link: | Shipping and Receiving emailed with shop availability for dropoff OR pickup date/time? | Duties Paid Ahead of Time? (<$250 on peoples' cards, >$250 on PCard) | Duties invoice link: | Pickup or dropoff date? | Order Status
Example | aero structural | Steel | 16" x 14" plate 4130 steel | for mounting ribs | Critical | 1 |  | 1 | 100 | 0 | 0 | 100 | Metal Supermarket | N/A |  | Using 5 sq. inches of existing material, need to buy this amount extra. | Rochelle, Rhythm | Metal Supermarkets (declined items and discount code), Company X (didn't respond after 2 weeks and a followup email). | None | Can pick it up from the Vaughan location | Ozge, Dejan, Emi | Maooz, Marta, Luca | Yes |  | Morgan | https://drive.google.com/drive/folders/1l6BRGBbI_woR5CXfgt1Ydn-UfLeRF23x?usp=share_link | Yes | N/A | N/A | Nov 26 1-5pm, shop dropoff, Morgan | Unpacked
Fasteners
Fastener | accumulator | Polypropylene Plastic Socket Head Screw | M4 x 0.7 mm Thread, 16 mm Long, Off-White |  | Critical | 3 |  | 3 | 7.5 |  |  | 22.5 |  |  | https://www.mcmaster.com/99477A136/ | [5 empty] | Emi | Maooz | Yes | P-CARD | [6 empty] | CHECK IF RECIEVED
Fastener | enclosures | 93640A143 | Nylon Plastic Socket Head Screw M4 x 0.7 mm Thread, 8 mm Long | Enclosure Lid Screws | Critical | 1 pack of 100 | 1 |  | 15.49 | [5 empty] | https://www.mcmaster.com/93640A143-93640A126/ | we have a 12 mm long, but i want 8 mm | Nathan |  |  |  | emi | Maooz | Yes | P-CARD | [6 empty] | CHECK IF RECIEVED
Fastener | enclosures | 94180A353 | Brass Tapered Heat-Set Inserts for Plastic M4 x 0.7 mm Thread Size, 4.7 mm Installed Length | Enclosure heat set insert | Critical | 1 pack of 100 |  | 1 | 21.82 | [5 empty] | https://www.mcmaster.com/94180A351/ | we have a tapered version, but its 4.7 mm long | Nathan |  |  |  | Emi | Maooz | Yes | P-CARD | [6 empty] | CHECK IF RECIEVED
Fastener | segment-prototype | Stainless Steel Wire-Lockable Socket Head Screws | 6-32 Thread Size, 5/16" Long (pack of 5) | fasten segments to container | Critical | 3 |  | 3 | 13.58 |  |  | 40.74 |  |  | https://www.mcmaster.com/catalog/131/3577/90152A143 | [5 empty] | emi | Maooz | Yes | Janaarth
Fastener | segment-prototype | Heat-Set Inserts for Plastic | Brass, 6-32 Thread Size, 0.226" Installed Length | fasten segments to container |  | 1 |  | 1 | 13.73 |  |  | 13.73 |  |  | https://www.mcmaster.com/catalog/131/3643/94459A731 | [5 empty] | emi | Maooz | Yes | Janaarth
Fastener | segment-prototype | thread deforming nuts | 18-8 Stainless Steel Top-Lock Distorted-Thread Locknut | fasten segment busbars |  | 1 |  | 1 | 24.18 |  |  | 24.18 |  |  | https://www.mcmaster.com/90045A111/ | [5 empty] | emi | Maooz | Yes | Janaarth
Fastener | segment-prototype | Medium-Strength Class 8.8 Steel Hex Head Screw | Zinc-Plated, M4 x 0.7 mm Thread Size, 8 mm Long | fasten segment busbars |  | 1 |  | 1 | 15.17 |  |  | 15.17 |  |  | https://www.mcmaster.com/91280A128/ | [5 empty] | emi | Maooz | Yes | Janaarth
Fastener |  | Center-Lock Distorted-Thread Locknuts Medium-Strength, Class 8 Steel, M6 x 1.00 mm Thread Size | Center-Lock Distorted-Thread Locknuts Medium-Strength, Class 8 Steel, M6 x 1.00 mm Thread Size | fasten segment busbars to maintenance plugs |  | 2 | 0 | 2 | 14.3 |  |  | 28.6 |  |  | https://www.mcmaster.com/92048A120/ | [5 empty] | emi | Maooz | Yes | Janaarth
Fastener |  | Black-Oxide Alloy Steel Hex Drive Flat Head Screw | 90 Degree Countersink, M4 x 0.7 mm Thread Size, 10 mm Long | fasten segment brackets together | Critical | 1 | 1 | 2 | 6.38 |  |  | 12.76 |  |  | https://www.mcmaster.com/91294A190/ | [5 empty] | emi | Maooz | Yes | Emi
AC Container Parts
Material | accumulator | Aluminum | 18" x 20" 6061 T6 0.125 | Container Floor | Critical | 1 | 0 | 1 | 90.84 |  |  | 90.84 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/aluminum-sheet-6061/ | no | Justin |  |  |  | Emi | Luca | Yes | Luca | [6 empty] | Recieved
Material | accumulator | Aluminum | 21" x 20" 5052 H32 0.090 | Container Lid | Critical | 1 | 0 | 1 | 60.11 |  |  | 60.11 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/aluminum-sheet-5052/ | no | Justin |  |  |  | Emi | Luca | Yes | Luca | [6 empty] | Recieved
Material | accumulator | Steel | 1.000 X 1.000 X 0.065 MILD STEEL STRUCTURAL (WELDED) SQUARE TUBE(10 inches) | Container Mounts - Frame Side | Critical | 1 |  | 1 | 7.54 |  |  | 7.54 | Metal Supermarket |  | https://www.metalsupermarkets.com/product/mild-steel-square-tube-structural-welded/ | no | Janaarth |  |  |  | Emi | Maooz | Yes | P-CARD | [6 empty] | CHECK IF RECIEVED
Fastener | accumulator | Steel | JIS High-Strength Steel Flanged Hex Head Screw M8 x 1.25 mm Thread, 50 mm Long | Container Mounts Bolts | Critical | 1 pack of 25 |  | 1 | 14.17 |  |  | 14.17 | Mcmaster Carr |  | https://www.mcmaster.com/95735A451/ | Maybe | Janaarth
Fastener | accumulator | Steel | JIS High-Strength Steel Flanged Hex Head Screw M8 x 1.25 mm Thread, 30 mm Long | Container Mounts Bolts | Critical | 1 pack of 25 |  | 1 | 10 |  |  | 10 | Mcmaster Carr |  | https://www.mcmaster.com/95735A425/ | Maybe | Janaarth
Material | accumulator | Aluminum | 40" x 35" 6061 T6 0.09 | Container walls | Critical | 1 |  | 1 |  |  |  | 7.54 | Metal Supermarket
Accumulator
Part | segment-prototype | Spot Welder | kWeld Spot welder full kit | to spot weld nickel busbars | Critical | 1 | 0 | 1 | 349.99 |  |  | 349.99 |  |  | https://gridrewired.com/products/kweld-spot-welder-kit | [5 empty] | Emi | Maooz | Yes | P-CARD | [6 empty] | In Shop
Part | segment-prototype | Spot Welder power source | kWeld battery pack | kCap Ultracapacitor Module | Critical | 1 | 0 | 1 | 284.99 |  |  | 284.99 |  |  | https://gridrewired.com/products/kcap-ultracapacitor-module?pr_prod_strat=jac&pr_rec_id=09dc970be&pr_rec_pid=6226590728391&pr_ref_pid=6224207904967&pr_seq=uniform | [5 empty] | Emi | Maooz | Yes | P-CARD | [6 empty] | In Shop
Material |  | Clear Impact-Resistant Polycarbonate | 24" x 24" x 1/8" Sheet | accu shelf |  | 1 | 0 | 1 | 30.67 | 31.11 |  | 61.78 |  |  | https://www.mcmaster.com/8574K53/ | [5 empty] | Emi | Maooz | Yes | Emi
Part | accumulator | RL00571-25 | Maintenance plug | Module Connection | Critical | 10 | 2 | 12 | 11.56 |  |  | 138.72 | Mouser |  | https://www.mouser.ca/ProductDetail/Amphenol-Technical-Products/RL00571-25?qs=HwcZ7FPCDholjztjy82bZg%3D%3D | [5 empty] | Emi | Maooz | Yes | arian
Part | accumulator |  | Positive Maintenance Plug Stud | Module Connection | Critical | 5 | 1 | 6 | 15.67 |  |  | 94.02 | Mouser |  | https://www.mouser.ca/ProductDetail/Amphenol-Technical-Products/RL9057-101-F1RE?qs=024T18Co8Yc7s8amuw8k9A%3D%3D | [5 empty] | Emi | Maooz | Yes | arian
Part | accumulator |  | Negative Maintenance Plug Stud | Module Connection | Critical | 5 | 1 | 6 | 12.76 |  |  | 76.56 | Mouser |  | https://www.mouser.ca/ProductDetail/Amphenol-Technical-Products/RL9057-101-F1-BK?qs=vDxCgdWo2h9eScpNHEOQhg%3D%3D | [5 empty] | Emi | Maooz | Yes | arian
Connector | accumulator | Larger crimps for AC I/O Connector - MALE | CONN PIN 16-20AWG GOLD CRIMP | Accu main IO | Critical | 25 | 0 | 25 | 0.777 |  |  | 19.425 | Mouser | 1060-16-0644 | https://www.mouser.ca/ProductDetail/TE-Connectivity-AMP/1060-16-0644-Loose-Piece?qs=k0bvAmZt86BxHy1Jmq%2Fzqg%3D%3D | [5 empty] | Emi |  |  | arian
Connector | accumulator | Crimp removal tool for Accu main I/O 16-20awg | HD30 EXT TOOL BLU | Accu main IO | Critical | 2 | 0 | 2 | 2.1 |  |  | 4.2 | Digikey | 0411-336-1605 | https://www.digikey.ca/en/products/detail/te-application-tooling/0411-336-1605/6566673 | [5 empty] | Emi |  |  | nathan | [6 empty] | In Shop
Connector | accumulator | Crimp removal tool for Accu main I/O 14-16awg | HD30 EXT TOOL GRN | Accu main IO | Critical | 2 | 0 | 2 | 2.21 |  |  | 4.42 | Digikey | 0411-291-1405 | https://www.digikey.ca/en/products/detail/te-application-tooling/0411-291-1405/6566674 | [5 empty] | Emi |  |  | nathan | [6 empty] | In Shop
Material | accumulator | Kapton® 100HN – A1 – 0.0504mm ¦ DuPont™ | 1 of the stock sheet sizes - 1000mm x 914mm | Electrical insulation of container | Critical | 1 |  | 1 | 116.8 |  |  | 116.8 |  |  | https://materials-direct.com/product/dupont-kapton-100hn-a1-0-0504mm/ | [5 empty] | Emi | Maooz | Yes | P-CARD | [6 empty] | Ordered
Part | motor-and-controller | FHLR2GCB2G 25 200-S Shielded 25mm2 | 25mm^2 HV high current wire for inside the accu (5m) |  | Critical |  |  | 0 | 141.66 | 110.56 |  | 252.22 |  |  | https://www.powertraincables.com/product/fhlr2gcb2g-200-s-25mm2/ | [5 empty] | Emi | Maooz | Yes | Emi
Material | accumulator | NOMEX® 410 – A1 – 0.18mm ¦ DuPont™ | 2 of the stock sheet sizes - 1000mm x 914mm | Electrical insulation of container | Critical | 2 |  | 2 | 53.99 | 155.8 |  | 263.78 |  |  | https://materials-direct.com/product/dupont-nomex-410-a1-0-18mm/ | [5 empty] | Emi | Maooz | Yes | P-CARD | [6 empty] | Ordered
Material |  | Kapton Tape | Acrylic Adhesive, 3/4" Wide, 15' Long, 0.0025" Overall Thickness | Electrical insulation of container | Critical | 2 | 0 | 2 | 12.12 |  |  | 24.24 |  |  | https://www.mcmaster.com/7648A734/ | [8 empty] | Emi
Material | accumulator | Hydrophobic Acoustic Mesh | It allows air and sound to pass but stops water, dust, and other contaminants. | To pass rain test | Critical | 2 | 1 | 3 | 150 | 83 |  | 233 |  |  | https://www.materialsampleshop.com/products/hydrophobic-acoustic-mesh |  | Justin
Part | accumulator | 4awg ring terminal | Terminals Battery Cable Lug, 4 AWG, 1/4" Stud |  | Critical | 6 |  | 8 | 1.92 |  |  | 15.36 |  |  | https://www.mouser.ca/ProductDetail/Panduit/A4-14R-C?qs=d0WKAl%252BL4KbzWfMI1w9Wzw%3D%3D
Accumulator Segments
Material | accumulator | PC filament for 3d printing | Creality PETG filament 1.75mm | segment brackets, other brackets | Critical | 2 |  | 2 | 22.55 |  |  | 45.1 |  |  | https://www.amazon.ca/Creality-PETG-No-Tangling-Performance-Dimensional/dp/B0B2J25NM3/ref=sr_1_11?crid=3ME8SOMOXIG73&dib=eyJ2IjoiMSJ9.vjefA8SLGHU0TdfJqkR3sE5a_b1PKEy4pk-bIfL3iKRArAJ3k7LzJTeVey7ufmCAIE-PzZiPljYI7aLItKF06TxvMbjMFBueyftVi6f2AZYVhc3vgLM3GnkAAZFyyC9-7_KINAzi0WokmOWDhw9gi5s5K_UGtyqSZ4m1PgmfXJ3xPn9gZwk9jmz8rpzybOB-TU9UUkF20tiKKrgRiyzRx9Gb_LdKPAMG_MVjCApB2Z0zDUSTtSp9_F5XnxhLvb3Gg_Z7-5MT2nP4PVCPhgnipbGTSj0lYRx7muxvQP8JJs0.NF6xrckLcyE6zj_2NrHO_6bkkWHmmMoE6_vT9ggTeoE&dib_tag=se&keywords=creality%2Bpetg&qid=1762113230&s=industrial&sprefix=creality%2Bpetg%2Cindustrial%2C114&sr=1-11&th=1
Connector | segment-prototype | Cell tap PCB fuses | Fuse (1206 surface mount, 500mA and 63 VDC rated) | cell tap pcbs | Critical | 105 | 45 | 150 | 0.976 |  |  | 165.432 | Digikey | 0440.500WR | https://www.digikey.ca/en/products/detail/littelfuse-inc/0440-500WR/2520404 | [5 empty] | Emi | Maooz | Yes | Owais | [6 empty] | Recieved
Connector | segment-prototype | Cell tap pcb fuses | FUSE BRD MT 375MA 125VAC/VDC | cell tap pcbs | Critical | 105 | 45 | 150 | 0.9851 |  |  | 147.77 | Dijikey | 0440.375WR | https://www.digikey.ca/en/products/detail/littelfuse-inc/0440-375WR/2520391
Material | segment-prototype | general PETG filament for segments | Polymaker PETG Filament 1.75mm, 1kg |  | Critical | 3 | 0 | 3 | 27.99 |  |  | 83.97 | Amazon |  | https://www.amazon.ca/dp/B09DKP4TLW?ref=cm_sw_r_apan_dp_HSJ81K3BD0SKAZ14MMKJ&ref_=cm_sw_r_apan_dp_HSJ81K3BD0SKAZ14MMKJ&social_share=cm_sw_r_apan_dp_HSJ81K3BD0SKAZ14MMKJ&starsLeft=1&skipTwisterOG=1&th=1
Material | segment-prototype | Garolite (FR4) | Flame-Retardant Garolite G-10/FR4 Sheet Multipurpose, 48" x 36", 1/8" Thick, Black | bracket | Critical | 1 |  | 1 | 291.71 |  |  | 291.71 | McMaster-carr | 85345K652 | https://www.mcmaster.com/85345K652/ | Emi |  |  |  |  | Emi
Material | segment-prototype | Garolite (FR4) | Flame-Retardant Garolite G-10/FR4 Sheet Multipurpose, 24" x 24", 1/8" Thick, Black | bracket | Critical | 1 |  | 1 | 116.68 |  |  | 116.68 | McMaster-carr | 85345K632 | https://www.mcmaster.com/85345K632/ | Emi |  |  |  |  | Emi
Connector | segment-prototype | Cell tap voltage connetor | 22 pin connector pcb mount | cell tap pcbs | Critical | 10 | 0 | 10 | 3.59 |  |  | 35.9 | Digikey | 430452227 | https://www.digikey.ca/en/products/detail/molex/0430452227/3310311?s=N4IgTCBcDaICwGYAMcCsYMHYQF0C%2BQA | Emi |  |  |  |  | Emi |  |  | nathan | [6 empty] | In Shop
Connector | segment-prototype | Cell tap temp connetor | 12 pin connector pcb mount | Cell tap pcbs | Critical | 10 |  | 10 | 4.04 |  |  | 40.4 | Digikey | 430451226 | https://www.digikey.ca/en/products/detail/molex/0430451226/3310224?s=N4IgTCBcDaICwGYAMcCsBGMYBsIC6AvkA | Emi |  |  |  |  | Emi |  |  | nathan | [6 empty] | In Shop
Connector | segment-prototype | Cell tap temp connetor | 12 pin CONN RCPT HSG 12POS 3.00MM | Cell tap pcbs | Critical | 10 | 0 | 10 | 0.67 |  |  | 6.7 | Digikey | 430251208 | https://www.digikey.ca/en/products/detail/molex/0430251208/3310168?s=N4IgTCBcDaICwGYAMYCsBGMSAcIC6AvkA | Emi |  |  |  |  | Emi |  |  | nathan | [6 empty] | In Shop
Connector | segment-prototype | Cell tap temp connetor | CONN RCPT HSG 22POS 3.00MM | Cell tap pcbs | Critical | 10 | 0 | 10 | 1.97 |  |  | 19.7 | Digikey | 430252208 | https://www.digikey.ca/en/products/detail/molex/0430252208/4693201?s=N4IgTCBcDaICwGYAMYCsYxIBwgLoF8g | Emi |  |  |  |  | Emi |  |  | nathan | [6 empty] | In Shop
Connector | segment-prototype | microfit3.0 removal tool | TOOL HAND EXTRACT MICROFIT 3.0 | Cell tap pcbs | Critical | 1 | 0 | 1 | 40.53 |  |  | 40.53 | Digikey | 11030043 | https://www.digikey.ca/en/products/detail/molex/0011030043/252489?s=N4IgTCBcDaIAxwIyLgZgQFlSAugXyA | Emi |  |  |  |  | Emi |  |  | nathan | [6 empty] | In Shop
services | segment-prototype | Cell tap PCB manufacturing services | Cell tap PCB | Cell tap PCB | Critical | 10 |  |  | 125.91 | 32.2 |  | 158.46 | PCBWAY |  | https://www.pcbway.com/orderonline.aspx
Material | segment-prototype | Nickel Busbars, lasercut | 0.15mm, all pieces |  |  | 1 |  | 1 | 203.76 |  |  | 280 | [11 empty] | Emi
sensor | segment-prototype | Temp sensors | JT series 50 mm length film type NTC sensor | segments temp monitorting | Critical | 50 | 0 | 50 | 0.686 |  |  | 38.759 | Digikey | 4316-103JT-050-ND | https://www.digikey.ca/en/products/detail/semitec-usa-corp/103jt-050/16579006?_gl=1*7oqwze*_up*MQ..*_gs*MQ..&gclid=CjwKCAiAwqHIBhAEEiwAx9cTee-pfJgNrbfgKEWeLlwkCv02Xf_RdIpl7QLbkO8qpiO-2okg8RosuhoC2-EQAvD_BwE&gclsrc=aw.ds&gbraid=0AAAAADrbLlgra9cGyKmpyfBAwMAHTt6rL |  |  |  |  | 10/segments, extra 1/seg | Emi |  |  | Owais | [6 empty] | Recieved
wire | segment-prototype | wire for side brackets to Cu plates | 32 AWG kapton insulated wire, 30ft | segments temp monitorting | Critical | 1 |  |  | 51 |  |  | 51 | acu glass product | 113094 | https://www.accuglassproducts.com/wire-and-cable/kapton-insulated/stranded-wires/32-awg
Material | segment-prototype | Lubrication for cell tap connectors | Electrical Contact Grease, Conductive Grease, Copper Anti-Seize Compound, High Temperature for Electronics, 30g | Cell tap Connector durability | Critical | 1 |  |  | 13.99 |  |  | 14.14 | qzjijosen |  | https://www.amazon.ca/Conductive-Temperature-Multipurpose-Electronics-Construction/dp/B0DDKH9HY7
Material | segment-prototype | Epoxy | 8329TFF – Fast Cure Thermal Adhesive | sensor adhesive | Critical | [6 empty] | 84 | mouser |  | https://mgchemicals.com/products/adhesives/thermally-conductive-adhesives/thermal-glue/
Connector | segment-prototype | SDC board 4pin mating connector | CONN RCPT HSG 4POS 4.20MM | SDC pcb | Critical | 5 |  | 5 | 0.43 |  |  | 2.15 | Digikey | 39012045 | https://www.digikey.ca/en/products/detail/molex/0039012045/685976 | [8 empty] | nathan | [6 empty] | In Shop
Motor/Motor Controller
Connector | accumulator | SLPPB35BSO1EH | SURLOK PLUS 8.0MM RIGHT ANGLE PL. 270deg keyway, used on all MC connections and one AC connection. |  | Critical | 3 | 0 | 3 | 39.07 |  |  | 117.21 | Digikey | SLPPB35BSO1EH | https://www.digikey.ca/en/products/detail/amphenol-industrial-operations/SLPPB35BSO1EH/9385626 | [8 empty] | nathan | [6 empty] | In Shop
Cooling
Part | cooling | Radiator | Alphacool NexXxos ST30 Full Copper X-Flow Radiator, 240mm, Dual Fan, Black |  | Critical | 1 | 0 | 1 | 102.7363 | 49.2515 | 8.7326 | 174.0761 | Titan Rig | 03-30-AC-0140-01-ON | https://www.titanrig.com/alphacool-nexxxos-st30-full-copper-x-flow-radiator-240mm-dual-fan-black.html
Part | cooling | Radiator Fan | Alphacool Core 120mm PWM Fan, 4000 rpm, 2-pack |  | Critical | 1 (2 pack) | 0 | 1 (2 pack) | 37.5654 |  |  | 42.4489 | Titan Rig | 03-10-AC-0121-01-ON | https://www.titanrig.com/alphacool-core-120mm-pwm-fan-4000-rpm-2-pack.html
Part | cooling | Hose conector | 6Pcs G1/4" Thread to 3/8" Barb Fitting Hose Connector for 9-10mm Inner Diameter Hose 25x9.8x9.2mm (Black) |  | Critical | 1 (6 pack) | 0 | 1 (6 pack) | 11.31 |  |  | 12.7803 | Amazon | ‎686-B-HB | https://www.amazon.ca/Briny-River-Connector-Diameter-25x9-8x9-2mm/dp/B0F62H2VVJ/ref=sr_1_8?dib=eyJ2IjoiMSJ9.JevZxBe9gvGUrFD2N35_c3_-qP5ruZlSqZk5--7SHG93QgCygTmjOxrSVvogL-2s7pMVtponnk2dNYudJW3EsF4KWhhxN8hePxdEdDEjkMNuatYjRN6khXyAkxJz5PUPm06n2wf1UUKgXZOVhnmu4t5GIS4zgg4WEFP2CwgIpmOx9u56Q13Bqj1dn-DKOPYPo4i7Kgw7XtTTgh12aSkVUI2w7DQ9dA0Rt8moumc9on5bqZsi8w_kdfHJfn81JnsdDiun9utoilOpY48jhVx8kHX72obCKtUHi_-v7mxwehk.UCFwi1JThCx2RQyQyENRjJ-FLSLRF9tI31bfgwMWmuc&dib_tag=se&gad_source=1&hvadid=668188319980&hvdev=c&hvexpln=0&hvlocphy=9000762&hvnetw=g&hvocijid=4173603434009327600--&hvqmt=e&hvrand=4173603434009327600&hvtargid=kwd-359699516559&hydadcr=24948_13702409&keywords=g1%2F4%2Bto%2B3%2F8%2Bbarb&mcid=7cce7905aebd3d659a6d9a135d79dc8e&qid=1766441528&sr=8-8&th=1
0
Shutdown Circuit
Part |  | 15kOhm Resistor | HSA5015KE | for discharge / tsmps | Critical | 3 |  | 3 | 6.44 | N/A | N/A | 21.8316 | Digikey | A131873-ND | https://www.digikey.ca/en/products/detail/te-connectivity-passive-product/HSA5015KE/2366461 | [5 empty] | Emi |  |  | Owais | [6 empty] | Recieved
GLV Integration
Connector | glv | MHDB9SP | 9 Position D-Sub Plug, Male Pins Connector | connecting to motor controller | Critical | 1 | 1 | 2 | 0.56 |  |  | 1.2656 | Digikey |  | https://www.digikey.ca/en/products/detail/mh-connectors/MHDB9SP/16984080 | yes | Nathan |  |  |  | emi |  |  | Emi | [6 empty] | In Shop (Lead Notified)
Connector | glv | A-DF 09 LL/Z | 9 Position D-Sub Receptacle, Female Sockets Connector | connecting to AC | Non-critical | 1 | 1 | 2 | 0.77 |  |  | 1.7402 | Digikey |  | https://www.digikey.ca/en/products/detail/assmann-wsw-components/A-DF-09-LL-Z/5051922 | yes | Nathan |  |  |  | emi |  |  | Emi | [6 empty] | In Shop (Lead Notified)
Connector | glv | Male pin for DTM04-1pa | CONN PIN 16-20AWG NICKEL CRIMP | for all dtm connectors, AC IO too | Critical | 100 | 0 | 100 | 0.18 |  |  | 20.34 | Digikey | 1060-16-0622 | https://www.digikey.ca/en/products/detail/te-connectivity-deutsch-ict-connectors/1060-16-0622/6566707 | [5 empty] | Emi |  |  | Emi | [6 empty] | In Shop (Lead Notified)
Connector | glv | Female socket for dtm06-12sa | CONN SCKT 16-20AWG NICKEL CRIMP | for all dtm connectors, AC IO too | Critical | 100 | 0 | 100 | 0.35345 |  |  | 39.9398 | Digikey | 1062-16-0622 | https://www.digikey.ca/en/products/detail/te-connectivity-deutsch-ict-connectors/1062-16-0622/6566725 | [5 empty] | Emi |  |  | Emi | [6 empty] | In Shop (Lead Notified)
Connector | wire harness | DTM04-12PA-L012 | 12 pin male terminals, wire to panel | connector for wire harness | Critical | 3 | 0 | 3 | 11.27 |  |  | 38.2053 | Digikey | DTM04-12PA-L012 | https://www.digikey.ca/en/products/detail/te-connectivity-deutsch-ict-connectors/DTM04-12PB-L012/7220052 | yes just need more spares | Nathan |  |  |  | Emi |  |  | Emi | [6 empty] | In Shop (Lead Notified)
Connector | wire harness | DTM06-12SA | 12 pin female terminals, wire to wire | connector for wire harness | Critical | 3 | 0 | 3 | 2.45 |  |  | 8.3055 | Digikey | DTM06-12SA | https://www.digikey.ca/en/products/detail/te-connectivity-deutsch-ict-connectors/DTM06-12SA/6566630 | yes just need more spares | Nathan |  |  |  | Emi |  |  | Emi | [6 empty] | In Shop (Lead Notified)
Connector | wire harness | DTM06-12SB | 12 pin female terminals, wire to wire | connector for wire harness | Critical | 3 | 0 | 3 | 2.45 |  |  | 8.3055 | Digikey | DTM06-12SB | https://www.digikey.ca/en/products/detail/te-connectivity-deutsch-ict-connectors/DTM06-12SB/6566631 | yes just need more spares | Nathan |  |  |  | Emi | Maooz | Yes | Emi
Connector | wire harness | DTM06-3S | dtm 3 pin female | connector for wire harness | Critical | 11 |  |  | 1.82 |  |  | 20.11 | Digikey | dtm06-3s | https://www.digikey.ca/en/products/detail/te-connectivity-deutsch-ict-connectors/DTM06-3S/6566634 | no | Nathan |  |  |  | Emi |  |  | Nathan | [6 empty] | Ordered
Connector | wire harness | DTM04-3P | dtm 3 pin male | connector for wire harness | Critical | 11 |  |  | 2.34 |  |  | 25.67 | Digikey | dtm04-3p | https://www.digikey.ca/en/products/detail/te-connectivity-deutsch-ict-connectors/DTM04-3P/6566644 | no | Nathan |  |  |  | Emi |  |  | Nathan | [6 empty] | Ordered
Part | wire harness | AMber LEDs for RTML | LED Clearance or Side Marker Light - 3-3/4" Rectangle - 12 LEDs - Amber |  | Critical | 2 | 0 | 2 | 9.68 | 24.73 |  | 44.09 | SuperBrightLeds |  | https://www.superbrightleds.com/vehicle-lights/signal-lighting/marker-clearance/led-clearance-or-side-marker-light-3-3-4-rectangle-12-leds+color-amber | [5 empty] | emi
Part | glv | 555-timer for lightboard | SOIC-8 pin NA555DR , digikey | creates the blinking for the RTML light | Critical | 1 | 1 | 2 | 0.78 |  |  | 0.78 | Digi key | 296-21752-1-ND | https://www.digikey.ca/en/products/detail/texas-instruments/NA555DR/1571933 |  | Camila, Emi |  |  | we only need 1 for thr actual desing, but the second one is a backup
Part | glv | mosfet for RTML and TSSI circuits | SOT-23 AO3400A mosfet | used to power both TSSI and RTML lights | Critical | 3 | 3 | 6 | 4.02 | 9.09 |  |  | Digi key | 785-1000-1-ND | https://www.digikey.ca/en/products/detail/alpha-omega-semiconductor-inc/AO3400A/1855772
Part | glv | 12 pin header | 12 pin SMD header, mouser, 3.0mm pitch | used to connect lights on dashboard to lightboard | Critical | 1 | 1 | 2 | 4.62 |  |  |  | Digi key | WM23804-ND | https://www.digikey.ca/en/products/detail/molex/0039288100/930300?s=N4IgTCBcDaIMwE4C0YAcTUEYAM2QF0BfIA
Part | glv | dc-dc converter for LV battery | XINGYHENG 2Pcs 20A 300W High-Power Buck Converter Module DC 6-40V to DC 1.2-36V Adjustable Constant Voltage Constant Current | control LV power | Critical | 1 | 0 | 1 | 23.99 |  |  | 23.99 | amazon |  | https://www.amazon.ca/XINGYHENG-High-Power-Converter-Adjustable-Protection/dp/B0978Y8FTM/ref=pd_ci_mcx_mh_mcx_views_0_title?pd_rd_w=q1jqe&content-id=amzn1.sym.2419cdd9-4822-439a-9284-599ac1726c07%3Aamzn1.symc.c3d5766d-b606-46b8-ab07-1d9d1da0638a&pf_rd_p=2419cdd9-4822-439a-9284-599ac1726c07&pf_rd_r=J0Q5THQTY5K7RE3VRG84&pd_rd_wg=K8UPc&pd_rd_r=f38de8cc-d1a3-4aa5-af54-d0f38aaf264c&pd_rd_i=B0978Y8FTM | [5 empty] | emi
|  | 10 Pack LM2596 DC-DC Buck Converter Step Down Module Power Supply DIP Output 1.25V-30V 3A |  | control LV power | Critical | 1 | 0 | 1 | 15.67 |  |  | 15.67 | amazon |  | https://www.amazon.ca/BULVACK-LM2596-Converter-Module-1-25V-30V/dp/B07VVXF7YX/ref=sr_1_8?crid=3TRZK72SYTVMQ&dib=eyJ2IjoiMSJ9.eZNYeiFBzdJ20gbJGxTZORNp19GV7oumDSWTWXpDDYKPO2t_VHDEluGMy1TzwjZrwngfbunI4tl6LOARKLE2_aOJRE1S8K4TLL-GOELX1qN9u5-Lji8pKqMzUf1kDKQ5mafcuR6_ZyCva5yFwj9LO0HyI4dESpcMnWQr3ImU7-d4u0f4DJS9wyH6HrgCzbgE7_xUniG0xzRZC_zRX0VO_N1v9sGmrAAyDwm4GXAZ34_tbBMBHqKHBZOmrIvev-CvH3Odn-TElRCJWHnXzxU7LseJYXB_yDfYkv8rQYORk0Q.tZztPn04-G3gKqDGMm3eMQoEtI99VumC6KMqJKe8040&dib_tag=se&keywords=buck%2Bconverter%2B12v%2Bto%2B5v&qid=1768344153&sprefix=buck%2Bconverter%2B12v%2Bto%2Caps%2C135&sr=8-8&th=1 | [5 empty] | emi
Part | wire harness | DTM6P-BT | boot for DTM04-6P | extra protection and strain relief | Non-critical | [7 empty] | Digikey or mouser |  |  | yes just need more spares | Nathan
Part | wire harness | DTM6S-BT | boot for DTM06-6S | extra protection and strain relief | Non-critical | [7 empty] | Digikey or mouser |  |  | yes just need more spares | Nathan
Part | wire harness | DT12P-BT-BK | boot for DTM04-12PA-L012 | extra protection and strain relief | Non-critical | [7 empty] | Digikey or mouser |  |  | yes just need more spares | Nathan
Part | wire harness | DT12S-BT-BK | boot for DTM06-12SA | extra protection and strain relief | Non-critical | [7 empty] | Digikey or mouser |  |  | yes just need more spares | Nathan
Part | wire harness | Sumitomo W5DL | Semi-Rigid Shrink Tube for Transitions and Stain Relief: 2.5:1 | upgrade from what we have (FP 301 by 3M) | Non-critical | [7 empty] | Digikey or mouser |  |  | yes but this will be an upgrade | Nathan |  |  | i still need to determine what diameter to buy
Part | wire harness | 1/8" INDENT KIT 10 COLORS | by prowireusa, to differentiate wire by color | i wouldnt get it right now because its not that necesssary and its expensive cus USD and shipping | Non-critical | [7 empty] | prowireusa |  | https://www.prowireusa.com/PRO-IDENT-KIT | no | Nathan
Part | wire harness | Sumitomo W3B2 | more flexible version to W5DL | upgrade from what we have (FP 301 by 3M) | Non-critical | [7 empty] | Digikey or mouser |  |  | yes but this will be an upgrade | Nathan |  |  | i still need to determine what diameter to buy
Part | wire harness | HFT5000 | heat shrink fabric tubing, protect against heavy abrasion | upgrade from what we have | Non-critical | [7 empty] | Digikey or mouser |  |  | yes but this will be an upgrade | Nathan
Connector | wire harness | Molex Versakrimp | Terminal Inline, Individual Openings (Parallel) Connector Crimp | replaces solder joint, provides better mechanical strength and strain relief | Non-critical | [7 empty] | Digikey or mouser |  |  | no | Nathan
Part | wire harness | zip ties | Zip Ties Assorted Sizes 1000 Pack 14+12+10+8+6+4 Inch Cable Ties Heavy Duty Plastic Wire Ties UV Resistant Zipties White Small Zip Tie Wraps Assortment Cord Management for Home, Office, Gardening |  | Critical | 1000 | 0 | 1000 | 19.79 | 0 |  | 22.3627 | Amazon |  | https://www.amazon.ca/Assorted-Resistant-Assortment-Management-Gardening/dp/B0C4B9B5S4/ref=sr_1_1_sspa?crid=3S9DI0DJOPDWD&dib=eyJ2IjoiMSJ9.KHXCzj8Vd7Erky6nvlpM_2ojto3ZwotoMDhRzL7HiNd85q0ZLcGVCYk2M7wWyN1f-pHpRkzhbVyShynY6IVGERYNgAJyJkB3_FvWRKywUeoYKRryznxKUE7zclrMvlDBg9buIelhXta8lJEzn_A6n9tL98141S44foqscSmBJPhMtzgYwJuo15jGuQ2mPOQRYPqF8wPWX4PgnPj1lP3f1X7b0Etiksw7PwAqpQA6tJXRN2gxHtQPfROubz_OtI76kR--i7FzF6rnenhUs6uC1e1gwIeJLPNo1Qxo02UorT4.uSYxEU-hQm0ZiU4cAvKzQZ8vxpN4qqEKeXFPSBfcEQE&dib_tag=se&keywords=zip%2Bties%2Bassorted%2Bsizes%2B1000%2Bpack&qid=1769471341&sprefix=zip%2Bties%2Bassorted%2Bsizes%2B1000%2Bpack%2Caps%2C95&sr=8-1-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&th=1 | no | Janaarth |  |  |  | Emi | [9 empty] | Ordered
Part | wire harness | white electrical tape | Electrical Tape, 6 Pcs White Insulation Tape, 15m Waterproof Tape for Home Vehicle Auto, Car Power Circuit Wiring |  | Critical | 1x6 | 0 | 6 | 8.99 | 0 |  | 10.1587 | Amazon |  | https://www.amazon.ca/Electrical-Waterproof-Adhesive-Retardant-0-6Inch/dp/B0BPBTN6LX/ref=sr_1_2_sspa?crid=3C2GS7UX6XQ6Y&dib=eyJ2IjoiMSJ9.19mqmfnLUedaQ6p_pOCyY8mGpMBXveAvct0rqszrSgfoac9spXsNt_8hdBhWpenlFlNvuNitnnjIZf_oEkmJyDGjwr9XZxsdC3o9BUq-nkV7N8c1sewOXAyJu-9aQLpf0YwfHOpWNoIaE-cN7TrMXaGwB1DQlUhc87N-UI4zKQdCWCKHS06NjhkBv-7lXt5-uTn60tNT6fTzuo8nlxsOoZ9_Atg3rBlOILhBF9H8JZNsjG6BxOr8hxzxwONtXqGUNNBPkFvy_00XYtjvPGV69aPHSvXjtftsa6i443Irwbc.7d0ID7Vg55WrlaNPa-OgamakNz9YMnASVJep6pj3OUg&dib_tag=se&keywords=electrical%2Btape%2C%2B6pcs%2Bblack%2Bwaterproof&qid=1769471150&sprefix=electrical%2Btape%2C%2B6pcs%2Bblack%2Bwaterproof%2Caps%2C100&sr=8-2-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&th=1 | no | Janaarth |  |  |  | Emi | [9 empty] | Ordered
Part | wire harness | black electrical tape | Electrical Tape, 6 Pcs Black Waterproof Tape, Adhesive Gaffer Tape for Flame Retardant, 0.6Inch * 49.2FT |  | Non-critical | 1x6 | 0 | 6 | 10.99 | 0 |  | 12.4187 | Amazon |  | https://www.amazon.ca/Electrical-Waterproof-Adhesive-Retardant-0-6Inch/dp/B0B7DX2Z7J/ref=sr_1_2_sspa?crid=3C2GS7UX6XQ6Y&dib=eyJ2IjoiMSJ9.19mqmfnLUedaQ6p_pOCyY8mGpMBXveAvct0rqszrSgfoac9spXsNt_8hdBhWpenlFlNvuNitnnjIZf_oEkmJyDGjwr9XZxsdC3o9BUq-nkV7N8c1sewOXAyJu-9aQLpf0YwfHOpWNoIaE-cN7TrMXaGwB1DQlUhc87N-UI4zKQdCWCKHS06NjhkBv-7lXt5-uTn60tNT6fTzuo8nlxsOoZ9_Atg3rBlOILhBF9H8JZNsjG6BxOr8hxzxwONtXqGUNNBPkFvy_00XYtjvPGV69aPHSvXjtftsa6i443Irwbc.7d0ID7Vg55WrlaNPa-OgamakNz9YMnASVJep6pj3OUg&dib_tag=se&keywords=electrical%2Btape%2C%2B6pcs%2Bblack%2Bwaterproof&qid=1769471150&sprefix=electrical%2Btape%2C%2B6pcs%2Bblack%2Bwaterproof%2Caps%2C100&sr=8-2-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&th=1 | no | Janaarth |  |  |  | Emi | [9 empty] | Ordered
Part | wire harness | zip tie mounts | Zip Tie Mounts - Small Cable Tie Adhesive Mount, 1n black 100PCS |  | Critical | 1x100 | 0 | 100 | 9.78 | 0 |  | 11.0514 | Amazon |  | https://www.amazon.ca/Zip-Tie-Mounts-Adhesive-backed-anchors-Management/dp/B08Y6Q1H2Y/ref=sr_1_6?crid=1GDKDG80V6DVA&dib=eyJ2IjoiMSJ9.mE6O-POIy6OsGGhLfGnJS6SlMqgWXXrpxFqK2Fge9Pm8Dbp_MiMR_OenwAwoqlNOP4sT842DRdmVtsF1avBNKXpUfK_AwQ6twbyIxwsYFj5RKz_QAqoYmEePuWQpafSbaSXdzcSb6eIKNP_EZda4cG0-14mbUqpaYJ-RoACmj_e4v3_pv9Hm0b659wFRkXTZvvKDgaSagpH1eQvCGW2IEGhZCaMxp4Za45FHl1riEf9Q92Nz-xPItNPG2Dy0TkbZd2h0ca8uVSb2ccBj2BcMvLxWa2XNim4NzGFN6qAqOpU.Tvp7LIno8IAmv5r8VJLwVq7BTaBY9gnffzGNaHRhNvc&dib_tag=se&keywords=zip%2Btie%2Bmounts%2B-%2Bsmall%2Bcable%2Btie%2Badhesive%2Bmounts&qid=1769471006&sprefix=zip%2Btie%2Bmounts%2B-%2Bsmall%2Bcable%2Btie%2Badhesive%2Bmount%2Caps%2C119&sr=8-6&th=1 | no | Janaarth |  |  |  | Emi | [9 empty] | Ordered
Part | wire harness | velcro cable ties | 80PCS Reusable Cable Ties, Black Adjustable 6-Inch Cord Organizer Ties |  | Non-critical | 1x80 | 0 | 80 | 9.99 | 0 |  | 11.2887 | Amazon |  | https://www.amazon.ca/Adjustable-Organizer-Multi-purpose-Management-Organizing/dp/B08V8NK5TN/ref=sr_1_5?crid=2IG69TG25GNTX&dib=eyJ2IjoiMSJ9.QCb5rfdrbq8zWbFEZnzTKs3GdjL19acT2KVhI2LXs2H3dPa_hqw2vcWXCr0BA3OCJdGWdc2eRxPMM9F8n7bLn8A3s1KPWRSuSQ1_WMkCocObw6vC8PtUoNwK4pUk5dq77qiSVZJIdodMbrlR5w9f0Yq9AQ9fHL0E9IXO4jFRrXxUbbx9XFwwsN65a1T5eTRYZKO57WN0emJ4GL7i7NpuX2Ocq2qG-7BPdEjtSZzUZ6Qob0E3tUrWZ7PKd7EIsv4YgEaxzNbovGONp493DLI0nKTBKz1h9VqGb4M6CQ8z-hw.MUMIbALzLRX5ZBEImGVT6G3LykFpjGnXuDHh9HQJkZ0&dib_tag=se&keywords=oneleaf%2B80pcs%2Breusable%2Bcable%2Bties&qid=1769470680&sprefix=one%2Bleaf%2B80%2Bpcs%2Breusabl%2Caps%2C85&sr=8-5&th=1 | no | Janaarth |  |  |  | Emi | [9 empty] | Ordered
Connector | wire harness | 22012067 | 6 pos molex connector for bspd | wire harness | Critical | 5 |  | 5 | 0.2 | 0 |  | 1.13 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Connector | wire harness | 39012025 | 2 pos molex connector for pcbs | wire harness | Critical | 10 |  | 10 | 0.431 | 0 |  | 4.8703 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Contacts | wire harness | 1060-16-0677 | tin for tm26 firewall male | wire harness | Critical | 50 |  | 50 | 0.28 | 0 |  | 15.82 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Contacts | wire harness | 1062-16-0677 | tin for tm26 firewall female | wire harness | Critical | 50 |  | 50 | 0.29 | 0 |  | 16.385 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Contacts | wire harness | 770520-3 | gold for mc_io female | wire harness | Critical | 6 |  | 6 | 1 | 0 |  | 6.78 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Contacts | wire harness | 8500113 | tin for bspd female connector | wire harness | Critical | 100 |  | 100 | 0.068 | 0 |  | 7.684 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Contacts | wire harness | 39000039 | tin for molex female connectors | wire harness | Critical | 100 |  | 100 | 0.15 | 0 |  | 16.95 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Contacts | wire harness | 1062-20-0177 | tin for dtm female | wire harness | Critical | 250 |  | 250 | 0.21 | 0 |  | 59.325 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Part | dash | PEC11L-4020K-S0020 | ROTARY ENCODER | dash | Critical | 2 |  | 2 | 2.66 | 0 |  | 6.0116 | Digikey |  |  | no | Nathan |  |  |  | Emi | [9 empty] | Ordered
Sensor Integration
Part | glv | VCU PCB |  | PCB | Critical | 1 | 4 | 5 | 2.94 | 11.66 | N/A | 27.05 | JLCPCB | N/A |  | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop
Part | glv | CAN Transiver | MCP2551 | PCB | Critical | 4 | 8 | 12 | 2.95 | N/A | N/A | 40.002 | Sayal Electronics |  | https://canada.newark.com/microchip/mcp2551-e-sn/can-transceiver-1mbps-1-1-5-5v/dp/92C4186 | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop
Part | glv | Driver Pace guide light | NeoPixel Compatible WS2812 5050 RGB LED (8 LED Stick) | Dash | Critical | 1 | 1 | 2 | 2.95 | N/A | N/A | 6.667 | Sayal Electronics |  | https://www.canadarobotix.com/products/2740 | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop
Connector | glv | Connector | Connector Header Through Hole, Right Angle 20 position 0.165" (4.20mm) | PCB | Critical | 2 | 2 | 4 | 2.12 | 15 | N/A | 9.5824 | DIGIKEY | WM1360-ND | https://www.digikey.ca/en/products/detail/molex/0039301200/561086?s=N4IgTCBcDaIAxwMwE5FwIxgSAugXyA | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop
Connector | glv | Connector | 20 Rectangular Connectors - Housings Receptacle Natural 0.165" (4.20mm) | PCB | Critical | 2 | 2 | 4 | 1.23 | N/A | N/A | 5.5596 | DIGIKEY | WM3709-ND | https://www.digikey.ca/en/products/detail/molex/0039012200/278162 | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop
Connector | glv | Connector | CONN HDR 38POS 0.1 GOLD PCB | PCB | Critical | 2 | 2 | 4 | 2.28 | N/A | N/A | 10.3056 | DIGIKEY | S7122-ND |  | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop
Connector | glv | Resistor | RES 330 OHM 5% 1/4W 1206 | PCB | Critical | 5 | N/A | 5 | 0.02 | N/A | N/A | 9.153 | DIGIKEY | 311-330ERCT-ND |  | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop
Connector | glv | Zener Diode | DIODE ZENER 3.3V 500MW SOD123 | PCB | Critical | 30 | N/A | 30 | 0.06 | N/A | N/A | 1.8 | DIGIKEY | BZT52C3V3-7-F | https://www.digikey.ca/en/products/detail/diodes-incorporated/BZT52C3V3-7-F/717734 | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop
Connector | glv | Connector | CONN HDR 24POS 0.1 GOLD PCB | PCB | Critical | 2 | 3 | 5 | 1.54 | N/A | N/A | 7.7 | DIGIKEY | PPPC241LFBN-RC | https://www.digikey.ca/en/products/detail/sullins-connector-solutions/PPPC241LFBN-RC/810196 | No | N/A | N/A | N/A | N/A | Emi |  | Yes | Owais | [6 empty] | In Shop

## Sheet Metal Procurment
Material | Material (if other) | Thickness (in) | Dimensions (l x w, in) | Qty | Part Name/Description | Sub-System | Lead | Link | Notes
4130 | N/A | 0.125 | 8x16 | 1 | Harness tab | Aero Structural | Filip P |  |  | Example
Mild Steel/Other | N/A | 0.06 | 8 x 8 | 1 | Steering Rack Tab | Steering | Luca
6061 | N/A | 0.032 | 22.22x16 | 1 | Top Firewall | Frame-Sub | Matteo
6061 | N/A | 0.032 | 22.22x17.6 | 1 | Lower Firewall | Frame-Sub | Matteo
6061 | N/A | 0.05 | 39.8x20.9 | 1 | Front floor | Frame-Sub | Drew
6061 | N/A | 0.05 | 21.2x22.5 | 1 | Rear floor | Frame-Sub | Drew
4130 | N/A | 0.032 | 7x8 | 1 | top Firewall Tabs | Frame-Sub | Matteo |  | look to use scrap metal in shop before ordering
4130 | N/A | 0.05 | 3.36x3.36 | 1 | Lower Firewall tab | Frame-Sub | Matteo |  | look to use scrap metal in shop before ordering
6061
Material | Material (if other) | Thickness (in) | Dimensions (l x w, in) | Qty | Part Name/Description | Sub-System | Lead | Link | Notes
6061 |  | 1/4" | 4.5 x 14 | 2 | FW Mounts | Aero Structural | Anisha
6061 |  | 1/4" | 8 x 21 | 2 | RW Mounts | Aero Structural | Anisha
6061 |  | 1/4" | 3.5 x 13 | 2 | FW Internal Rib | Aero Structural | Anisha
6061 |  | 1/4" | 3.8 x 16.5 | 2 | RW Internal Rib | Aero Structural | Anisha
6061 |  | 1/8" | 27.5 x 19 | 1 | FW Internal End Ribs (1st, 2nd, 3rd, 4th Element) | Aero Structural | Anisha |  | I added all end rib sizes (left and right for all elements) together to make it easier. Therefore qty is 1.
6061 |  | 1/8" | 8 x 14.5 | 1 | RW Internal End Ribs (1st, 2nd, 3rd, 4th Element) | Aero Structural | Anisha |  | I added all end rib sizes (left and right for all elements) together to make it easier. Therefore qty is 1.
Material | Material (if other) | Thickness (in) | Dimensions (l x w, in) | Qty | Part Name/Description | Sub-System | Lead | Link | Notes
6061 |  | 0.125 | 18" x 20" | 1 | Container Floor | Accumulator Container | Justin, Janaarth
Mild Steel/Other | 5052-H32 | 0.09 | 21" x 20" | 1 | Container Lid | Accumulator Container | Justin, Janaarth

## Sheet Metal Stock
Material | Material (if other) | Thickness (in) | Thickness (mm) | Dimensions (l x w, in) | Notes | Subsystems that can use metal | Column 1
6061 |  | 0.032 | 0.8128 | 18 x 12 and 15 x 10 | can do two sheets from existing metal |  | CUT
6061 |  | 0.04 | 1.016 | 24 x 7 and 6.5 x17.5 | two sheets can be cut from exisiting sheet | Suspension | CUT
4130 |  | 0.06 | 1.524 | 13 x 23.5 |  |  | Already Cut
4130 |  | 0.06 | 1.524 | 39 x 21 | need to cut out small part of existing cuts | Steering (Only require 8" x 8") | CUT
4130 | not labeled | 0.05 | 1.27 |  |  |  | Already Cut
4130 | not labeled | 0.06 | 1.524 | 36 x 48 - 2 pieces |  | LV tabs | Already Cut
6061 |  | 0.125 | 3.175 | 4" x 9" - 2 pieces |  |  | Already Cut
6061 | not labeled maybe 6061 | 0.08 | 2.032 | 36 x 85 |  | Suspension
6061 | not labeled (should test) | 0.125 | 3.175 | 20 x 10 |  |  | CUT
4130 |  | 0.125 | 3.175 | 12 x 12 | needs rust cleaned | Suspension
| 5052 | 0.125 | 3.175 | 11 x 11.5 and 11 x 10 | two sheets can be cutout |  | CUT
4130 |  | 0.125 | 3.175 | 10.5 x 8 | need to cut out sheet for manufacturing | Suspension, Pedal Box
4130 |  | 0.125 | 3.175 | 36 x 29 | need to cut out existing cut material | Suspension, Pedal Box
6061 |  | 0.13 | 3.302 | 15 x 21.5 | need to cut out existing cut material | Aero Structural (RW Tabs) | CUT
4130 |  | 0.16 | 4.064 | 20 x 14 | cut out existing cutout area | Drivetrain, Brakes
4130 |  | 0.1875 | 4.7625 | 10 x 8.5 | must cut out excess
4130 |  | 0.19 | 4.826 | 6 x 12 |  | drivetrain
4130 |  | 0.25 | 6.35 | 18 x 14.5 | cut out existing cutout area | Suspension, Pedal Box
6061 |  | 0.25 | 6.35 | 15 x 7 and 3.5 x 12.5 | cut out 2 usable sheets | Accumulator Mounts
4130 |  | 0.25 | 6.35 | 10 x 15.5 and 6 x 9 | cut out 2 usable sheets | Suspension, Pedal Box
| maybe 6061 not labelled | 0.75 | 19.05 | 20 x 12

## Business Procurement
Part Information | [20 empty] | Approval |  |  | Procurement
Type | Subsystem | Item | Description (Size/Type) | Why you need it | Critical? | Quantity | Spares | Total Qty. | Unit Price (CAD) | Shipping Cost (CAD) | Estimated Duty Charge (Use this calculator) ($ CAD) | Total Cost (CAD) (Incl. Tax) | Vendor Name | Part No. | Link | Do we have this, or a similar item that could be designed for, in the shop? (If similar or same in shop/storage already, provide explanation) | Item added by (if new member, include lead/ apprentice working with as well): | Companies contacted to sponsor item or get discount (if none, provide reasoning) | Details on company sponsoring + discount code etc. | Comments | System Lead Approval: | Management Approval: | Final Approval? | Added to a Purchase Request by: | Purchase Request Spreadsheet Link: | Shipping and Receiving emailed with shop availability for dropoff OR pickup date/time? | Duties Paid Ahead of Time? (<$250 on peoples' cards, >$250 on PCard) | Duties invoice link: | Pickup or dropoff date? | Order Status
Example | aero structural | Steel | 16" x 14" plate 4130 steel | for mounting ribs | Critical | 1 |  | 1 | 100 | 0 | 0 | 100 | Metal Supermarket | N/A |  | Using 5 sq. inches of existing material, need to buy this amount extra. | Morgan, Nick | Metal Supermarkets (declined items and discount code), Company X (didn't respond after 2 weeks and a followup email). | None | Can pick it up from the Vaughan location | Santino, Victor, Maooz | Rochelle, Rhythm | Yes | Morgan | https://drive.google.com/drive/folders/1l6BRGBbI_woR5CXfgt1Ydn-UfLeRF23x?usp=share_link | Yes | N/A | N/A | Nov 26 1-5pm, shop dropoff, Morgan | Unpacked
Livery
Material | Livery | Vinyl Wrapping | Custom Custom Printed Wrap Graphics | For Livery, if PCL is unable to sponsor us | Maybe-Critical, depending on PCL | 1 |  | 1 | 1048 | 0 | 0 | 1184.24 | TBox Studio |  | https://tboxstudio.com/ | No | Andrew | PCL Graphics | Sponsored us in the past, to be renewed | Adding this in case PCL Declines renewal offer. Morgan used this company for TM-24, and they gave us a $250 discount | Andrew
Social Media/Marketing | [6 empty] | Social Media/Marketing | [6 empty] | Livery
IT | Social Media / Marketing | Squarespace Domain Subscription | Annual renewal occuring Oct 26 | Mandatory to keep website live | Critical | 1 | N/A | 1 | 138 | 0 | 0 | 155.94 | Square Space | N/A | https://torontometformularacing.squarespace.com/config/settings/domains-email/domains | No | Andrew | Squarespace has been our website provider for a decade. They provide a web design that is very user friendly, allowing members with little to no experience effectively update it. | N/A | This year's subscription was billed to Rhythm | Andrew
Marketing Assets | Social Media / Marketing | Matte Business Cards (standard) | 500 Units, Standard, Matte, Custom Design | To provide contact info to potential sponsors, students, etc. at exhibiting events | Critical | 500 |  | 500 | 0.06 | 0 | 0 | 29.38 | Vistaprint | N/A | https://www.vistaprint.ca/business-cards/standard | No | Andrew | at 0.06 per unit, this price is already minimal for the value we are getting. Shipping is also free. | N/A | To be placed with Apparel to get free shipping | Andrew | Maooz | Yes
Graphics / Apparel | [6 empty] | Social Media/Marketing | [6 empty] | Apparel
Apparel | Graphics / Apparel | Team Apparel | Custom Embroidered/Printed Jackets, T shirts, polos, Mechanic shirts, hats, and hoodies | So team members can represent TMFR at Competition, Unveiling, and other events. | Critical | 30 units per item |  | 30 units per item | N/A | 0 | 0 |  | Entripy |  | https://www.entripy.com/catalogsearch/result/?q=mechanic%20shirt | No | Andrew | None yet, Will reach out to Entripy and Wordans for sponsorship & discount |  | Rochelle placed all the orders last year, and personally provided me with this ask amount. With the amount of variables involved in ordering apparel (colours, logo placements, embroidery vs printing can change the price/unit drastically) it would be impossible to estimate prices per unit for each piece of apparel. Therefore, $5000 is a safe, yet reasonable estimate. For further reasoning, please contact me. | N/A
Events | [6 empty] | Events | [6 empty] | Events
Events | Events | Foam boards for Unveiling Decoration | 24x36in. Not sold per unit, sold as a 3 pack. | To show the scope of each subsystem at unveiling | Non-Critical | 1 |  | 1 | 150 | 0 | 0 | 172.89 | Staples |  | https://www.staples.com/services/printing/foam-boards/ | We Could use the ones from last year worst case scenario | Andrew | N/A | N/A |  | Andrew
Events | Events | 1/3 subs - assorted | Sandwhiches for unveiling | To feed sponsors, members, school faculty, and other attendees at unveiling | Critical | 130 |  | 130 | 5.5 | 0 | 0 | 646.36 | Good Behaviour Ice Cream |  | https://goodbehaviourto.ca/catering | No | Andrew | Good Behaviour has provided us with a 20% discount and free shipping in the past |  |  | Andrew
Events | Events | Forks (100 pc.) | Plastic, 6.7in | Forks for unveiling | Non-Critical | 1 |  | 1 | 13.99 | 0 | 0 | 15.8087 | Amazon |  | https://www.amazon.ca/Plastic-Reusable-Cutlery-Birthday-Barbecue/dp/B0CQY44ZG2/ref=sr_1_5?dib=eyJ2IjoiMSJ9.bVRmSQ1hUZb9Jjwm8Xd6zG8V_IPNoPEwTuZ3oXxiiZf_yoYPZGdA81QeC5iiLX8IFzUO8Vh4W0FTdfQTW_OfpyRCoj96o-KbZFWnZIjIz9NP0nG4937Uxjs9W8Doks4-gj7iTaCwwBn-JX2VTZouHgASzbfB2PFvAG7Uuk3w4nY2EHlS-seku5jfTPk0VzMWDFxEb7cAsZTkE8DFNsjKkDXeLq4XE_-ZmcElkfDpK_Bm9fbNzmGIJLFNjV2YP_R1WKv3BtaSeRN0OQ34iF9V1y5OKFlJjM7h_Q_EBQiozgU.fJh4dTLhAG4p7v76VfbkpKzF3roZq4ldjRHRbOzdH5Q&dib_tag=se&keywords=forks%2B100%2Bpack&qid=1752719637&s=hpc&sr=1-5&th=1 | No | Andrew | N/A | N/A |  | Andrew
Events | Events | Fruit Platter (one serves 20) | N/A | Fruit for unveiling | Critical | 4 |  | 4 | 44.99 | 0 | 0 | 203.35 | Metro |  | https://fresh2go.metro.ca/individual-trays/fruits-and-vegetables/celebration-fruit-platter.html | No | Andrew | N/A | N/A |  | Andrew
Events | Events | Water bottles (24 pack) | N/A | Water for unveiling | Non-Critical | 5 |  | 5 | 2.98 | 0 | 0 | 16.2155 | Walmart |  | https://www.walmart.ca/en/ip/Great-Value-24pk-Spring-Water/10295446?classType=REGULAR&athbdg=L3048&from=/search | No | Andrew | N/A | N/A |  | Andrew
2424.1842
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE
[21 empty] | FALSE | FALSE

## Shop suppliesequipment procurem
ans | [20 empty] | Approval |  |  | Procurement
Type | Subsystem | Item | Description (Size/Type/Brand Name) | Why you need it | Critical? | Quantity | Spares | Total Qty. | Unit Price (CAD) | Shipping Cost (CAD) | Estimated Duty Charge (Use this calculator) ($ CAD) | Total Cost (CAD) (Incl. Tax) | Vendor Name | Part No. | Link | Do we have this, or a similar item that could be designed for, in the shop? (If similar or same in shop/storage already, provide explanation) | Item added by (if new member, include lead/ apprentice working with as well): | Companies contacted to sponsor item or get discount (if none, provide reasoning) | Details on company sponsoring + discount code etc. | Comments | System Lead Approval: | System Lead Approval: | Final Approval? | Added to a Purchase Request by: | Purchase Request Spreadsheet Link: | Shipping and Receiving emailed with shop availability for dropoff OR pickup date/time? | Duties Paid Ahead of Time? (<$250 on peoples' cards, >$250 on PCard) | Duties invoice link: | Pickup or dropoff date? | Order Status
Example | aero structural | Steel | 16" x 14" plate 4130 steel | for mounting ribs | Critical | 1 |  | 1 | 100 | 0 | 0 | 100 | Metal Supermarket | N/A |  | Using 5 sq. inches of existing material, need to buy this amount extra. | Morgan, Nick | Metal Supermarkets (declined items and discount code), Company X (didn't respond after 2 weeks and a followup email). | None | Can pick it up from the Vaughan location | Santino, Victor, Maooz | Rochelle, Rhythm | Yes | Morgan | https://drive.google.com/drive/folders/1l6BRGBbI_woR5CXfgt1Ydn-UfLeRF23x?usp=share_link | Yes | N/A | N/A | Nov 26 1-5pm, shop dropoff, Morgan | Unpacked
Shop List

## Fastener Procurement
M1
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
M2
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
M3
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
M4
Fastener Type | Pitch (mm) | Length (mm) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
Socket Head Cap Screw | 0.7 | 25 | N/A | 8 (minimum) | 16 | Steering | Carbon tie rod insert fasteners | Luca | https://www.mcmaster.com/91290A176/
Nylon Locknut | 0.7 | N/A | N/A | 8 (mininum) | 16 | Steering | Carbon tie rod insert fasteners | Luca | https://www.mcmaster.com/94645A101/
Hex Head Screw | 0.7 | 8 | N/A | 8 | 18 | Frame Sub | Attach Firewall | Matteo | https://www.mcmaster.com/91287A111/ | Consolidated to line 33
Nylon Locknut | 0.7 | N/A | N/A | 8 | 18 | Frame Sub | Attach Firewall | Matteo | https://www.mcmaster.com/94645A101/ | Consolidated to line 34
M5
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
Hex Head Screw | 0.8 | 35mm |  | 8.8 Steel | 25 | Nose cone/ Bodywork | Needed for the magnet tabs | Biblina | https://www.mcmaster.com/products/hex-head-bolts/hex-head-screws-1~/medium-strength-metric-class-8-8-steel-hex-head-screws/length~35-mm/?s=m5+hex+head+bolts | Pending
M6
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
Hex Head Screw | 1 | 30 | 12 | 10.9 | 25 | Aero Structural (RW) | Mounting for rear wing | Maooz | https://www.mcmaster.com/95327A521/
Deformed Thread Nut | 1 | N/A | N/A | ISO Class 8 | 12 | Outboards | Clevis | Omar | https://www.mcmaster.com/93795A220/
Hex Head Screw | 1 | 18 |  | 8.8 Steel | 3 | Drivetrain | Chain guard | Rhys | https://www.mcmaster.com/catalog/131/3593/91280A328 | Consolidated with line 60
Hex Head Screw | 1 | 14 |  | 8.8 Steel | 3 | Drivetrain | Scatter shield | Rhys | https://www.mcmaster.com/catalog/131/3593/91280A063 | Consolidated with line 60
Nylon Locknut | 1 | 6 (height) |  | Class 10 | 8 | Drivetrain | Chain guard/scatter shield | Rhys | https://www.mcmaster.com/products/94645a205/
Flat Washer | N/A | N/A |  | 18-8 | 24 | Drivetrain | Chain guard/scatter shield/eccentric rings | Rhys | https://www.mcmaster.com/catalog/131/3692/93475A250
Hex Head Screw | 1 | 25 |  | 8.8 Steel | 3 | Drivetrain | Sensor-side eccentric | Rhys | https://www.mcmaster.com/catalog/131/3593/91280A334 | Consolidated with line 60
Hex Head Screw | 1 | 35 |  | 8.8 Steel | 3 | Drivetrain | Sprocket side eccentric | Rhys | https://www.mcmaster.com/catalog/131/3593/91280A340
Low Profile Hex Head Screw | 1 | 12 |  | 8.8 Steel | 2 | Drivetrain | Chain guard/Scatter shield | Rhys | https://www.mcmaster.com/93070A143 | Consolidated with line 60
Nylon Locknut | 1 | 6 (height) |  | Medium Strength S | 6 | Drivetrain | Sensor & Sprocket side eccentric | Rhys | https://www.mcmaster.com/products/90576a115/ | Consolidated with line 57
Nylon Locknut | 1 | 10 |  | 6H | 8 | Aero Structural (RW & FW) | Mounting for rear wing | Anisha | https://www.mcmaster.com/93625A250/ | Consolidated with line 57
Socket Head Cap Screw | 1 | 14 |  | ISO Class 12.9 | 24 | Drivetrain | Full set of differential housing screws | Rhys | https://www.mcmaster.com/91290A319
Nylon Patch Bolt | 1 | 20 | N/A | 18-8 | 40 | Undertray | Undertray mounting | Davis | https://www.mcmaster.com/93310A816/ | Purchasing this instead: https://www.mcmaster.com/96755A324
rivet nut | 1 | n/a |  | zinc plated steel | 10 | Undertray | undertray mounting | Davis | https://www.mcmaster.com/95105a183/
rivet nut | 1 |  |  | 6H Aluminum | 25 | Aero Structural (RW & FW) | RW & FW internal aluminum ribs to endplate fasteners | Anisha | https://www.mcmaster.com/94020A387/
M7
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
M8
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
Hex Head Screw | 1.25 | 50 | 28 | 10.9 | 25 | Acuumulator Container | Accumulator Mounts | Janaarth | https://www.mcmaster.com/95735A451/
Hex Head Screw | 1.25 | 30 | n/a | 10.9 | 25 | Accumulator Container | Accumulator Mounts | Janaarth | https://www.mcmaster.com/95735A431/
Hex Head Screw | 1.25 | 11 | 25 | B-O Alloy Steel | 3 | Drivetrain | Sensor-side Mount | Rhys | https://www.mcmaster.com/catalog/131/3542/90782A124
Flat Washer | n/a | n/a | n/a | Stress-Resistant Spring | 15 | Drivetrain | Sensor & sprocket-side Mount | Rhys | https://www.mcmaster.com/catalog/131/3724/92927A925
Nylon Locknut | 1.25 | n/a | n/a | Zinc high strength | 6 | Drivetrain | Sensor & sprocket-side Mounts | Rhys | https://www.mcmaster.com/products/94645a210/
Hex Head Screw | 1.25 | 11 | 30 | B-O Alloy Steel | 3 | Drivetrain | Sprocket-side Mount | Rhys | https://www.mcmaster.com/catalog/131/3542/90782A125
Socket Head Cap Screw | 1 | 8 | n/a | 10.9 | 3 | Drivetrain | Differential rebuild | Rhys |  | Requires link
M9
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
M10
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
M11
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
M12
Fastener Type | Pitch (mm) | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
1/4"
Fastener Type | TPI | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
Flat Washer | N/A | N/A | N/A | SAE 8 | 96 | Suspension | PR / BL / CA | Benjamin | https://www.mcmaster.com/98023A029/
Nylon Locknut | 28 | N/A | N/A | SAE 5 | 30 | Suspension | PR / CA | Benjamin | https://www.mcmaster.com/95615A130/
Hex Head Screw | 28 | 1.75" | Partially Threaded | SAE 5 | 36 | Suspension | PR / BL / CA / Clevis | Benjamin | https://www.mcmaster.com/91247A014/
Hex Head Screw | 28 | 1.5" | Partially Threaded | SAE 5 | 4 | Suspension | CA | Benjamin | https://www.mcmaster.com/91247a012/
Deformed Thread Nut | 28 | N/A | N/A | SAE 5 | 10 | Suspension | Clevis | Omar | https://www.mcmaster.com/90673A111/
Hex Head Screw | 20 | 1.125" | N/A | Grade 8 | 6 | Drivetrain | Sprocket carrier | Rhys | https://www.mcmaster.com/catalog/131/3581/92620A545
Nylon Locknut | 20 | N/A | N/A | Grade 8 | 6 | Drivetrain | Sprocket carrier | Rhys | https://www.mcmaster.com/products/97135a210/
Flat Washer | N/A | N/A | N/A | 18-8 | 6 | Drivetrain | Sprocket carrier | Rhys | https://www.mcmaster.com/products/97135a210/ | Incorrect link and washer height not listed
Socket Head Cap Screw | 24 | 0.375" | 3" | Alloy Steel | 1 | Pedal Box | Brake Bias Bar | James | https://www.mcmaster.com/91259A106/
button head bolt | 20 | 7/8" | 0 | alloy steel | 10 | Undertray | Mounting to frame | Davis | https://www.mcmaster.com/91355A179/ | Pending
Nylon Locknut | 20 | N/A | N/A | 18-8 | 10 | Undertray | Mounting to frame | Davis | https://www.mcmaster.com/94238A101/
1/2"
Fastener Type | TPI | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
Nylon Locknut | 13 | N/A | N/A | SAE 5 | 6 | Suspension | PR / Toe | Benjamin | https://www.mcmaster.com/94846A209/
#10 Screw
Fastener Type | TPI | Length (length) | Shoulder Length (If Applicable) | Grade/Material | QTY | Subsystem | Reason | Item Added By | Link
Socket Head Cap Screw | 32 | 2-1/2" |  | Zinc-Plated Alloy Steel | 25 | Pedal Box |  | James | https://www.mcmaster.com/90044A121
| 32 | 1-1/4" |  | Zinc-Plated Alloy Steel | 25 | Pedal Box |  | James | https://www.mcmaster.com/90128A948/
Flat Washer |  |  |  | 18-8 Stainless Steel | 100 | Pedal Box |  | James | https://www.mcmaster.com/92141A011/
Nylon Locknut | 32 |  |  | Zinc-Plated Steel | 100 | Pedal Box |  | James | https://www.mcmaster.com/90631A411/

## Water Jet
Water Jet Orders - Guide
System | System Lead | Part Name | Material Type | Material Dimension (L x W x T) | Quantity | Does Viking have material | Material in Shop | Material Ready? | DXF Ready | Drawing Ready | DXFS and Drawings Approved | Order Sent to Viking | Completed
Send Out 1
Accumulator | Emi | Busbars | C110 Copper | 19" x 15" x 0.125" | 1 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Aero Structural | Anisha | FW & RW Mounts | 6061 Aluminum |  | 4 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
LV Enclosures | Nathan | Rear Enclosure Tabs | 4130 steel | 0.787402 '' x 0.393701'' x 0.06'' (20 x 10 x 1.524 mm) | 4 | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[6 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Send Out 2

## 3D Printing
3D Printing
Item | Subsystem | Qty | Material | Designer | Structural/Non Structural? | Status | Printer | Date of Print | Due Date
Item | Subsystem | Qty | Material | Designer | Structural/Non Structural? | Status | Printer | Date of Print | Due Date
Item | Subsystem | Qty | Material | Designer | Structural/Non Structural? | Status | Printer | Date of Print | Due Date
Item | Subsystem | Qty | Material | Designer | Structural/Non Structural? | Status | Printer | Date of Print | Due Date

## Bolt Checks
System | Subsystem | Task | Responsible | Done by who? | Comments/Observation
Systen is clean. Air hose, wipe down.
All bolts marked off with blue plaint marker after check
VD | SU | Suspension Fasteners (check preload!)
VD | SU | tire wear measure, picture of surface?
VD | SU | suspension set up set and recorded
VD | SU | corner weights set
VD | SU | dampers inspected
VD | SU | ball bearing compliance inspected and documented
VD | BR | Brake fasteners tightened
VD | BR | Brake plumbing (no leaks or kinks in the line, lines ziptied)
VD | BR | Brake rotors cleaned
VD | BR | Brake pads checked and measured
VD | BR | Brake fluid filled
VD | BR | Bleed valve tightened
VD | BR | Calipers lockwired
VD | BR | Bias bar set and recorded
VD | BR | BOTS is out
VD | BR | Brake pedal is stiff
VD | WT | Hub bearings cleaned and greased (every 60km)
VD | WT | Hub nuts tighted and cotter pin put in
VD | WT | camber and toe set and documented
VD | WT | wheel compliance check
VD | WT | Lug nuts torqued (35Nm)
VD | ST | Steering fasteners tightened and lock wired
VD | ST | steering function (record play)
VD | ST | Inspect steering clevis
VD | FR | Inspect impact attenuator glue
VD | FR-Sub | Frame Sub items fasteners fastened
VD | FR-Sub | Firewalls fastened in
VD | FR-Sub | Firewalls sealed
VD | FR-Sub | Floor Fasteners
VD | FR-Sub | Headrest ziptied/fastened
CN |  | Systen is clean. Air hose, wipe down.
CN |  | All bolts marked off with blue plaint marker after check
CN | Ergo | Driver harness Fastners
CN | Ergo | Driver harness inspection
CN | Ergo | Seat inspection (front, back, cracks, delamination)
CN | Ergo | Throttle pedal actuates
CN | Ergo | Steering wheel bolts tight
CN | Ergo | Steering Wheel play checked
CN | Ergo | Quick connect inspected
CN | Ergo | Pedal box mounts/fasteners
CN | EL/CN | Check APPS sensor voltage with multimeter
CN | EL/CN | Check the dash connector
CN | EL/CN | Dash and screen dash fasteners
CN | EL/CN | dash buttons inspected
CN | EL/CN | Estop functioning
CN | EL/CN | Check brake pressure sensor with multimeter (1.5-4.5V)
CN | EL/CN | Check BOTS is functioning
EV |  | Systen is clean. Air hose, wipe down.
EV |  | All bolts marked off with blue plaint marker after check
EV | AC | Accumulator bolts Tightened
EV | AC | Maintence plugs and HV lines connected
EV | AC | Battery securing system fastened
EV | AC | Place Polycarbonate top insulated
EV | AC | Connectors are pluged in
EV | AC | Lid fasteners are tightened
EV | AC | External connectors are connected
EV | AC Hand Cart | Bolts are tightened
EV | AC Hand Cart | Charger is connected
EV | AC Hand Cart | Estop is functioning
EV | AC Hand Cart | Cable is not tangled and brakes are functioning
EV | EL Safety | All fasteners are tightened
EV | EL Safety | TSMP and GLMP are functioning
EV | EL Safety | Hoop estops ares functioning
EV | EL Safety | Ready to drive sound is functioning
EV | EL Safety | TSAL lights produce the correct colours
EV | EL Safety | IMD light is functioning
EV | EL Safety | AMS light is functioning
EV | EL Safety | Inertia switch is funcitoning
EV | EL Safety | Dash estop is functioning
EV | EL Safety | HVD is functioning
EV | EL Safety | Voltage indicator is functioning
EV | GLV | Electrical connectors are connect and not corroded
EV | GLV | Open wires/connectors taped off
EV | GLV | Wires fastened down and not dangeling near rotating parts
EV | GLV | Fuses in and not blown
EV | GLV | Ring terminals nut fully tightened
EV | GLV | Shorai batteries are charged and fully fastened
EV | GLV | Brake light turns on when brakes are pressed
EV | GLV | Fan works
EV | GLV | Charge team computer
EV | Motor | Motor fasteners are tight
EV | Motor | Motor bolts lockwired
EV | Motor | HV lines have thread deforming nut
EV | Cooling | cooling fasteners tighted and no leaks
EV | Cooling | Cooling plumbing (lines not frayed, no leaks, hose clamps tightened)
EV | Cooling | Cooling bungs/pin hole leaks plugged
EV | Cooling | Shroud gap taped
EV | Cooling | coolant filled and bled
EV | Drivetrain | Drivetrain fasteners
EV | Drivetrain | Chain tensioned
EV | Drivetrain | Chain cleaned
EV | Drivetrain | Chain Lubed
EV | Drivetrain | Half Shafts can plung
EV | Drivetrain | Tripod bearings greased
EV | Drivetrain | Boots secured

## Lessons Learned 2021-23
Category | Who | Lesson | Notes
Design | Erica | Leads spend a lot of time trying to figure out what they should know for their subsystem and finding good resources. We should standardize the initial subsystem learning with a list of must read sources or a list of topics they must know for their system. That way everyone has the same base of knowledge and they can build upon that.
Design | Erica | It seems that even though we have a month for design, due to how overwhelming it is to start a new system it still isn't enough time to do adequate research so you have the knowledge to design your system. We can maybe fix this by doing more standardized learning in first year. Basically give everyone the basic subsystem topics to learn in their first year so no matter what system they are in the following year they already have basic knowledge of the system and can build from there
Design | Erica | New systems need help/guidance to start research. Having a meeting with them and discussing a research/analysis plan is helpful
Design | Erica | Comunication is key! Include that as a major team goal and enforce it on the system and subsystem levels
Project Management | Erica | Interactive meetings where you ask others their opinions/thoughts are more effective then a long meeting of one person talking
Project Management | Erica | Recording team/system meetings and posting them on drive is benefitial for people who can't attend the meeting
Project Management | Erica | Having guides that are easy to follow and include all the info needed for a task it much easier to follow then giving people vague info. Its worth it to spend the extra time to prepare a good quality document
Project Management | Erica | Feedback from LTP: People learned best from linkedin learning courses, then lectures. I also thing hands on workshops would be useful too. Self learning from a document is difficult
Recuitment | Erica | See Lesson 2 above. We can input a 2-3 phase new member learning plan where they first learn basics of the car/each system, then they learn the theories/info for each subsystem needed for design, then they learn more hands on workshops to improve their skills in the shop. Come design they will know the info needed to design their system (the basics) and have the skills to manufacture them. Then in the design phases they would do more high level research and analysis. Develop their knowledge further. We could also include a big project at the end so they can build something
Manufacturing | Erica | Talk to the company who makes the parts (ex:caliper) before you rebuild them!
Design | Erica | For setting up design reviews either get each subsystem to talk to each other and pick a few times that work for everyone or have everyone sign up using a calendar or something like that so the eng lead doesn't have to waste time figuring out when everyone is available.
Design | Erica | So new leads who are familiar with Salustri's design process and not our may want to integrate his process into our design phase. This is possible but requires more time. Maybe address other design processes/ salustri's design process at the beginning of design and explain why we do it the way we do.
Business Presentation | Erica | include alum early (especially mal) to get their take on the business case. We want the most obvious interpretation of the case so we dont confuse judges. Also get Mal's help with the finances early
Business Presentation | Erica | Do a mock presentation infront of the alumni and have them as you questions (acting as judges and just general inquiries) and make sure to do this well in advance of the actual comp so you have time to make changes
Business Presentation | Erica | We have the presentation, organization and content down as well as the quality of the slide show. In order to get first we must nail the interpretation of the business scenario (pick the most obvious one, get help from industry professionals) and we must be able to answer the judges questions (do the mock presentation with alum and prep answers). If we do this we will get first
Business Presentation | Erica | There needs to be a script and presentation freeze. You cant keep editing and changing things until the last minute otherwise the presenters wont be able to memorize it
Business Presentation | Erica | Practise makes perfect. Work on transitions. Make the presentation exciting, engaged and have a wow factor. Make sure to practise with your partner other wise you wont have chemistry or have a good flow
Business Presentation | Erica | Make sure the presenters are included in the design process of the presentation. Otherwise they wont know the information and wont be able to answer the judges questions
Business Presentation | Erica | The appendix is used as a last resort. If you know the answer to a judge's question dont waste time flipping through the appendix. It is good to have just in case but more of the time the text is too small to read and if you don;t know the order of sllides its not worth it
Business Presentation | Erica | You must wear professional business attire (suits) the judges look for that. Make sure to be clean with your hair neat.
Business Presentation | Erica | Handouts do help and are good for when judges are judging and don't remember what you said in your presentation. Make sure they include only the most important information
Cost | Alum | Don't lie about the weight for any component that is easily removable on the car (ex the seat). They wont make you undo any bolts but they will remove easy parts. Also make sure the car presented at competition is the same as in cost report. Everything the judges can see should be costed (ex: the honeycomb and screen that we put over the rad in RF-19)
Design | Erica | When scheduling design reviews it is easier to have each person fill out all their availability. When a group fills out their availability there is a lot less availability listed and they seem to only input their perfered times. veryy difficult to schedule with alum. Or get each subsystem to schedule their own design review with the alum but then the eng lead may not be able to attend (because they may overlap)
Finances | Erica | Alwasy settle last years finances and cheq reqs before purchasing for the next year. Its confusing otherwise
Design | Erica | Discuss Grab cad folder trea with system and upper leads before CAD starts to make sure it works for every system
Design | Erica | leads need to be familiar with AND FULLY UNDERSTAND their rules. things will get missed if this doesn't happen
Design | Erica | targets, guidance and overall vision must come from the upper/system leads. It is there job to make all the subsystem members cohesive and on the same page. cannot leave subsystem members to make decisions that effect the whole team
Design | Erica | COMMUNICATION! leads cant wait until othr people get updates. they must take initiative and reach out to people. Integration is difficult and a 2 way street
Sponsorship Week | Devon | Communication and preperation is key. Getting the sponsorship blurbs/photos done as early as possible would help with clarity and confirming everything is right. One person posting everything across four platforms is a lot - we should either have a larger posting team or invest in a program like Hootsuit. The contests went smoothly. There needs to be more communication upfront so that nothing is missed and the group is clear on the expectations and end goals.
Virtual Unveiling | Devon | Gathering content for the web page takes longer than expected, leads should ask for and give this infomration promptly. Always start gathering content as early as possible and clearly assign it to the approproate lead/team member.
CAD | Jibran | Consider naming part/assembly files differently each year from their respective files from the previous year. Ie: RF20 and RF21 had the drivetrain file as "DR-Drivetrain", this prevented both from being opened at the same time. Having the previous year system open while working on the one for this year can help in the CAD process.
Design | Erica | BOM and proceurment are basically the same thing. makes more sense to only do procurement after manufacturing plan is done
Orientation | Rob | Have something prepared to invoke questions - presentation or visual, component spread/schematic. - something to bring questions to new members
Orientation | Jibran | Enhancing the orientation structure (ie: assign leads to tasks such as having them present their system)
Orientation | Jibran | Leads meet up prior to orientation to discuss presentation plan and schedule
Orientation | Rob | Have some next steps planned for new members (doesn't have to be tasks but even some learning or reading)
Orientation | Simeon | Do not do it on Webex (makes noise when someone joins, breakout sessions do not work well because you need to assign people, has 50 minutes time limit). More communication needed with leads before the event to let them know how it will work. Discord seems to work well, but it might not work for the presentation. RFR has access to a paid zoom account which can be used instead of Webex. Missing information and mistakes on slides (needs to be more communication to ensure that the slides are complete). Should practice the presentation.
Orientation | Jibran | Have activities for the new members to do such as a name that part game like we did before (we can do it to an extent with the car CAD)
Orientation | Erica | infomation about the team should be verified for presentation. have the leads prepare something to show during the oritentation New memebers need some more information about ready to race program (start date, how it will work). also ALWAYS include business presentation video. gets them excited
Orientation | Erica | for future: i think we could still have in person orientations but maybe have a system info night where we are all on something like discord and we do a more indepth system presentation to get people interested in the system and talking.
Orientation | Erica | PRACTISE WITH SOFTWARE
Orientation | Erica | if online, they need to be exciting. show video, start with music. get everyone pumped. and make sure the videos music work
Testing | Erica | keep good notes during testing. document everything! make sure to write down track length (km) and how many runs we did on the track so we can have a reference of how many kilometers were done in a day.
Testing | Erica | need better way to pack testing tools. things are getting broken and thrown. also need better tools. labeling system?
Testing | Erica | very useful to have alumni drivers there to provide new drivers with advice. Easier than learning on your own.
Testing | Erica | get as many rainy testing days as possible. worse condition the car with perform in and great for new drivers to practise in
Testing | Luigi | Take tire temps on wet tires too
Testing | Luigi | Locked up front tires quite a bit on wet track (braking before turn entry), especially in earlier laps when tire temps were still low. Should've adjusted brake bias towards the rear. Also to have a better baseline of the bias bar's sensitivity to # of turns.
Newsletter | Simeon | Don't send the newsletter out during holidays because people are out of office and they don't recieve it.
Electric Powertrain |  | Entire car is built around the accumulator. Put a lot of time and resources into the accumulator. A lot of systems depend on it.
Electric Powertrain |  | Harder to make an electric car into a combustion car then to do a design from scratch
Electric Powertrain |  | Contianer and batteries take priorety. AMS, AIR could have come after you know container size and batteries choosen and can leave extra space in accumulator. Can pick AMS and AIR at any time. Number of cells and geometry is most improtant.
Electric Powertrain |  | all electric powertrain cannot go into cad unless accumulator is in.
Electric Powertrain |  | Need constant rule checks for EV
Electric Powertrain |  | Packaging is a problem for the accumnuator when figuring out how many cells to use.
Design/ Electric Powertrain |  | under Design phase 2, add a heading for each part in your system and under that, include the relevant rules pertaining to that part. Or as a team go through all the rules and section them based on part/subsystem so you are all in agreement in what rules are relevant in each part
Procurement | Fazle | Many components were bought from outside canada. This means costs like duty and customs brokerage fees are sometimes neglected in the budget. Ultimately, considering all the international purchases, this proves to be a major cost for the team. Solution would be to increase effort in finding local vendors.
Build | Luigi | Very important to complete a detailed weight tracking sheet during the manufacturing/ assembly phase. This is useful to have as reference for estimating the weight of future cars, and examine areas where weight is gain/ loss. Going to be SUPER important for first electric car
Electric Powertrain | Jesvin | always update grabcad as soon as you finish, or lock some of the components at least
Design | Nick | extend research phase of design if you have to. Dont try to skip through it. You dont know what you dont know. Research phase is super important.
Build/Testing | Kyle | buy 2 throttle cables not 1
Build/Testing | Nick | ALWAYS HAVE SPARES
Testing | Erica | Do complete bolt checks before starting the car if it hasnt been started in a while.
Testing | Jibrans | Start car once every two weeks so there are not problems with the system
Cross system knowledge especially for system leads in incredibly important. You cant just know only your system.
Electric powertrain weight estimation was significatly off from actual weight of electric powertrain. This messed up aero and VD and they then have to re-calculate. Going forward, design shouldnt be based on the old combustion cars.
EV system components are heavy!
Keep open communication across systems. Easy to ask and adjust then ask later and redo.
Dont wait on people to respond. if they are not responding send follow up messages. If still no response go to upper management
Message people for periodic updates before the deadline when you want a task to get done.
Always assign deadlines to tasks.
When contacting a sponsor, make sure you are 100% ready to move forward incase sponsor has the product and can quickly deliver. If you are not ready for the product you are wasting both your and the sponsors time
Frame is dependent on all other systems, mainly electric powertrain since it is the one with major changes.
Mounting design also includes design of brackets, jiggs, and tabs
Electric safety training in essential to making sure the team is safe. Its not enough to "go through" the training. the training needs to be practised everyday in the shop
make sure to convert price or quote from a supplier to canadian dollars
always factor in shipping and duties into price estimation
Keep track of parts using some sort of inventory so you know what you have and where it is. Wasting money if you are buying components you cant find
Keep a spec sheet on all the detailed design specs for each system so you can easily recall specs like wire gauges and ratings, bolts, FOS, material grades
YOU CAN NEVER HAVE ENOUGH DOCUMENTATION. write everything down. Documentation can save time, save money, solve problems. Literally the life line for the team. Reasoning, why did you make that decision
Organize documents so we have the information and know where it is. Should be super simple so everyone can find what they are looking for
Build | Luigi | Keep track of extra fasteners. We usually order more than what we need from McMasterCarr and end up ordering another box of the same fastener next year
Design | Luigi | With the concern for reliability and having the thought of keeping something "similar", redesigning something from scratch isn't necessarily a bad thing. You could learn EVERY aspect of your part/ system if you designed it from scratch. Also, you would discover important details you didn't know exists/ matters.
Build | Luigi | McMaster Carr is a convenient source for finding materials that need to meet a specific rating (ie. UL94V0). Sometimes good to select a material by looking at the options from McMaster Carr first because you already know it's available whereas if you search for a specific material (from your research) first, you might eventually have a hard time finding a supplier for it.
Leadership | Nick | Worry about tasks that you are responsible for first - otherwise, trust those who've you've delgated to
Drivetrain | Jibran | Should have given more time to explore different sprocket carrier geometries
Could have been beneficial to explore more attachment methods for the halfshafts asides from tripod bearings and cups
More detailed documentation
Design/ CAD | Erica | tripple check that all front, right, and ground plans are mated properly in all master assemblies
Design/ CAD | Erica | show team the heirachy of design and why we do it this way. it may help so people know how it all works together
Design/ CAD | Erica | have multiple grabcad and cad workshop showing different skills. right now we are having problems with mating and integrating between assemblies
Design/ CAD | Erica | need to change cad practises so we can edit our designs in the future. right now we have to do a lot of work to adjust a few dimensions (planning out cad better)
Design/ CAD | Luigi | Put all the fasteners in a named folder under your assembly tree. If you have a bigger system, divide the fastener folders into different sections (ie. FR linakge fasteners, RR linkage fasteners...). Makes the assembly trees less crowded.
Design/ CAD | Luigi | Be mindful to convert entities the correct sketch for suspension. If you want to convert entites the dynamic sketch, make sure to hide the static sketch first. Otherwise, they are on top of each other and you might convert entities a mix of the static and dynamic which means you'll face errors/ suspension not even update when the dynamic sketch is changed because it's restricted by the static sketch reference.
Design/ CAD | Luigi | Naming your sketches, planes, and features (extrude cuts/ boss...) is really useful and good practice regardless of how complex your part is.
Design/ CAD | Luigi | For the suspension assemby's master sketch, I think its better to make it referenced to the static sketch instead of the dynamic sketch. The only purpose of referencing it to the dynamic sketch is to check clearance of steering and wheel travel but you can also just make a separate "clearance check assembly" which is a copy of the frame master sketch file -> mate your parts to the dynamic sketch. This way, you will be able to simulate your clearance checks in one assembly without having to jump from the frame master sketch and opening/ rebuilding different assemblies until you see the update in the suspension assembly.
Sponsorship | Sophia | When contacting a sponsor, try to find a direct contact in the company to email or call (or use Linkedin). You are more likely to get a response this way rather than emailing the general company's email form.
Sponsorship | Sophia | A good approach for a first email is to propose a sponsorship collab that you will explain over a quick call because it intrigues the contact to make a call to find out more about what you are proposing to them. Better to explain what we are asking for over call since company is more willing to listen.
Frame | Erica | frame is dependent on all other systems, spectifically the ones changing. If frame is bottlenecked by other systems for final geometry, work on perfecting fea and torsional rigidiy investigation
frame/design | Erica | cad and make sketchings with adjustments in mind. You should be able to go back and adjust some dimensions and have the entire cad update accordingly. otherwise you spend weeks trying to fix a bunch of conflicts. good cad practises are essential! | have more cad practises and tutorials. on cad etiquette
Design | Nick | Don't let perfect get in the way of done - you cant have a perfect justification for every design component/decision
livery | Morgan | start livery planning as soon as aero is being finalized. come us with plans for deliverables and deadlines
livery | erica | have some one working with the cad to get it to a presentable and workable state so in renders we are not missing crucial parts and it looks like a complete car. making the cad functional for rendering (light weight for vizualize)
Bodywork | Morgan | Make sure Dacron is sealed before beginning testing. Don't test with parts of aircraft fabric exposed to elements without at least one layer of sealant.
Manufacturing | Jibran | Should you have to use a used fastener, make sure it's clean (re-tap the thread, sand the head) for the sake of making the car more presentable
design | Erica | have constant rules reviews where you just look over rules to make sure every section is convered (specifically electric powertrain)
| Erica | NEED TO DOCUMENT WHEN THIS ARE PUCHASED AND PUT ON THE CAR. if you are buying parts that are aftermarket and are going driectly on the car, document when you purchased the item so if you re-use it on a future car you know how old it is
| Fazle | dont be afraid to deligate to new members, you will be able to focus more on the super important tasks and you will be teaching the next generation
| Erica | solve the conflicts in your system/subsystems cad. just because you finish cad, doesnt mean you dont have to check up on it and maintain it
Design | Luigi | One way to know what you don't know is to design from scratch so you discover all the important details during the process.
| josh | could have cut 3d printing prototyping and testing time in half if we had more iterations of the part earlier and investigate more options earlier. you will decrease the frequency of tests of you explore more options earlier
| erica | make sure to sit down and analize testing and prototyping results for all testings. this will help you iterate less if you really reflect on the test results and use it to predict the results of future tests.
| fazle | during research phase, good to look into certifications and requirements that relate to your subsystem to make sure you meet them. ex: being aware of ul certification for 3d prints
design/research |  | read into all of the documentation that is available for every major part for your system. even if you think its not going to be relevant to you. read manuals of products too! these companies understand their products and its their job to make good documentation
good to know how to design each component of your system even if you are procuring/purchasing it.
do the analysis even on parts you buy. you cant assume they will work
assume, come manufacturing, the team will be working together on manufacturing so make sure you understand how to manufacture other parts of people's systems (specifically true for wiring or electrical manufacturing since were limited in this area with personel)
Steering | Josh T | for steering wheel: decide on if you are going to implement buttons at the beginning of design process. have difficulty with integration of the buttons. find button, test with cover design, and verify if that is the correct button to use.
design | dani | make sure to read through entire research binder before starting. better for scheduling your time appripriately and making sure you dont miss anythign
design | david | research binder/amount of information was intimidating at first but after taking to lead it was much easier to understand
design |  | research binder with guiding questions are useful for guidance. better to have them research so they learn on their own and they find more information, futher their research on their own. not great to spoon feed. also helpful for finding your own resources
| rochelle | go to each subsystem meeting as a new members and try to learn as much as you can!
| sophia | for apprentices: schedule specific amount of time weekly to do readings and learn new material (from resource chart or your own resources) so you dont fall behind and are constantly learning about the system
| Edward | Try to absorb as much knowledge as you can from the leads since you will eventually be running the system
3D printing is not viable for contious stamping but it a great prototyping mechanism.
Design | Erica | Have a range of people in design reviews from other systems who are knowledgeable about the subjects. helps catch more things (shouldnt just have the system leads present, probably a team of min 3 reviewers from outside the system)
Design | Erica | SES for accumulator needs to be look at earlier in design and filled out as we go
Design | Luigi | When choosing the material for your part, confirm that the machining sponsor is able/ can conveniently machine that material. It can drive their cost up for tooling (ie. Grade 5 Titanium).
CAD | Luigi | Having fasteners inside a folder in the assembly tree makes it so much cleaner. Should be standardized team-wide for future CAD assemblies.
Design/ Competition | Erica/Nick | Electrical tech inspection is difficult and requires us to pass a much of tests to prove we meet the rules. its not enough to just meet the rules. you must review the technical inspection process and documents and ensure we meet those too
Design | Erica | Alumni are very willing to help and will even learn more about the electric competition to help us prepare. Use them for moch design and tech inspection. also just when ur stuck
Competition | Erica | Never assume something will pass tech because it did last year
Competition | Erica | know the rules very well. this is your only defence against technical inspectors
Design | Erica | remember your goals and constantly reflect on them. its easy to just "design a race car" rather than "design a race car to meet a specific goal. example if your goal is to pass tech, nothing else matters except that. and the whole team should be working towards that. if one system is done meeting rules and will pass tech but another wont, we need to extra people to help the other system
Sponsorship | Erica | Getting a discount is still a sponsorship. Many companies have educational programs that offer discounts. A discount is better than no sponsorship especially if you have the budget to afford it
Sponsorship | Erica | its good to show a company how much you have budgets for a specific expense/product and why you need a discount to achieve that. That way they know their company will make money and they can see you dont want to just hassel them and get free stuff. You have a budget, but the stuff you need is outside so you need a discount (ex: wiha tools. had $6000 for tools and need $12,000 worth of tools. therefore asked for a 50% discount)
Sponsorship | Erica | the more realistic and upfront you are, the more likely the sponsorship will go through. you dont just want to ask a company for sponsorship. you want to ask for a specific amount or product. that way they know what they are spending, why we need it, and where the money/product will go to. ex: asking for a multimeter sponsorship vs. asking for 3 specific multimeters
Sponsorship | Erica | If you cant get through to a company becuase you dont have a specific email of a person, try sending a more general email based around education and ask to be forwarded to the marketing department. or keep trying different general emails
Sponsorship | Erica | If a company doesnt have an available email address, try calling them. This works best if you are asking for an educational discount. A lot of companies have educational programs and calling guarantees you can talk to someone and get the correct email
Design | Nick | The ESF should be used from day one to help design components and circuitry for the electric powertrain system. It automatically does many calculations for you and instantly tells you if your designs are rule compliant
Competition | Nick | Google sheets does not have the same functionality as excel, and so when filling out the sheet, opening it in excel is the best way to fill it out/check that it is filled out correctly
Design | Fazle | Trying to fill out the ESF from the getgo, making design decisions informs a lot of potential rules issues that may not be clear in the rules. so should be consulted pretty early on. Many changes to design WILL come up when filling in the ESF
Design | Edward | Make sure you are certain on the design requirements/constraints before hopping in and making a design. Will save alot of time not having to redesign components.
Design | Edward | For electric powertrain walkthrough how power/signals will flow in practice with real components and how they will be connected). Was able to catch missed components since they were assumed to be there or they wern't thought of. (Caught missed connectors, adapters, additional circuitry that needed to be added)
Design | Matthew | It's good to document steps taken as a guide for the next lead, if a guide doesn't already exist
Chassis | Erica | Frame tubes, frame jigs, and suspension need to be sent out on september 1st to ensure the car is completed for comp
Competion | Rami | When signing up for competition, make sure to open webpage exactly 2 hours before, keep the tab open, and do NOT click multiple times, only click once.
GLV | Nick | Start working on your wiring diagrams early and make sure they are easily updatable/adjustable and continue to update them and set check in times to make sure wire diagrams you make are alwasy updated cause when you set those deadlines it forces you to think about how everything is connect. We use rapid harness to draw the wiring diagrams.
GLV - Rapid Harness | Nick | Tutorials are helpful for rapid harness but googling questions is also easy. Good to jump into it and use it for your application rather than trying to learn teh software first
Sponsorship | Morgan | Obtaining sponsors early and looking for sponsors for projects and new things early
Electric Powertrain | Nick/Erica | Inependent research will only take you so far. connecting with people in industry will teach you much more much quicker. specifically to electric powertrain and can help point you in right direction faster
Electric Powertrain | Nick/Erica | Electric powertrain is not like combustion. we need a lot of resources from industry. we need industry professionals to guide us. and we need their resources (we need HV labs to test components). dont try to use combustion stuff cause were familiar with it.
Electric Powertrain | Nick/Erica | Make connections early with industry professionals, lay out the expectations and requirements, have a person dedicatied to maintianing that relationship. dont just get them to check off a box
Electric Powertrain | Nick/Erica | It is incredibly difficult to pass electric powertrian tech and forms. the tech intespction forms, ESF, and FMEA should be open and included in design. THESE DOCUMENTS NEED TO BE DONE EARLY AND DURING DESGIN
Manufacturing | Santino | Always double and triple check measurements before ordering materials and designing parts ^^do it yourself, don't rely on another person
Design | Fazle | Work more collaboratively, with each other and with industry professionals. More design reviews and design conversations help advance designs and catch mistakes
Design | Rami | Work sessions are a great way to get a lot of work done in a reasonable amount of time, allowing for good collaboration.
Electric Powertrain | Erica | Most teams use unprotected cells and then design their own fusible links. this requires additional design and testing for the ESF so recognize and design for this early
General | Jibran | If you have multiple leads or multiple people working on or running the system, you need to have seperate meetings and be up to date on what everyone is doing. you cannot assume someone someone else in your system has done the work. and you should be able to give the team captain or PM an update on the whole system, not just your part.
General | Rami | If you are an apprentice or new member or not a lead, ask as many questions as possible. Dont be shy, NO STUPID QUESTION. one day you will be supporting and leading the team. try to know as much as you can
General | Matthew | Also I believe slack can be used a lot more effectively to communicate, like using channels instead of groups or DMs. At least for VD we hardly write anything in slack channels
Testing | Morgan | On testing days, get your hands dirty/help do as many things as possible. One day you'll be the one who has to do it! And the more practice you have the better.
General | Rami | If it's a task or workflow that needs to be done often, make sure you minimize the work or effort needed to actually get it done, humans naturally take the path of least resistance and won't do something if it takes too much "brain power".
Design | Rob | Utilize other teams research and lessons learned. Seems like a no-brainer but Kasey and I could have saved ourselves hours of research that we later found summarized nicely in capstones and online threads from other teams. As far as we currently know (cross our fingers), we dodged some compatibility issues between certain motor and motor controller models that we were looking at. Note: The compatibility issues were not always clearly listed on the manufacturers websites. Heard about them from other teams' unfortunate lessons learned.
Manufacturing | Santino | When doing a task, ask different people for their opinion on how the task could be executed. It could save a lot of work or prevent a major error. Also, don't be afraid to share your opinion on how you think a task should be completed, even if you are less experienced
Design | Nick | Regardless of whether there is a plan, don't start doing the tasks or following deadlines without fully understanding it yourself and outlining your goals and what you are looking for and investigating.
Project Management | Erica | Every task NEEDS deadlines. there needs to be an overall plan that the team is working towards. even if you are not fully sure on the outcome or where its going. when you sit down with the upper management, you can definatly create at least a short term plan with deadlines
General | Nick | Formula is an excersize in project management.
Design | Rami | Make sure to measure carrying capacity/dimensions before purchasing or moving anything
Chassis | Erica | Send out process is not difficult, it is just tedious so leave yourself 1-2 weeks to get everything ready for send out and then make changes to trims after they review it. also initiall you send them the BOM and CAD file. then after you send individual tube files
Controls | Kyle | For controls/pedal box, it is easy to think of it in the hardware aspect but its easy to miss the electrical or software aspect. its easy to assembly it but if the software side doesnt work then you need to spend more time with that. the software is just as important as the hardware.
Accumulator | Fazle | In industry, there is no clear theoretical way on how to design a fusable link, it is more experimental. so we need time to experiment. in industry, they experiment based on initial calcs, then they experiment and find the current temperature curve and then use that data to figure out which size to use.
Main fuse rule
Electric Powertrain | Fazle | Consult rules questions we asked for RF-21 in design
Accumulator | Erica | Accumulator also needs a top layer of insulation as well as the side walls
Design | Fazle | Use 3D printing to prototype and test things, fitment, extra. it can be used to simulate assembly and check fastener sizes
Accumulator | Fazle | For accumulator mounts, we used 3D printing to print the mounts and bolts and set the correct spacing, then we tested to see if we could fit the bolts in based on the spacing. this saved us the time and headache of realizing the bolts didnt fit after we manufactured the container
Drivetrain | Jibran | when designing sprockets, you should be in contant discussion with the frame lead to check chain interference so we dont have to make changes late in design
Frame | Erica | Need a new frame design. cant just use a combustion frame and extend it to fit electric powertrain cause it has different parts and different protection requirements. we can also seriously imporve on packaging from RF-21
Brakes | Daniel | When disassembling brakes, if rotors are removed, put dummy rotors or spacers to keep the calliper pistons from pushing the pads together when the brake pedal is pressed. It can be hard to push back the piston and insert the rotor back.
Design | Erica | Decide on scope early in design and stick to it. Look at it from a big picture. Consider resources and manufacturing availability. for RF-21 we had no one who would manufacture the titanium hubs so late in design we have to switch to using RF-20s hubs.
Design | Jibran | FEA is not as clear cut as you think, even if you think you understand the load case. all fea set up should be reviewed by an upper lead or alumni to make sure it is set up properly and represents the physical load case
General | Farris | Always remind system leads about updates on the system and any tasks we would help at hand. That way, we could learn more and be better about the system.
Design | Muhammad | A bit of a broad lesson. But if you are really unsure about whether a certain component meets rules, you could try asking the judges on FSAEonline and they should be able to clarify.
Design | Erica | Use other FSAE teams as resources. get their opinion and interpretation on a rule or problem. a lot of them are will to help out in design and solving problems. set a meeting with them if you haeve anough to discuss and present
Business - Recruitment | Simeon | Make sure there is a lead available from each system at each new member orientation date.
General | Kyle | Very important to meet people in person and work together cause it builds to team and trust
Team | Jibran | Important to have semi regular team building
Controls | Dadmehr | To simulate what drive might feel with the steer wheel, whenever you test the feeling of the steering wheel, you can wear gloves to better understand what the driver will feel
Design | Dadmehr | When using a 3D printer, you have to think of the pattern and way the 3D printer prints for strength
Electric Powertrain | Edward | Don't just think about your tasks you are working on it's own, think of it in the context of the entire car and how it interacts with other systems. (I.e when having to move voltage indicator to fit in frame, reconfigure APPS sensor because hardware wasn't quite setup properly)
Design | Erica | YOUR COMPONENT NEEDS TO BE MOUNTED ONTO THE CAR. you are responsible for the mounting component. talk to the frame lead if you need help
Accumulator | Nick | packaging with the accumulator and cells is a major problem for frame
Accumulator | Erica | Need a better process for selecting batteries based on endurance requirements and how that relates to power and performance. Battery selection and size completely changes the frame. a big accumulator doesnt mean a good accumulator
Controls | Kyle | The ergo sketch doesnt give you a gauge on how wide the frame it. MAKE SURE THE DRIVE FITS
Design/ Electric Powertrain | Nick | Research is not always going to find the best design. you need to experiment, understand, and test to figure out if the design works. meaning testing and experiments need to be incorporated IN DESIGN
General/Design | Kyle | bring apprentices/new members to integration meetings to listen and understand even if they arnt incharge of the task
General | Daniel | Record your meetings especially if what you are saying is not getting written down so you can go back to your thoughts/procedure. E.g. FEA meetings, discussions, reviews, etc.
Manufacturing | Kyle | By extra long bolts and cut in post if necessary
Manufacturing | Morgan | Don't lockwire stuff until you are completely done working on it
Manufacturing | Jibran | when you are making a part that requires rivets, use temporary rivets until the part is final, then replace the temporary rivets with permanent rivets when you are sure
Design | Luigi | Design for "clean"/ rounded/ standard dimensions if possible. Makes it very convenient in manufacturing.
Design | Erica | Rules are not alwasy muchually exclusive meaning susbsystem leads have rules that pertain to their subsystem in other sections. need to address this so no rules are missed
Design | Erica | It is important all leads understand the basic terminology of the frame (primary structure,etc) so they know what rules pertain to them. otherwise rules are missed
Design | Erica | ESF and SES need to be incorporated into design as part of a rule check and as additional rules considered in design. we are finding new rules we werent aware of while filling out the SES and ESF way to late
Design | Erica | Not all rules in the SES are in the rule book. BOTH have to be used as "rule books"
Controls | Kyle | Some mates will break in controls mainly because the assemblies are mostly direct to frame. Keep checking the assemblies for errors just incase as the frame changes throughout its design
Manufacturing | Luigi | Almac can't laser cut aluminum. They prefer just steel
Design/EL-CN | Dion | specifically define your design constrainst at the beginning of the design phase. This will help you focus your design to the bare bones
Design/EL-CN | Dion | Successful prototyping is very important before moving on to final technical designs. Spend most of your time on good prototyping and identifying design errors in this stage
Manufacturing/EL-CN | Dion | Break down your manufacturing tasks into reasonable chunks. For example, if you are assembling a PCB with many components, you can either bake SMT components all at once or organize soldering your components in sections of the PCB
Design | Farris | Always lock the part files before modifying to let other people know that we are working on the file - said by a lead
Design | Farris | Never delete CAD files, always store them to not lose track of modifications made previously.
General | Farris | When researching articles on websites, it is wise to store the article information by downloading them instead of inserting website links. Certain website links usually expire overtime.
Manufacturing | Luigi | Make sure that your Solidworks Part file is in IPS (inches) before you save as DXF so that the DXF file is in IPS. This would save Almac some time from converting from Metric DXFs to IPS.
Manufacturing | Luigi | Laser cutting machine can only take a minimum of like 6" x 6" of material. So even if your parts require less material, you need to order larger ones.
Manufacturing | Luigi | Size your material with a 1/4" margin for laser cutting. So add an extra 1/4" around the perimeter of the minimum material you would need for your part
Manufacturing | Luigi | Laser cutting general guide: hole diameters should be at least greater than the material thickness
Manufacturing | Luigi | Nest parts as much as possible into one sheet of material. This way, we'll save our laser cutting/ waterjet sponsors a LOT of time
Manufacturing | Claudia | Nickel is a hard metal to procure in Canada. Most Canadian metal companies get their's from the US and don't store them in-house. Your best bet will be to procure it from McMaster-Carr.
General | Claudia | When making meeting notes. First, continuously jot quick keywords as the meeting goes on and once it is done go back and make them more specific so that when you go back and read them you can easily remember what was discussed.
General/Design | Claudia | The ESF is also a great learning tool to help better understand the different components found within the electric powertrain and what exactly our goals should be when designing.
Design | Claudia | Make sure you always document your proof or reasoning behind specific thoughts when working on a research task. It's easy to forget why you thought something is true if you don't have supporting evidence to back it.
Procurement | Claudia | When purchasing from a local company where quotes are given double-check the quoted statement they give you. More importantly, make sure the tax is calculated correctly!!
Design | Fazle | The SES is another very important document to consult as you design especially for the structural aspects of your design (chassis, accumulator, attenuator) as the SES can be used as a tool to confirm whether your design meets rules. NOTE: just because it passes SES does not mean it passes rules
Design | Fazle | when designing mounts, make sure to work closely with the frame team as the mounting design Severely affects frame design
Design | Rami | A lot of the core design decisions that you are making can be decided by rules or previous work, ALWAYS look at the rules pertaining to what you're designing and have a look around in the drive for ANY notes about design.
General | Rami | After working on anything team-related, try to write some quick notes about what you learned so you can confirm that you've remembered them.
Procurement | Rami | If you've split up the design of one item to two different people, don't forget to check the mating together and that they fit together and that they are the proper sizes.
General | Mohammad | Try to always give yourself a bit more time than you think you will need for tasks and projects. You might run into complications or confusions that delay you.
Design | Edward | When coming up with a design for something, it's better to have a design on paper based on the given constraints so it's easier to conceptulize and modify things before transferring it to a "final format". (E.g for software development, you should write psedudocode (rough code) on paper and once you're satisfied you can write the actual code. Same can apply for designing parts in SolidWorks.)
Manufacturing/Electric Powertrain | Edward | When trying to figure out why something isn't working with software/hardware, systematically approach the problem and try to break it down into logical steps. (E.g Don't start changing multiple things at once or do guesswork. Identify potential root causes, break it down into smaller parts if needed and try to solve them one at a time.)
Frame Sub-items | Jibran | If you are making a floor or any part that has two separate segments that have bends, it might be a good idea to have those two segments as separate parts and mate them in an assembly
Safety | Jibran | If a harness tab geometry is simple enough, doing a simple hand calc to verify that it meets the load requirement may be enough
Social Media | Isabelle | Plan in advance, it's super important to be aware of which team members you need to talk to, when certain items should be posted, and how you want your content to look
Social Media | Isabelle | With any video/photo you want to post make sure they fit the specific dimensions so test them out before posting, I've created an account specifically for testing photos and content for instgram
Social Media | Isabelle | Talking to your team members about different content and when your posting is super important you want to make sure it's the same and consistent on each platform you're posting to
Design | Polina | Always include citations/ links to the resources you used for the reaserch. This saves time when you have to go back and reference the original document/forum.
Bodywork/Design | Jayan | Understand that just because we are desining a Formula 1 style car, it does not mean FSAE is Formula 1. So when researching bodywork (more so nosecone) stick to asking team members/leads about their knowledge and experinece with bodywork as this will not confuse FSAE vs F1. External sources such as the internet and race car books can be used ,but the reader should be mindful of the fact that those are written with respect to actual racing competitions. The significance is because the nose cone does not serve the same purpose for our car as it does in F1.
Bodywork | Jayan | It is worth mentioning that the nosecone is no longer considered an aerodynamic device (According to rules 2022). It is not concerned with producing downforce or any aerodynamic enhancements. Thus, when utilizing knowledge on aerodynamics and airfoils, keep in mind that it is independent to the nose cone.
Design/CAD | Rhythm | Try to make use of global variables in solidworks so that making changes to the geometry becomes more time-efficient, rather than going to each edge and changing the dimension, you can simply type the changed dimension in the global variables box
Design/3D Printing | Rhythm | Have a clearance of atleast 0.5mm between the enclosure's top and bottom pieces if it's going to be opened frequently and/or if you want it to open easily
3D printing | Rhythm | Save filament by doing a test-print at 60% scale or lower
Design/CAD | Rhythm | Make sure enclosure tabs are at least 15mm x 12 mm (in my experience) so that it prints nicely
Brakes | Daniel | Make records of the datasheet of the purchased parts (brake pads, calipers, etc.). Ideally, include an image or link to the datasheet in your design binder.
Brakes | Daniel | Start with one simple rotor CAD design (even blank rotor) and make sure the FEA works and makes sense. If it does, proceed with design improvement.
Brakes | Daniel | It can be hard to find supplier for desired material for the rotor so try to source early and keep in mind the availability of your chosen material. Aerospace suppliers have high performance rotor materials.
Brakes | Daniel | Print one dust shield for rear and one for front, then test fit (instead of printing 4 all at once). If it does not fit, less filament and time go to waste. If it fits, proceed 3D printing the rest.
Outboards | Daniel | When re-using parts, take time to clean and visually inspect the parts for scratches and cracks. Then, decide if it can be reused.
Outboards | Daniel | Be generous on greasing the bearings and be cautious in using the bearing puller
Tires | Daniel | Rotate tires (on-car or stored) to prevent deformities.
Tires | Daniel | Keep stored tires away from elements (sun, moisture, extreme heat/cold) and corrosive fluids.
Tires | Daniel | You can resize commercial tire covers to fit our tires. This is cheaper than buying specialized tire covers or buying materials to make tire covers from scratch.
Aero Structural | Simeon | Front mount should be as low as possible to not interfere with the nose cone
Design | Simeon | Consider as many loading scenerios as possible when doing FEA
Steering | Rochelle | Try to avoid using double u joint because they add complexity and weight
Brakes | Michael | Evaluate current practices of brake bleeding. Maybe easier methods of bleeding brakes
Design | Rob | Make the decisions with the information that you have. A design can always be improved and you will often only have so much information available. Find all of the information that you can and don't be afraid to make a conclusive decision to avoid pushing back crucial deadlines. Obviously, if there is not enough information to make an educated decision, then wait until you can find enough or ask for help on making the decision
Steering | Rochelle | Fasteners in the steering system must be critical fasteners
Design/3D printing | Michael | Altough we use CAD to aid in design of parts. Parts may still not fit in real world setting as a result of factors that were not accounted for and will require more renditions
Accumulator | Nick | Be aware of shortages of items that need to be purchased. If it can't be procured, its useless
Brakes | Michael | When selecting brake fluid be aware that although there are racing specfic fluids with better performance, they may not be as readily available as larger brands
Motor | Rob | When procuring, verify the part numbers. It can be very easy to delete or input an incorrect part number.
Steering | Rochelle | Ackerman steering mechanism reduces the friction and also reduces the steering effort and helps to take more sharp turns.
Motor | Rob | The motor size and power output should be reflective of the accumulator. A smaller motor may allow for a faster car. Additionally, if the accumulator cannot fully supply the motor, the ability to produce extra power from a large motor may go unused.
Accumulator | Nick | Packaging is one of the biggest challenges of accumulator design, and is one of the most important considerations when selecting cells
GLV | Nick | An understanding of STAR grounding an electrical interference in electric vechicles is key and should be considered early on
GLV | Nick | Consider putting connectors in CAD in as many places as possible, as the distance they stick out of components is often forgotten about
Frame | Erica | The accumulator side protection structure is meant to protect the batteries in the accumulator. The 2021 rule asked for a SIS like strucutre with the top tube below the upper SIS member or above the top of the accumulator, the 2022 rule required the entire upper tube to be at least 240mm higher than the lowest top surface of the lower SIS member. This will get more detailed in 2023. Read this rule carefully. confirm with others. and make sure you understand and apply it cause we had to get an exception to the rule in 2022 and that wont happen again. see frame deisgn binder 2021/2022
General - Communication | Farris | By default, Slack only notifies @mentions on the app. It is wise to change notifications to all messages to not miss key communication from members and delay the workload because of not being notified.
Design | Mujtaba | Using SolidWorks measure the approximate weight that the system would be. This will help in material selection in terms of the weight it would add to the system
Design | Mujtaba | Try to avoid adding more to a design to solve a problem and making it more complex in the process. Instead, brainstorm for simpler alternatives that would not have the problems in the first place.
Social Media | Isabelle | When posting graphics make sure the photos on the graphic are edited to make it look as clean as possible
ESF | Rami | When inputting values, make sure you have an idea of what you should be aiming for. (Look for other entries in the ESF, verify with other teams)
ESF | Rami | Ring Terminals are not usually current rated, only voltage rated and most of the time manufacturers don't know their current rating and just say "it's rated for the wire it accepts"
Accumulator | Claudia | UL has implemented a new card system for their 3D printing filaments. To guarantee that a 3D printed model has UL94-V0 properties its filament should have a UL blue card associated with it to tell you how to properly print with the filament.
Project Management | Erica | In our team fsaeonlince account there are two "team member" sections. One is for our previous IC cars (this has our old cost report and rules questions) and the top one if for our EV cars (this is the new one you should use to submit documents and fill out cost report). Make sure people only use the EV one (one at the top) to submit documents and use cost report. The IC one is only used to view our old cost report and rules questions
Manufacturing | George | Don't weld the bulkhead until the pedal box tabs have been fully welded
Manufacturing | George | When welding a large sheet metal part, like the a steel accumulator it will warp and deflect a lot. You need to account for this when figure out the space in the accumulator for the modules. Add extra tacks to minimize deflection. Try to do symmetrical tacks or welding. If possible, Completely clamp the floor and weld the walls after. If you be can completely assembly the walls and tack everything together while locked to minimize deflection. Really think about the welding steps (which wall you will weld first) before finalizing the design. You need to determine this based on how much access you will have to make a full weld. Maybe consider using other fastening methods instead of welding
Manufacturing | Erica | Make sure all dxfs are reviewed by all the people that they effect. The accumulator walls were missing holes that cost us more time in manufacturing
Manufacturing | Erica | Be careful when using the tab and slot feature. Always double check the slots match the tabs
Frame/ Manufacturing/ Drivetrain | Luig/George | make sure diff carrier frame mount holes are in the correct orientation when welding. if tube is upsidedown after you weld, you will have to re drill
Manufacturing/ Accumulator | George/Erica | When welding a large and multiple sheet part, like the accumulator, you MUST have the cad open or a picture and drawing present to make sure you are welding things in the proper orientation. We welded the accumulator walls in the wrong order, causing us to have to make modifications to the walls to fix the holes for the wires. The walls were already fully welded so if we tried to cut them off, we would have ruined the whole accumulator container.
Drivetrain | Erica | make sure to order bolts and seals for the diff well before taking it apart so you have everything ready. Read the manual to make sure you have the correct gear oil
cooling | erica | making the radiator moutning tabs and drilling the holes in the tubes in house is not easy or quick. i would suggest properly cading the rad tabs and geting them laser cut. and getting the square tubes cut with the holes for the tabs in them. that way mocking them up is much faster.
frame/ drivetrain | erica | make sure to double check any tube with a hole in it before welding it on the frame. VR3 welding the diff carrier tubes upside down so we had to weld them shut and redrill the holes which wasted a whole day.
manufacturing | erica | ALWAYS measure and check cad before welding, even if you think you know the orientation or the order to weld something
manufacturing | erica | if you have a jig, make sure its useful and works as otherwise it wastes a lot of time. it needs to set the distance between parts but must also set the distance of a part relative to a fixed frame (datum)
manufacturing/ welding | michael | ideally you want to tack and weld tabs when what ever you are mounting is bolted in. otherwise the tabs may deflect and you wont be able to get it in. this is true for the motor, suspension, diff carrier bolts, rad, etc.
manfuacturing | erica | if you need to get the frame done to paint it and you are waiting on a laser cut order, you can make the tab in house, it will just be less accurate
Accumulator/Testing | Edward | When running tests (fusible link test or any tests in general), try and figure out how to use the equipment properly beforehand. We spent more time than we should have trying to setup the current clamp to work with the oscilloscope when trying to measure current.
Design/GLV | Edward | When programming microcontrollers like the VCU that have many functions, break your code up into manageable chunks/make it modular within reason and test each function on it's own to verify what works and what dosn't. If you have many things that arn't working, it can be difficult to pinpoint exactly where the issue is coming from.
Manufacturing/EL-CN | Edward | When doing sensor calibration (APPS), make sure to define what your voltage operating ranges are based on rules + limits on what VCU can read beforehand.(VCU can only read up to ~2.9V) Spent too much time trying to empirically adjust the output voltage of each sensor, where these issues wouldn't have existed if the operating range/out of range values were choosen beforehand.
Manufacturing/ welding/ procurement | Erica | For anything that is welded and has a nut and a bolt, you need to order cheap regualr nuts for welding. you cannot use nylock lock nuts when welding because you destroy the nut and can cause a fire. so for example, when ordering bolts and nuts for the accumulator mounts, you should order the nylocks used to fasten it, and cheap regular nuts for welding (these will be used when fastening the accumulator into the car to mock up the mounts and weld them on the frame)
bodywork/ nose cone/ quotes/ procurement | Erica | it is extremely easy to delay sending out an order by 3-4 weeks or 2 months because of changes that need to be made to send things out. For ex: the nosecone quote was delayed by 2 months because we had to make little changes each week. this could have been avoided by doing one big review and making sure the changes are made within the week. also consider the time needed to make drawings, prepare step files and write the email. If this happens to the frame or other items, you can really delay the entire timeline
manufacturing/welding | Erica | you cannot "just weld" everything. welding takes a LOT of time and delays things because you have to weld everything before painting the frame. try to think of other methods to attach things and use it. riveting, using fasteners, etc. this is also true for welding on brackets for mounts
manufacturing | Erica | when making the manufacturing timeline, consider what needs to be manufactured, built and assembled and include that into the timeline. For ex: the accumulator needs to be fully tacked or welded to weld the accumulator mounts on the frame, and drivetrain needs to be present to mock up the diff studs.
manfuacturing/drivetrain | erica | make sure the leads have a clear understanding of the mounting method and make sure ALL FASTENERS are in cad. We had to cut off and re-weld the diff carrier studs 3 times this year, first because VR3 welded the tubes upsidedown so the hole pattern was wrong and then because the studs were too short.
manufacturing/ design | Erica | there needs to be more manufacturing centered reviews during design. there are so many assumptions we made in design that are causing us a lot of time and heart ache in manufaacturing.
manfufacturing | Erica | everything that needs to be laser cut or water jet to be welded on the frame or is needed to jig something that is welded on the frame needs to be sent out early and all together. We had to send multiple laser cut and water jet orders to get everything we needed to weld, and somethings were still sent out too late so we had to make them in house. Making tabs in house is not efficient.
manufacturing | Erica | STANDARDIZE BOLT SIZES. either do all metric or all imperial. and try to have the same bolt sizes on all parts. there is no reason that one subystem or assembly has 5 different bolt sizes.
manufacturing/ drivetrain | Erica | be cautious of non symmetrical parts. make sure both the left and right side of the part is sent for laser cuting or water jetting with different names. This year we had 6 of the right side jacking bar plates. but the right and left are not symmetrical, so we had to make them in house which took a lot longer and delayed preping other things for welding
manufacturing/ welding/ argon | Erica | to order Argon, go talk to Alan. He will basically order it for us and exchange the tanks we have in the shop. DO NOT ORDER IT ON YOUR OWN. otherwise you have to have someone pay the $300 deposit per tank which you only get back when u return the tanks, which is also a lot of work and sketchy to do
shop/ project management | Erica | is something is wrong, brocken or damaged in the shop and it wasnt the teams fault, ask Rose is there is a way for the school to fix or replace it. We shouldnt have to work with brocken things and we should have to take basic necessities out of our budget. For ex: two of our cabinets were broken and it risks the cabinets falling over on someone because the drawers wouldnt locked so I asked Rose if the school could cover replacements and we got them replaced. We also had a leak in the shop that destroyed one of our computers so Rose replaced it for us. Dont take adavantage of this but also dont live with things that are broken and cause more work for yoruself
procurement/ design/ sponsorship | Erica | when selecting components, materials or anythig we have to purchase, each lead should always attempt for sponsorship first. This could be asking the company to donate the component or provide a discount. A discount is still sponsorship, especially if we need it and plan to buy it anyway. A lot of companies has student discounts or fsae discounts. For ex: we got 50% off all our wiha insulated tools
manufacturing/ frame sub items | Erica | laser cut and water jet cannot cut 0.025" material.
manufacturing | Erica | if there is a part or parts that require a sponsor to manufacturing them or requires a large manufacturing effort from a sponsor, you NEED to talk to the sponsor in advance. You need to confirm and get them to commit to doing the work. you need to make sure they are able to handle the volume or number of parts. you need to see if there are any design changes that you need to make to improve manufacturability. and you need to see if what you want to do is even possible. For outboards, we wanted to make titanium hubs, we got the material and designed them, but all our manufacturing sponsors said it was too hard to machine so they couldnt make it. For accumulator, we just assumed we could 3D print 120 battery modules our selves or a sponsor would help, but we never got a sponsor to commit, so we ended up taking 2 months to get them and we have to pay $4k to get 50 of the printed and then tried to print the rest from home. this severly delayed our timeline. For water jet and laser cut, some materials they cannot cut. like Almac wont do aluminum and waterjet and laser cut cant cut really thing materials. so you should ask them ahead of time so they dont send it back and then we have to make it
controls/dash/ sheet metal manufacturing | Erica | Certain considerations need to be made when designing a sheet metal part that has bends. Some items are, if there is a bend close to a hole, a refief notch needs to be added so when the hole does not distort when you bend. If there is a large cut out in the part, you will have a problem bending it because there is not material towork with (large holes will result in the part distoring). Make sure to leave clearnae, at least half an inch or more, between the bend line and other feature
Controls, dash | Erica | we had multiple problems when manufacturing the RF-22 dash. We tried to print a drawing from cad to mark the bend lines but the drawing was off. The drawing was printed upside down and cad wasnt checked, too the bends were the wrong way resulting in the dash being upside down (this affects the drivers cause they are trained with the E stop on the right). there was a bend very close to holes and the holes distored. a relief notch was added and the holes didnt distort further. There was a large hole for the electronic dash which removed a lot of material and left a really small ledge that would not bend because it was so small. The dash didnt fit very well in the frame after bending. The dash had to be re-bent because it was upside down. the moutning solution was also changed in the shop. originally riveting was chosen but the dash did not mate with the frame well so it was decided to zip tie it. new holes had to be drilled. The tsal and other lights hole sizes were known so we had to drill those out in house (takes more time, measurements could have been done before hand to put into the dxf). Future designs should depend less on the frame and should be easier to adjust or modify
Firewall/ frame sub items | Erica
Design/Competition/Michigan/ Team Captain | Erica | the spec sheet and ESF need to be filled out at the end of design in the summer. The design briefing powerpoint is a lot more work the the previous document so it should be started well in advance. Probably done over winter break. I only looked at it 3 weeks before the deadline which is on the day of my last exam which was not smart
design/competition/design briefing | Erica | dont start the design briefing and spec sheet at the beginning of final exams. spec sheet should be done at the end of design and the design briefing over winter break. it is a lot more work than it used to be. also make sure to have an entuire team help you. there should be 1-2 people per section of the design brief powerpoint
Accumulator. Fusible links | Erica/Edward | need an accurate way of cutting the nickle strips for the fusible links cause the width needs to be very precise and we need a lot of them so its very time consuming
frame/brakes/controls | erica | if the front bulkhead is large and requires by rules a diagonal member, make sure the diagonal member goes from the bottom left to the top right, allowing full travel for the brake pedal. otherwise it is difficult to fully bleed brakes. although confirm this will not be a problem with throttle travel first with controls
design/bolts | erica | BOLTS AND NUTS NEED TO BE IN CAD SO YOU CAN PROPERLY SIZE THE LENGH AND MAKE SURE IT IS NOT TOO LONG TO HIT SOMETHING AND NOT TO SHORT. TWO THREADS MINIMUM MUST SHOW
manufacturing/GLV | Edward | When plugging in electrical connections, ALWAYS make sure the wiring connections are correct before turning on/applying power. Ended up frying the VCU during testing, since accidently plugged in 12V to one of the pins to simulate high signal, thinking it was 5V. Could have easily been avoided if just double checked connections.
Design/bolts | Rhythm | Don't use M3 bolts to mount enclosures, use M4 minimum and Hex heads are probably easiest (depending on mounting position)
Design | Rhythm | Confirm physical measurements of a part, before designing an enclosure or mount for it, do NOT just trust the websites downloadable CAD file
Manufacturing Nosecone | Rhythm | When sanding corners or contoured edges with an orbital, use a sanding disk with a sponge between the disk and orbital to get a smooth finish
Manufacturing Nosecone | Rhythm | The first layer of the female mold is the most important, make sure to get a smooth and tight first layer, so less sanding and fill-up of holes is required
Manufacturing Nosecone | Rhythm | Try to always use microballoons and cabosil + epoxy to fill up holes, rather than spot putty
Manufacturing Nosecone | Rhythm | If spot putty is used to fill in holes in the spot putty, then apply very thin layers because it'll take SIGNIFICANTLY less time for it to dry, then reapply until the hole is filled (I found that you can wet sand thin layers after 5 minutes of applying)
Manufacturing Nosecone | Rhythm | If the nosecone has scratches/ white lines? Apply epoxy over the entire nosecone and the marks will go away (apply it all over the nosecone so there's an even amount of epoxy all over)
Design/manufacturing | Rhythm | Ensuring 3d printer enclosures are waterproof by doing a water test, apply epoxy around the outside or anneal the enclosure if needed
| Matthew | Like space out your drinks a little bit
Communication | Matthew | USE SLACK CHANNELS NOT DMS UNLESS IT"S ACTUALLY PRIVATE. Impossible to have knowledge of like anything thats going on without bugging the **** out of everyone without this
Communication | Matthew | We either need a slack sponsorship (to get premium) or use a different platform
Vehicle Dynamics | Matthew | It is really important to have sensors on the car if it is running, get VD team to figure this out if electrical team is busy, sensors can be cheap; it's better than nothing. Having the sensors helps not only for knowledge of that specific car but for VD knowledge in general. Look at past sensor data if it's not possible to get sensor data from current car
Knowledge Transfer | Matthew | Keep alumni in the loop (like me pls) and get their advice whenever possible if they are willing; do frequent design reviews or something
Planning | Matthew | Keep your third eye on the tracker and update it frequently
Rendering | Farris | Make sure to render the high quality renders although it takes time. Its better to wait for better render results than to render lower quality. The 30 fps is the ideal option for video renders as it produces good end result.
Business presentation | Isabelle | Every logo on the car is seen as a resource use them to your advantage, ask them questions
Business presentation | Isabelle | Short stories, story telling is great to try to sell something, makes a personal connection
Business presentation | Isabelle | Wear all black, monochromatic looks more professional and is proved to help calm you down
Business presentation | Isabelle | Never say thank you on the last slide, don't open it up for questions assume you've given a presentation for no questions, conclude it instead
Business presentation | Isabelle | 5 by 5 rule, 5 bullet points, 5 words
Business presentation | Isabelle | Make sure font is bigger than 28
Business presentation | isabelle | Always introduce yourself to board of directors, e.g chief marketing officer, helps direct questions
Business presentation | Isabelle | When refering tomarketing use social media platform insights, shows target audience, age range, and location (use a table to show this information not a screenshot)
Recruitment | Isabelle | For business recruitment go to classes to talk to students, ask professor if they can do something for extra credit, e.g graphic design helps make a poster
Recruitment | Isabelle | Fill out a skill set when hiring to have them rank themselves
Recruitment | Isabelle | Make SAE sound relevant outside of engineering, mention big companies we work with
Recruitment | isabelle | Use a barcode for students to access form quickly
Outreach | Isabelle | Use other school teams to your advantage e.g TMAV (drone team), invite them to testing to film content for you and them, looks good to the school
3D Printing | Farris | Always consult about your design dimensions with an upper lead before 3D printing. Saves time and effort to redesign a new one because our own idea doesnt work out.
Competition | Isabelle | Take the time to talk to other teams about business strategies
Sponsorship | Isabelle | Talk to co-op and the companies they deal with
Sponsorship | Isabelle | Use DM's to reach out to companies
Sponsorship | Isabelle | Find personal work emails to connect to sponsors
sponsorship | Isabelle | If we've been buying products from a company for a while mention how we've been a loyal customer to get a discount
Business presentation | Isabelle | Use alumni to your advantage
Business presentation | Isabelle | If we're still a car company mention that you own the vehicle and how you did field testing
Business presentation | Isabelle | Canadian vs American spelling, make it consistent
Business presentation | Isabelle | Use powerpoint tool to highlight data to give graph suggestions
Business presentation | Isabelle | Put laptop on do not disturb
Business presentation | Isabelle | what you plan to be is good. but scale it back to what your doing now and in the past and what you want to do to fix things
business presentation | isabelle | Mention safety for workers, what are the problems of EV vehicles
business presentation | isabelle | If online again, use e charisma for zoom calls, gesture in front of rib cage
Suspension | Matthew/Luigi | Find wider inboard control arm bearings to avoid the use of washers
Suspension | Matthew/Luigi | When tacking tabs onto frame, use a slightly wider spacer than needed to avoid clamping whatever is rotating
Suspension | Matthew/Luigi | Do more analysis to justify design decisions such as aiming for a specific track width or motion ratio, for example ChassisSim, yaw moment diagrams
Suspension | Matthew/Luigi | Set up multibody model to simulate suspension linkage movement and plot results, such as in Simscape Multibody
Suspension | Matthew/Luigi | For teams new to VD simulation, use existing software rather than trying to create our own for understanding
manufacturing/ testing | Edward | Always read and re-read instructions carefully before doing testing procedures and think through what you are doing before you actually do it. All it takes is one wrong connection or short to occur to fry equipment.
manufacturing/ testing | Edward | When working on software / firmware, always have the code that you know works stored somewhere, so you can revert back to something if you broke it after making a change. (i.e Use Github)
Frame | Jeff | Consideration should be given to eventual HV wire routing while designing relevant parts of the frame e.g. motor controller shelf on tm-23
Electric Powertrain | Claudia | When re-flashing thermister expansion modules make sure it is a .txt file! not hex
Electric Powertrain | Claudia | When re-flashing the thermister modules, make sure no other components are on the same CAN line
Electric Powertrain | Edward | When wiring devices up that communicate with eachother, ALWAYS make sure the ground (GND) lines are connected together. (I.e CAN GND on one device needst to be connected to CAN GND on the other device.) Voltages always need to be measured against a reference point (i.e ground)
General | Edward | First step to solving a problem is figuring out whether the problem even needs to be solved or not. Time can be wasted on trying to solve a problem that dosn't need to exist in the first place / isn't actually a problem.
Electric Powertrain / Software | Edward | First time you write software it probably isn't the best. It is better to write quick functional code that can be tested and can get feedback on and make itertations on, then trying to write perfect code the first time.
Design | Edward | For any big designs/redesigns, these should planned out well in advance before undertaking them. Figure out the designs objectives, goals, major milestones any lead times expected and hash it out as early as possible. Your plan should have decision-making built into it, to figure out how to progress if things need to change. (I.e If we are able to complete X by certain deadline then we should do Y, otherwise should do Z). Last thing you want it to be stuck having to fix a design with limited time and resources because it wasn't planned out properly in advance.
Send Out | Rhythm | Hold a meeting to go over the sendout etiquette & how to create drawings and DXF's PRIOR to starting the files
CAD | Rhythm | Have all system leads re-iterate to their leads that pdf drawings & files NEED to be placed into the send-out folder NOT KEPT IN THEIR INDIVIDUAL FOLDERS IN THE CAD FOLDER
Send Out | Rhythm | Double check all metal dimensions that someone else labelled - NEED to have the correct metal & files going to sponsors

## HV SafetyTools Procurement (hidden)
Status | Approved? | Item | Description (Size/Type) | Quantity | Spares | Total Qty. | Unit Price (CAD) | Shipping Cost (CAD) | Total Cost (CAD) | Vendor Name | Part No. | Link | Comments | Option 2 | Purchase or Sponsor | Plan | Delivered

## Single purchases (hidden)
PURCHASER:
Shipping Cost: